MONITORING REPORT

ON THE IMPLEMENTATION OF THE ACTION PLAN FOR THE STATE REGIONAL DEVELOPMENT STRATEGY IN 2025

| Strategic Objective* | Measures* | Implementation Pedriod* | Performance Indicators* | Implementation Status (Completed / Started / Not Started / Ongoing / Other) | Results Achieved | Expenditure on the Implementation of the Measure, UAH thousand |  |  | Challenges Affecting Implementation (including underlying causes and mitigation measures) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  | State Budget | Local Budget | Other Sources |  |
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |
| Strategic Objective: Building a Cohesive State across Social, Humanitarian, Economic, Climate, Environmental, Security and Territorial Dimensions |  |  |  |  |  |  |  |  |  |
| Specific Goal 1: Ensuring the Integrated Development of Territories, Taking into Account the Interests of Future Generations |  |  |  |  |  |  |  |  |  |
| Area “Promoting Territorial Development” |  |  |  |  |  |  |  |  |  |
| 1.Undertake priority measures to ensure public safety, support recovery and stimulate economic activity in territorial communities designated as recovery territories. | Preparation of Comprehensive Spatial Development Plans for Territorial Communities | 2025-2027 | Draft Comprehensive Spatial Development Plans prepared for at least 50 territorial communities | Ongoing | Vinnytsia Oblast Out of 63 territorial communities in Vinnytsia Oblast, 19 have adopted decisions to prepare Comprehensive Spatial Development Plans for Territorial Communities (CSDPs). Of these, the plan has been approved in the Vinnytsia Territorial Community, while the CSDPs for the Yampil and Horodkivka Territorial Communities are currently under preparation. |  |  |  | Vinnytsia Oblast Limited financial resources available in local budgets for the preparation of spatial planning documentation. |
|  |  |  |  |  | Dnipropetrovsk Oblast 16 territorial communities have adopted decisions to prepare CSDPs. One Comprehensive Spatial Development Plan has been completed. | Dnipropetrovsk Oblast 2 009,80 | Dnipropetrovsk Oblast 250,00 |  | Dnipropetrovsk Oblast In 2023, the remaining balance of the state subvention, amounting to UAH 1,466.05, was returned to the State Budget. The validity of the Cabinet of Ministers of Ukraine Resolution No. 853 of 28 July 2021 has expired. |
|  |  |  |  |  |  |  |  |  | Donetsk Oblast At present, all settlements in Donetsk Oblast are located within 100 kilometres of the administrative boundary between the temporarily occupied territory and the territory of Ukraine affected by active hostilities, including the line of combat engagement. Given the prevailing security conditions and the adverse living environment, the preparation of spatial planning documentation is either not feasible or not justified. |
|  |  |  |  |  | Zhytomyr Oblast 40 territorial communities have adopted decisions to prepare CSDPs. The design phase has commenced in the Novoborivska Settlement Council. |  | Zhytomyr Oblast 886,9 |  | Zhytomyr Oblast Lack of up-to-date base maps for the territory of the territorial community. Conducting topographic surveys requires substantial financial resources and is also particularly difficult during the period of martial law. Insufficient funding from local budgets for the preparation of planning documentation. The solution to the problem lies in ensuring adequate funding by territorial communities (including, where possible, funding from other sources not prohibited by law) and carrying out all procedures required for the preparation and approval of CSDPs. |
|  |  |  |  |  | Zakarpattia Oblast Implementation of the measure has commenced in 11 territorial communities. The measure is currently at the preparatory stage: decisions to develop Comprehensive Spatial Development Plans have been adopted, baseline data are being collected, the terms of reference for plan preparation are being developed, and the cartographic base is being prepared. Strategic planning sessions have also been conducted. |  | Zakarpattia Oblast The total expenditure incurred for the implementation of the measure amounted to UAH 2,768.6 thousand, financed from the local budget. Additional funding was mobilised under the USAID HOVERLA grant project (the amount is being уточнено). |  | Zakarpattia Oblast Lack of funding and allocation of financial resources from the state budget, local budgets and other sources; the need to attract international partners and assistance to support the process; shortage of qualified personnel at the local level; understaffing of authorised urban planning and architecture authorities; excessive workload of the authorised authorities due to tasks that do not fall directly within the remit of urban planning and architecture authorities (including accessibility, civil protection, housing and communal services, defence activities, mobilisation, environmental protection and infrastructure). Impact on the implementation of the measure: Slower progress during the preparatory stage and the preparation of Comprehensive Spatial Development Plans; limited resources for the collection and analysis of baseline data; delays in organising strategic planning sessions and preparing the cartographic base. Mechanisms for addressing the challenges: Identification of additional funding sources, including international assistance; methodological and advisory support for territorial communities; optimisation of tasks and prioritisation of the functions of authorised authorities; capacity-building and the temporary engagement of experts and/or temporary staff to ensure the continuity of the process. |
|  |  |  |  |  | Zaporizhzhia Oblast As a result of the full-scale invasion by the Russian Federation, 87% of the territory of Zaporizhzhia Oblast is currently either temporarily occupied or located in areas of active hostilities, affecting 54 out of 67 territorial communities (Order No. 376 of the Ministry for Communities, Territories and Infrastructure Development dated 28 February 2025, as amended; hereinafter – the Ministry for Communities, Territories and Infrastructure Development Order). The remaining part of the oblast (13 territorial communities) is located in the area of possible hostilities and is classified as the "orange zone"—territories situated within 25–70 km of the active combat zone (high security risk) and under the constant threat of Russian attacks. To date, four territorial communities in Zaporizhzhia Raion (Vilniansk Urban Territorial Community, Kushuhum Settlement Territorial Community, Mykhailo-Lukashivka Rural Territorial Community, and Shyroke Rural Territorial Community) have adopted decisions to prepare Comprehensive Spatial Development Plans for Territorial Communities (CSDPs). Following requests from the Kushuhum Settlement Territorial Community and the Vilniansk Urban Territorial Community, the Oblast State Administration has provided information on the state interests to be taken into account during the preparation of the Comprehensive Spatial Development Plans. A corresponding request from the Shyroke Rural Territorial Community is currently under consideration. |  |  |  |  |
|  |  |  |  |  | Kyiv oblast The preparation of Comprehensive Spatial Development Plans for Territorial Communities (CSDPs) has commenced in 8 territorial communities: Bohuslav Urban Territorial Community, Obukhiv Urban Territorial Community, Dymer Settlement Territorial Community, Kotsiubynske Settlement Territorial Community, Kalyta Settlement Territorial Community, Hatne Rural Territorial Community, Pirnove Rural Territorial Community, and Tashan Rural Territorial Community. |  | Kyiv Oblast 21000,0 |  | Kyiv Oblast Due to the limited financial capacity of the budgets of territorial communities and the Kyiv Oblast budget to finance the preparation of Comprehensive Spatial Development Plans for Territorial Communities (CSDPs), as of 31 December 2025, only 12% of the territorial communities in the oblast had commenced the preparation of these plans. The solution to this issue is possible only through the mobilisation of funding from state budget subventions and international technical assistance. |
|  |  |  |  |  | Kirovohrad Oblast Local self-government bodies have adopted 20 decisions on the development of Comprehensive Spatial Development Plans for Territorial Communities (CSDPs). In 2025, 8 detailed territorial plans outside the boundaries of settlements were developed and approved. As of January 1, 2026, the following exist within the region: - 759 general plans; - 179 zoning plans; - 359 detailed territorial plans (of which: 246 within settlement boundaries, 113 outside settlement boundaries). District spatial planning schemes are not being developed. The Department of Regional Development, Urban Planning and Architecture of the Kirovohrad Regional Military Administration has sent a request to the "Archizem" design organization for a commercial proposal regarding the development of a 1:100,000 scale topographic/cartographic base. |  |  |  |  |
|  |  |  |  |  |  |  |  |  | Luhansk Oblast According to Order No. 376 of the Ministry for Communities, Territories and Infrastructure Development dated 28 February 2025, the greater part of Luhansk Oblast is classified as temporarily occupied territory, while the remaining part is classified as territories of active hostilities. Accordingly, the implementation of the measure will be possible following the de-occupation of the oblast's territory, the cessation of active hostilities, and the implementation of security and stabilisation measures. |
|  |  |  |  |  | Lviv Oblast Decisions on the preparation of Comprehensive Spatial Development Plans for Territorial Communities (CSDPs)have been adopted in 66 territorial communities. Working groups have been established in 8 territorial communities. |  | Lviv oblast 11020,0 |  |  |
|  |  |  |  |  | Mykolaiv Oblast As of 31 December 2025, CSDPs had not been prepared in the oblast. Local self-government bodies are carrying out work on the preparation of the Comprehensive Spatial Development Plans. |  |  |  |  |
|  |  |  |  |  | Odesa Oblast 48 territorial communities adopted decisions on the preparation of CSDPs. 14 territorial communities submitted requests to the Odesa Oblast State Administration for the determination of state interests to be taken into account during the preparation of the CSDPs. 8 territorial communities approved the terms of reference. 1 territorial community is preparing a CSDP (final stage). |  | Odesa Oblast 17000,00 |  | Odesa Oblast The delayed preparation of CSDPs is caused by the lack of adequate funding in local self-government bodies, the significant outflow of the population, including entrepreneurs, specialists in the preparation of urban planning documentation, and officials of local self-government bodies, as well as the lack of priority given to addressing this issue at the state level. At present, the Law of Ukraine introducing amendments to a number of legislative acts, including the Law of Ukraine "On the Regulation of Urban Planning Activities", has entered into force. The amendments effectively extend the deadline for the preparation of CSDPs from 2025 to 2028. This provides legal grounds for addressing urban planning issues without CSDPs, solely through the preparation of Detailed Territory Plans. Thus, on the one hand, territorial communities need to accelerate the preparation of CSDPs and master plans of settlements (where such plans are absent or require updating). On the other hand, there are a number of objective reasons due to which this process is delayed. |
|  |  |  |  |  | Poltava Oblast 35 territorial communities commenced the preparation of CSDPs: in 4 communities, the contractor has been selected and the preparation is underway; in 5 communities, working groups have been established to approve the terms of reference; and in 26 communities, decisions on the preparation of CSDPs have been adopted. | Poltava Oblast 2611,9 | Poltava Oblast 6254,0 |  | Poltava Oblast The lengthy timeframe and high cost of preparing CSDPs require co-financing from the state budget and other funding sources. |
|  |  |  |  |  | Rivne Oblast Measures for the preparation of CSDPs are being implemented in the oblast. At present, the Shpaniv and Varashterritorial communities are at the final stage of preparation. Another 20 territorial communities in the oblast have adopted decisions on the preparation of CSDPs and are carrying out organisational measures to prepare the baseline data and identify the developers of the urban planning documentation. | Rivne Oblast 19363,1 | Rivne Oblast 13134,8 |  | Rivne Oblast During the implementation of measures for the preparation of CSDPs, a number of challenges arise. The high cost of preparing urban planning documentation creates a financial burden on local budgets and may affect the timely payment for completed stages of work. Mechanism for addressing the challenge: Phased financing of the works, as well as exploring opportunities to attract international technical assistance and state support programmes. The limited number of design organisations with the relevant experience and qualifications to prepare CSDPs results in longer implementation periods. Mechanism for addressing the challenge: Conducting information and awareness-raising activities among design organisations, engaging additional contractors, and improving the qualifications of specialists in the field of spatial planning. |
|  |  |  |  |  | Sumy Oblast 7 territorial communities in the oblast commenced the preparation of CSDPs. |  |  |  |  |
|  |  |  |  |  | Ternopil Oblast In the oblast, 12 communities have adopted decisions on the preparation of CSDPs. The Zalishchyky Territorial Community has prepared the terms of reference for the CSDP, the Baikivtsi Territorial Community has commenced the collection of information for the preparation of the CSDP, while the remaining communities are at the decision-making stage. |  |  |  |  |
|  |  |  |  |  | Kharkiv Oblast CSDPs have been prepared for 3 territorial communities: Rohan, Pisochyn, and Solonytsivka. |  |  |  |  |
|  |  |  |  |  | Kherson Oblast The preparation of CSDPs has not commenced in the oblast. The relevant activities have not been initiated in the majority of territorial communities, contracts for the preparation of urban planning documentation have not been concluded, and funding for such work has not been allocated. |  |  |  | Kherson Oblast The main challenges affecting the implementation of the measure are: 1) limited local budget resources, which make it impossible to commission the preparation of CSDPs; 2) the need to prioritise the restoration of damaged infrastructure facilities, as a result of which the preparation of urban planning documentation has been postponed; 3) the difficult security situation in de-occupied and frontline communities, which complicates field surveys, the collection of baseline data, and the implementation of project activities. Accordingly, implementation of the measure will be possible after the stabilisation of the security situation, the de-occupation of the oblast's territory, and subject to adequate funding from the state and/or local budgets, as well as the mobilisation of other funding sources not prohibited by the applicable legislation. |
|  |  |  |  |  | Khmelnytskyi Oblast 2 CSDPs have been prepared: - Medzhybizh Territorial Community – the CSDP was approved in 2024; - Sataniv Territorial Community – the draft CSDP has been prepared, with approval planned for 2026. | Khmelnytskyi Oblast 2094,5 | Khmelnytskyi Oblast 865,6 |  |  |
|  |  |  |  |  | Cherkasy Oblast In 2025, measures for the preparation of CSDPs were carried out in the Shpola, Korsun-Shevchenkivskyi, Ruska Poliana, and Biloziria territorial communities at various stages of preparation, including the compilation of baseline data, preparation of the terms of reference, conclusion of contracts, and preparation of design documentation. |  | Cherkasy Oblast 12987,8 |  |  |
|  |  |  |  |  | Chernivtsi Oblast Implementation of the measure has not commenced. |  |  |  | Chernivtsi Oblast The preparation of CSDPs is hindered by the limited financial resources of territorial communities under martial law, the substantial volume of required baseline data, the complexity of preparing and approving the documentation, and the insufficient number of qualified specialists at the local level. |
|  |  |  |  |  | Chernihiv Oblast 1 CSDP has been prepared. |  | Чернігівська область 5547,8 | Чернігівська область 8000,0 |  |
|  | 2) Conducting surveys and clearing territories, forestry land, valuable natural areas, including the territories and sites of the Nature Reserve Fund, water bodies, water fund land, and production facilities of explosive ordnance. | 2025-2027 | Primary non-technical surveys were conducted, and clearance operations were carried out in territories and water bodies (except for territories and water bodies where hostilities are ongoing and within the 20-kilometre zone from the line of combat contact) to remove explosive ordnance. | Ongoing | Ministry of Defence of Ukraine During the reporting period, the units of the security and defence forces, as well as mine action operators, were not engaged in planned activities for the detection, removal and disposal of explosive ordnance in forestry land, valuable natural resources, Nature Reserve Fund sites, water bodies, and water fund land in the de-occupied territories. At the same time, it is reported that, since the beginning of the Russian Federation's full-scale military invasion of Ukraine, as of 31 December 2025, mine action operators have identified 74.01 km² of contaminated/suspected hazardous areas (natural resources). Following repeated non-technical surveys, clearance certificates were issued for sites covering a total area of 2.7 km², while 4.04 km² of territories (natural resources) have been cleared. In addition, during 2025, the security and defence forces surveyed a total of 14.63 km² of forest land and 112.39 km² of water areas. |  |  |  | Changes in the security situation and the Russian Federation's use of remote mining methods and cluster munitions result in the re-contamination of areas and the need to conduct surveys in territories that had previously been considered free of evidence of explosive ordnance risks. |
|  |  |  |  |  | Ministry of Internal Affairs of Ukraine In 2025, the pyrotechnic units of the State Emergency Service of Ukraine carried out the following activities: under humanitarian demining, primary non-technical surveys were conducted over 249,809 ha, and technical surveys (demining) were carried out on 475 ha, including approximately 0.75 ha of forestry land; under operational demining, territories covering a total area of 25,499 ha were cleared, including 1,336 ha of water areas. This included the clearance of approximately 4,600 ha of agricultural land in accordance with the Action Plan for the Survey of Agricultural Land for Explosive Ordnance. During 2025, the Explosive Ordnance Disposal Units of the National Police of Ukraine carried out more than 53.4 thousand deployments in response to incidents involving explosive materials, including nearly 3.7 thousand deployments for the clearance of terrain (sites) of explosive ordnance and 27 deployments in water areas. The total area cleared of explosive ordnance exceeded 6.3 thousand hectares. | Ministry of Internal Affairs of Ukraine Within the expenditures allocated under the State Budget of Ukraine under Budget Programme 1007020 "Ensuring the Functioning of the Bodies, Institutions and Establishments of the National Police of Ukraine." |  |  |  |
|  |  |  |  |  | Shipping Administration During 2025, the Shipping Administration did not receive any requests to conduct primary non-technical surveys or to carry out the clearance of territories and water bodies of explosive ordnance. |  |  |  |  |
|  | 3) Ensuring the implementation of humanitarian demining of agricultural land. | 2025—2027 | Compensation was provided to at least 10 agricultural producers for the humanitarian demining of agricultural land. | Ongoing | Ministry of Economy of Ukraine This indicator is being implemented under Budget Programme 1201420 "Compensation for the Costs of Humanitarian Demining of Agricultural Land" (hereinafter – Budget Programme 1201420). At the same time, it should be noted that, pursuant to the Law of Ukraine "On the State Budget of Ukraine for 2026", the name of Budget Programme 1201420 was changed to "Humanitarian Demining". Since the launch of Budget Programme 1201420, as of 27 March 2026, 15,111.9 ha of agricultural land have been cleared and returned to productive use. 73 agricultural producers have received compensation for the costs of humanitarian demining of agricultural land. | 884409,8 |  |  |  |
| 2. Identifying Priority Areas for the Sustainable Development of Mountain Areas and Creating the Necessary Conditions for the Comprehensive Resolution of Existing Economic, Infrastructure, and Social Challenges | Identification of functional types of territories | 2026 | Resolution of the Cabinet of Ministers of Ukraine adopted | Completed | Ministry for Communities, Territories and Infrastructure Development Article 112 of the Law of Ukraine "On the Principles of State Regional Policy" stipulates that the composition of the functional types of territories of Ukraine shall be approved by the Cabinet of Ministers of Ukraine within the State Regional Development Strategy of Ukraine. To implement the provisions of the Law, the Ministry for Communities, Territories and Infrastructure Development developed, and the Cabinet of Ministers of Ukraine adopted, Resolution No. 1493 of 19 November 2025 "On the Definition of the List of Functional Types of Territories and the Requirements for Indicators Used to Classify Territories into Different Functional Types", which approves the requirements for the indicators used to classify territorial communities into different functional types of territories. On 19 November 2025, the Government adopted Resolution No. 1493, defining the list of functional types of territories and the requirements for the indicators used to classify territories into different functional types. . On 12 December 2025, the Government adopted Resolution No. 1686, amending the State Regional Development Strategy for 2021–2027, approved by the Cabinet of Ministers of Ukraine Resolution No. 695 of 5 August 2020. The amendments, inter alia, approved the list of functional types of territories, updated the regional development priorities through 2027, and ensured their alignment with the priorities and approaches of the European Union Cohesion Policywith a view to strengthening Ukraine's integration into the European regional policy framework. To ensure the implementation of these Government decisions, the Ministry for Communities, Territories and Infrastructure Development, by Order No. 299 of 17 February 2026, updated the composition of the Commission for the Assessment and Classification of Territories into Functional Types (hereinafter – the Commission). A comprehensive process of collecting and consolidating information from ministries, central executive authorities, and oblast military administrations was carried out. The data were updated as of 1 January 2026. Based on the information received, territorial modelling for Ukraine was conducted. The Commission is currently holding meetings to adopt decisions on the classification of territorial communities into specific functional types. Following the Commission's work, a draft resolution amending the State Regional Development Strategy will be prepared and submitted to the Government for consideration. |  |  |  |  |
| 3. Establishing effective instruments for implementing the State policy to support the development of rural areas, taking into account the EU accession criteria and Ukraine's international legal obligations in the field of European integration. | 1Establishment of a joint network based on the Agricultural Knowledge and Innovation System (AKIS), accessible to advisers of public and private institutions and organisations in the agricultural sector. | 2026 | A joint network based on the Agricultural Knowledge and Innovation System (AKIS) has been established. | Ongoing | Ministry of Economy of Ukraine 1.During 2024–2025, the conceptual and organisational model of the Agricultural Knowledge and Innovation System (AKIS) was developed, providing for the establishment of a network of 8 regional hubs serving as centres for the integration of science, education, advisory services, and business. 2.Cross-sectoral cooperation among the key participants of the system (public authorities, research institutions, educational institutions, advisory services, and businesses) was ensured through a series of training and information events. 3.The Coordination Council on the Functioning of AKIS was established as a permanent advisory and consultative body to ensure strategic governance and policy coordination. Its first meeting is scheduled for April 2026. 4.Preparations for the launch of the Unified State Platform for the Agricultural Knowledge and Innovation System (AKIS) are being finalised. The platform will serve as a digital tool for interaction among system participants and for the dissemination of knowledge, innovation, and best practices. Its launch is scheduled for April 2026. The platform is currently being populated with content, including case studies, research findings, and technological solutions. |  |  |  | Limited financial resources, in particular the absence of stable funding sources for the operation of the AKIS components (regional hubs, the platform, and coordination mechanisms), hinder the full-scale launch of the system. There is a need to mobilise international technical assistance and integrate into European support instruments (EIP-AGRI, Horizon Europe, etc.), including securing international funding to ensure the effective launch of the system and its integration into the European knowledge and innovation ecosystem. |
|  | 2) Establishment of a farm data collection system based on the Farm Sustainability Data Network (FSDN) principles | 2027 | Farm data system established | Ongoing | Ministry of Economy of Ukraine In 2025, the second phase of the pilot project on the implementation of the Farm Accountancy Data Network/Farm Sustainability Data Network (FADN/FSDN) was carried out in Poltava and Zhytomyr oblasts, involving 29 agricultural producers. A draft Resolution of the Cabinet of Ministers of Ukraine "On Approval of the Procedure for the Establishment and Operation of the Farm Sustainability Data Network (FSDN), and the Methodology for Data Collection, Processing and Analysis" has been prepared and is currently under review by the structural units of the Ministry of Economy of Ukraine. |  |  |  |  |
| 4. Ensuring Access for Rural Residents to Social and Administrative Services, Including in the Administrative Centres of Territorial Communities and Districts | 1) Establishment and modernisation of Administrative Service Centres (ASCs), their territorial subdivisions and remote administrator workstations, taking into account barrier-free service provision, and ensuring the delivery of administrative services to applicants through the "Mobile Administrator" and "Mobile Centre" services for outreach and inclusive service delivery to rural residents | 2025—2027 | Provision of the administrative services specified in the Order of the Cabinet of Ministers of Ukraine No. 523 of 16 May 2014 has been ensured in 100% of Administrative Service Centres established by rural and settlement councils. | ongoing | Vinnytsia Oblast Administrative services are provided in all Administrative Service Centres in accordance with the Resolution of the Cabinet of Ministers of Ukraine No. 1226 of 1 October 2025 "Certain Issues of the Provision of Administrative Services through Administrative Service Centres." |  |  |  |  |
|  |  |  |  |  | Volyn Oblast Administrative services are provided in 53 territorial communities of the oblast. The oblast has 21 mobile administrator workstations ("mobile suitcases") and 1 Mobile Administrative Service Centre (Mobile ASC) in the city of Ustyluh. |  |  |  |  |
|  |  |  |  |  | Dnipropetrovsk Oblast 100% of ASCs in the region are equipped with a service for the provision of administrative services through a mobile automated administrator workstation ("mobile suitcase"). |  | Dnipropetrovsk Oblast 1,200.00 – oblast budget; 1,200.00 – local budgets. |  |  |
|  |  |  |  |  | Donetsk Oblast During 2025, the Mobile Employment Centre conducted 26 outreach visits. Nearly 1.2 thousand people participated in these activities and received consultations on employment, job placement, training opportunities, voucher programmes, micro-grant schemes, participation in public works, and other related issues. |  |  |  |  |
|  |  |  |  |  | Zhytomyr Oblast Administrative services specified in the Resolution of the Cabinet of Ministers of Ukraine No. 1226 of 1 October 2025 "Certain Issues of the Provision of Administrative Services through Administrative Service Centres" are provided in the ASCs across the oblast. |  |  |  |  |
|  |  |  |  |  | Zakarpattia Oblast The provision of administrative services in accordance with List No. 523 has reached 68% of the target indicator. 10 Mobile Administrator units are operational, providing outreach and inclusive services to the population. Administrative Service Centres are being modernised, and their service portfolios are being aligned with legislative requirements. |  | Zakarpattia Oblast 2,367.3 |  |  |
|  |  |  |  |  | Zaporizhzhia Oblast All operational Administrative Service Centres (ASCs), their remote administrator workstations, territorial subdivisions, and mobile offices established by rural and settlement councils provide administrative services in accordance with the Resolution of the Cabinet of Ministers of Ukraine No. 1226 of 1 October 2025 "Certain Issues of the Provision of Administrative Services through Administrative Service Centres", taking into account Note 5 on determining the list of ASCs considered operational (capable of providing services under the existing conditions) in the territories included in the list of territories where hostilities are (or have been) conducted or which are temporarily occupied by the Russian Federation, approved by the Order of the Ministry for Communities, Territories and Infrastructure Development. |  |  |  |  |
|  |  |  |  |  | Ivano-Frankivsk Oblast Provision of administrative services specified by Order of the Cabinet of Ministers of Ukraine No. 523 dated May 16, 2014, is ensured in 100 percent of Administrative Service Centers (ASCs) established by village and settlement councils. |  |  |  |  |
|  |  |  |  |  | Kyiv Oblast In Kyiv Oblast, there are 69 Administrative Service Centres (ASCs), 3 territorial subdivisions, 168 remote administrator workstations, and 1 village elder performing the functions of an administrator. In 2025, these service points delivered nearly 1.3 million administrative services, the list of which was provided for by the Order of the Cabinet of Ministers of Ukraine No. 523-r of 16 May 2014 and approved by the Resolution of the Cabinet of Ministers of Ukraine No. 1226 of 1 October 2025 "Certain Issues of the Provision of Administrative Services through Administrative Service Centres." These include services for war veterans, combatants, and their family members, which are provided in 100% of ASCs. ASCs in Kyiv Oblast are currently updating their service lists to comply with the new requirements. Within their available financial resources and with the support of international partners, territorial communities are improving the material and technical capacity of ASCs by carrying out major renovations, introducing measures to ensure accessibility for persons with disabilities and other persons with reduced mobility, equipping ASCs with modern computer hardware, and providing "mobile suitcase" equipment kits to enable outreach (mobile) service delivery to community residents. Overall, 7 territorial communities in Kyiv Oblast are equipped with 8 such mobile service kits. |  | Kyiv Oblast 8258,0 | Kyiv Oblast 2668,0 | Kyiv Oblast The absence of state budget subventions, as well as the limited financial capacity of local budgets, makes it impossible to equip most Administrative Service Centres (ASCs) with modern premises that meet security and accessibility requirements. At the same time, limited human resources and insufficient salary levels do not allow local self-government bodies to appoint a sufficient number of administrators to ensure the provision of the full range of services. Increasing the salaries of ASC administrators and resolving the issue of allocating state budget subventions to local budgets for the development of the network of Administrative Service Centres as a priority public investment project will improve the material and technical capacity of ASCs and enhance the quality of service delivery. |
|  |  |  |  |  | Kirovohrad Oblast The oblast has 49 Administrative Service Centres (ASCs) in operation. 114 remote ASC workstations have been established in the starosta offices of 19 territorial communities. The Diia Centre designation has been implemented in the ASCs of the Bobrynets and Oleksandriia City Councils, and has been partially implemented in the ASCs of the Kropyvnytskyi, Svitlovodsk, and Znamianka City Councils. Within the framework of cooperation with the Polaris Programme "Support to Multilevel Governance in Ukraine", the Oleksandriia Territorial Community successfully completed the competitive selection process and received a vehicle to ensure the provision of administrative services to community residents, including those requiring enhanced social attention and support. According to the monitoring conducted by the Ministry of Digital Transformation of Ukraine on ensuring conditions for the presence and service of persons with disabilities and other persons with reduced mobility in Administrative Service Centres: 86% of ASCs in the oblast provide free (unobstructed) access to their premises, including 84% equipped with ramps and 61% with stairways fitted with handrails; 49% have accessible sanitary facilities. |  | Kirovohrad Oblast 90,0 | Kirovohrad Oblast 877,4 |  |
|  |  |  |  |  | Luhansk Oblast Before 24 February 2022, 23 Administrative Service Centres (ASCs), 100 remote administrator workstations, 1 territorial subdivision, and 9 Mobile ASCs operated in Luhansk Oblast in accordance with the Law of Ukraine "On Administrative Services." As a result of the Russian Federation's full-scale invasion of Ukraine, 22 ASCs are currently operating in relocation outside their temporarily occupied territorial communities. These ASCs do not have dedicated premises for the provision of administrative services that comply with the location and facility requirements established by the current legislation. Their staff are working from 36 locations in 22 settlements in other oblasts, including the premises of military administrations of settlements, a healthcare institution, the NGO "IDPs of Ukraine", and 31 humanitarian hubs of Luhansk Oblast. At some locations, representatives of several ASCs work simultaneously, and appointment schedules for applicants have been organised based on the availability of workstations in the humanitarian hubs and on a rotational basis with representatives of other structural units of military administrations, district state administrations, the Luhansk Oblast Employment Centre, the Main Directorate of the Pension Fund of Ukraine in Luhansk Oblast, as well as lawyers, doctors, psychologists, and others. Older persons and persons with disabilities from the Lysychansk Territorial Community are able to receive services at their place of residence in Dnipro and Dnipropetrovsk Oblast through the portable "Mobile Office" complex provided under international technical assistance. Similar "Mobile Office" complexes have also been provided to the ASCs of the Sievierodonetsk, Hirske, Popasna, Svatove, and Bilolutsk territorial communities. No requests from citizens for this service were received. The ASCs of Luhansk Oblast fall under Note 5, according to which administrative services are introduced subject to the following conditions: the ASC has the necessary organisational, financial, and other support; and the administrator or official assigned all or part of the administrator's functions possesses a professional or partial professional qualification enabling them to provide the relevant service. As of 31 December 2025, between 11 administrative services (at the Chmyriv ASCs) and 142 administrative services (at the Kreminna ASC) had been introduced through the ASCs. |  |  |  |  |
|  |  |  |  |  | Lviv Oblast The provision of administrative services has been ensured in 100% of Administrative Service Centres (ASCs)established by city, rural, and settlement councils. Lviv Oblast ranks first in Ukraine in terms of the number of administrative service delivery points, with 593 service points, including 73 ASCs, 17 territorial subdivisions, 502 remote administrator workstations (RAWs), and 1 Mobile ASC. The "Mobile Administrator" service operates in 12 territorial communities. In 2025, funding was allocated from the oblast budget to complete the project "New construction of the Administrative Service Centre and Media Library building at 17V Ivan Franko Square, Sudova Vyshnia, Sudova Vyshnia Territorial Community, Yavoriv District, Lviv Oblast. Adjustment." |  | Lviv Oblast 10000,0 | Lviv Oblast 10000,0 | Lviv Oblast The Order of the Cabinet of Ministers of Ukraine No. 523 of 16 May 2014 was repealed in 2025. Instead, the provision of administrative services is governed by the Resolution of the Cabinet of Ministers of Ukraine No. 1226 of 1 October 2025 "Certain Issues of the Provision of Administrative Services through Administrative Service Centres." The Sudova Vyshnia Territorial Community was unable to complete all the required works in 2025; however, the facility will be completed and commissioned in 2026. |
|  |  |  |  |  | Mykolaiv Oblast As of 2025, 37 regular Administrative Service Centres (ASCs) are operating in Mykolaiv Oblast, including 15 settlement and 13 rural ASCs, as well as 6 Mobile ASCs, including 1 rural Mobile ASC. In addition, 59 remote administrator workstations (RAWs) are operational, including 30 in settlement and 15 in rural communities. A total of 359 ASC staff ensure the operation of the centres, which provided more than 375,000 administrative services during the year. The Prybuzhany, Chornomorska, Doroshivka, and Syniukhyne Brid rural territorial communities are cooperating with the Polaris Programme to establish and open new Administrative Service Centres. |  |  |  |  |
|  |  |  |  |  | Odesa Oblast Monitoring is being carried out to oversee the implementation and adoption of the updated list of administrative services in accordance with the Resolution of the Cabinet of Ministers of Ukraine No. 1226 of 1 October 2025. Monitoring is also being conducted to ensure that the lists of administrative services provided through ASCs are aligned with the requirements of the Resolution and the current legislation. |  |  |  |  |
|  |  |  |  |  | Poltava Oblast Administrative Service Centres (ASCs) operate in all 60 territorial communities. In addition, there are 3 territorial subdivisions and 152 remote (including mobile) administrator workstations (RAWs). In total, the oblast has 215 administrative service delivery points. Measures are being taken to ensure that ASC premises comply with accessibility requirements. In 2025, an accessible modular ASC was opened in the Velyka Sorochyntsi Territorial Community. Reconstruction (fit-out) of ASC premises is ongoing in the Pyriatyn and Khorol territorial communities. The "Mobile Administrator" service is available in 9 territorial communities, while 1 territorial community operates a Mobile ASC. |  | Poltava Oblast 1345,0 | Poltava Oblast 10056,4 | Poltava Oblast Staffing of ASCs in rural areas. Introduction of a targeted state programme; establishment of higher official salary rates for ASC administrators and registrars in rural areas; introduction of a state personnel procurement mechanism for ASCs. |
|  |  |  |  |  | Rivne Oblast The Resolution of the Cabinet of Ministers of Ukraine No. 1226 of 1 October 2025 "Certain Issues of the Provision of Administrative Services through Administrative Service Centres" approved the updated list of administrative services for Administrative Service Centres. Accordingly, the Resolution of the Cabinet of Ministers of Ukraine No. 523 of 16 May 2014 ceased to be effective. In 2025, Administrative Service Centres in Rivne Oblast provided 988 thousand administrative services. The most frequently requested services were residence registration, state registration, social services, and land-related services. |  |  |  | Rivne Oblast Regulation of the administrative service fee. Introduction of uniform principles for determining the amount of the administrative fee, the procedure for its payment, and its use. The fees should be reasonable, transparent, fair, and self-financing. |
|  |  |  |  |  | Sumy Oblast The provision of administrative services in accordance with the Resolution of the Cabinet of Ministers of Ukraine No. 1226 of 1 October 2025 has been ensured in all Administrative Service Centres (ASCs) of the oblast. |  |  |  |  |
|  |  |  |  |  | Ternopil Oblast The oblast has established and operates 55 Administrative Service Centres (ASCs) and 282 remote administrator workstations (RAWs), 140 of which were established during 2025. 30 territorial communities have been equipped with mobile kits for the provision of administrative services under the "Mobile Administrator" and "Mobile ASC" models, ensuring 100% coverage of these services for all residents of the territorial communities in the oblast. 17 ASCs in the oblast operate under the Diia Centre format. At the same time, work is ongoing to upgrade the ASCs in the Ozerna, Biletske, and Kopychyntsi territorial communities to the Diia Centre format. In accordance with the Resolution of the Cabinet of Ministers of Ukraine No. 1068 of 25 November 2015, and using state budget subventions allocated to local budgets for the implementation of projects under the Emergency Credit Programme for the Recovery of Ukraine, reconstruction of ASCs was carried out in the city of Kopychyntsi and the village of Trybukhivtsi, and construction of an ASC in the urban-type settlement of Velyka Berezovytsia was initiated. 65,309 families/persons raising 9,208 children were covered by the social services of the territorial communities. | Ternopil Oblast 16946,378 | Ternopil Oblast 3399,733 |  |  |
|  |  |  |  |  | Kharkiv Oblast As of 1 January 2026, administrative services were provided to residents of territorial communities in 229 service access points, including 51 Administrative Service Centres (ASCs), 14 territorial subdivisions (TSs) of ASCs, 160 remote administrator workstations (RAWs), and 4 Mobile ASCs. As of 24 February 2022, services were provided through 74 service access points, including 36 ASCs, 11 TSs, 26 RAWs, and 1 Mobile ASC. The number of administrative service access points has increased by 210%. In 2025, 1 ASC, 1 ASC territorial subdivision, and 67 ASC remote administrator workstations were established. 29 ASCs (57%) are equipped with 34 mobile administrator suitcases, enabling the provision of administrative services in an outreach format. In 2025, 1,107 administrative services were delivered through Mobile ASCs. The provision of administrative services specified by the Resolution of the Cabinet of Ministers of Ukraine No. 1226 of 1 October 2025 has been ensured at 60%. |  |  |  | The Resolution of the Cabinet of Ministers of Ukraine No. 1226 of 1 October 2025 entered into force at the end of 2025, leaving local self-government bodies and administrative service providers with a limited period to bring their activities into compliance with its requirements. The process of adaptation and alignment of administrative services with the Resolution is ongoing, including: - review and updating of the lists of administrative services; - approval of new (updated) service lists by local council sessions; - alignment of information and technological service cards with the regulatory requirements; - staff training. |
|  |  |  |  |  | Kherson Oblast In 2025, a set of measures was implemented in Kherson Oblast to ensure access to social and administrative services for rural residents. The operation of 17 ASCs in de-occupied communities was restored, and 32 departments from occupied territories were relocated, enabling the operation of 49 centres. Mobile service formats were established, including 11 Mobile ASCs, 15 electric tricycles, and 39 mobile administrator suitcases, through which 119 settlements were covered, 454 outreach visits were conducted, and 7,426 administrative services were provided. All measures were implemented in accordance with the principles of accessibility and inclusiveness, ensuring equal access to public services for persons with reduced mobility, persons with disabilities, and residents of remote communities. As a result, a modern system of stationary and Mobile ASCs has been established, ensuring the accessibility and quality of administrative services even under the challenging conditions of the region. |  |  |  |  |
|  |  |  |  |  | Khmelnytskyi Oblast Administrative Service Centres (ASCs) operate in 52 territorial communities of the oblast, ensuring 100% provision of both their own administrative services and the services specified by the Resolution of the Cabinet of Ministers of Ukraine No. 1226 of 1 October 2025, including with due regard to accessibility requirements. 8 territorial communities are taking measures to open ASCs in 2026. Cherkasy Oblast To improve accessibility and ensure equitable service provision for all population groups, including persons with disabilities, the Cherkasy Regional Military Administration initiated an assessment of the accessibility of 66 Administrative Service Centres (ASCs) in 2024 and developed an "ASC Accessibility Map." As of 31 December 2025, 23 territorial communities (Bobrytska, Stepanetska, Leskivska, Rotmistrivska, Ruskopolianska, Cherkaska, Horodyshchenska, Smilianska, Chyhyrynska, Balakliivska (Cherkasy District), Lypianska, Zvenyhorodska, Kalynopilska, Talnivska, Matusivska, Shpolianska, Yerkivska, Vodianytska (Zvenyhorodka District), Chornobaivska (Zolotonosha District), Ladyzhynska, Ivankivska, Umanska, and Khrystynivska (Uman District)) implemented measures to bring their ASCs into compliance with accessibility standards, making ASC premises more accessible and user-friendly for persons with disabilities and veterans. The Stepanetska, Korsun-Shevchenkivska (Cherkasy District), and Drabivska (Zolotonosha District) territorial communities purchased mobile service kits using local budget funds, enabling administrative services to be delivered to eligible residents at their place of residence. The Cherkasy City Council ASC operates a "Mobile Administrator" service, through which staff provide administrative services to residents of Cherkasy who are unable to visit the ASC due to age or health conditions. The ASCs provide both local government administrative services and services in accordance with Cabinet of Ministers of Ukraine Resolution No. 1226 of 1 October 2025. Chernivtsi Oblast To improve access to public services for residents of territorial communities, Administrative Service Centres (ASCs) operate in every community across Chernivtsi Oblast. Of the region's 52 ASCs, 41 have been established by rural and settlement councils, ensuring 100% coverage of rural and settlement localities across the oblast. In addition, ongoing efforts are being undertaken to renovate existing ASC premises. With financing provided under the Emergency Credit Programme for Ukraine Recovery, ASC reconstruction projects are being implemented in two territorial communities: - Since 2024, the Kelmentsi Territorial Community has been implementing the project "Capital Repair of the Administrative Building (Establishment of ASC Premises) in the Settlement of Kelmentsi." Completion is scheduled for 2026. The total project cost amounts to UAH 19.64 million, with 80% of works completed. - The Berehomet Territorial Community is implementing the project "Reconstruction of Non-Residential Premises into an Administrative Service Centre at 30 Tsentralna Street, Berehomet, Vyzhnytsia District, Chernivtsi Oblast." The total project value is UAH 20.15 million, with 85% completion. With funding from the state budget subvention allocated under Cabinet of Ministers of Ukraine Resolution No. 608 of 16 June 2023, the Mamalyha Territorial Community has been implementing, since 2023, a project to reconstruct the local House of Culture with an extension accommodating an ASC in the village of Mamalyha. The project is scheduled for completion in 2026 using local budget resources. As of 1 January 2026, the remaining project value amounted to UAH 703 thousand, while project implementation had reached 97% completion. To improve access to administrative services in remote mountainous areas, four mountain territorial communities—Koniatynska, Seliatynska, Putylska, and Ust-Putylska—received funding from the regional budget to procure mobile service kits for providing on-site administrative services to residents of remote mountain settlements. Chernihiv Oblast The network of Administrative Service Centres (ASCs) in Chernihiv Oblast comprises 197 service access points, including 57 ASCs, 122 remote workplaces, 16 starosta offices, one mobile ASC, and one territorial subdivision. The ASC infrastructure continues to be systematically modernised, with ongoing improvements to customer service conditions and the progressive introduction of inclusive service delivery approaches. A total of 14 ASCs and 2 remote workplaces have been equipped with mobile service kits. Two territorial communities provide outreach administrative services using passenger vehicles supplied by international partners, while another community delivers services through a Mobile Centre provided by international partners. In all 57 territorial communities of Chernihiv Oblast, the lists of administrative services delivered through ASCs have been approved in accordance with the applicable legislation. | Chernivtsi Oblast 11125,5 | Chernivtsi Oblast 2332,3 |  |  |
|  | 2) Provision of social services to individuals/families in accordance with their identified needs, including through the engagement of non-state social service providers | 2025-2027 | Social services provided to 80% of individuals/families identified as requiring them. |  | Vinnytsia Oblast A total of 144 social service providers of different ownership types are registered in the Unified Information System "Register of Social Service Providers and Recipients." These include 96 public (municipal) providers, 46 private providers, and 2 state providers. All of the above-mentioned providers deliver social services to residents of Vinnytsia Oblast in accordance with their identified needs. |  |  |  |  |
|  |  |  |  |  | Dnipropetrovsk Oblast During 2025, 53.3 thousand older persons and persons with disabilities received social services. |  | Dnipropetrovsk Oblast 963772,92 |  |  |
|  |  |  |  |  | Donetsk Oblast 1) During 2025, nearly 14,800 IDPs who approached hubs received information and advisory services from specialists of the Donetsk Oblast Employment Service. 2) During 2025, in rural areas, territorial social-service centres and social-service provision centres provided social services to more than 1,800 elderly citizens and persons with disabilities. As of 01.01.2026, 14 non-state-sector social-service providers are registered in communities of the government-controlled territory of Donetsk Oblast. Zhytomyr Oblast In the oblast, social services are provided at: 8 territorial social-service centres; 43 social-service provision centres; 15 structural units in the oblast's communities that provide residents with social services according to their needs; 14 residential-care institutions; and 7 rehabilitation centres. There are also residential departments for the permanent accommodation of elderly citizens and persons with disabilities, with capacity for 145 bed spaces, currently housing 136 people. In addition, the Zhytomyr city territorial community provides social services through social contracting with 2 organizations: the charitable organization "Caritas-Zhytomyr Charitable Foundation" and the civil society organization "Facets of the Possible." Zakarpattia Oblast Social services have been provided to 100 percent of persons/families who requested them and were found to need them. Zaporizhzhia Oblast The main providers of social services to residents of rural areas in the government-controlled territory of the oblast are 15 social-service provision centres of village and settlement councils (hereinafter — social-service providers). In 2025, these providers served more than 7,000 families in difficult life circumstances (of which nearly 10,000 were adults over 18 and 4,480 were children). During the reporting period, all families/individuals in need of social services were covered. Local-budget expenditures of village and settlement councils to support the operation of social-service providers amounted to UAH 36,586.33 thousand. In addition, social-service providers of the Novomykolaivka and Ternuvate settlement communities and the Bilenke and Pavlivka rural territorial communities engaged civil society organizations and charitable foundations; the total amount of charitable contributions received was UAH 1,428.42 thousand. Ivano-Frankivsk Oblast The oblast has addressed the problem of providing services in communities without their own social-service institutions through a mechanism of purchasing assistance from the non-state sector. Through implementation of the pilot "money follows the person" model, targeted payment for care has been arranged for IDPs and persons with disabilities. In partnership with Caritas, the network has been expanded by 8 new specialized departments, providing the oblast with an additional 74 bed spaces for institutional care and supported living. |  |  |  |  |
|  |  |  |  |  | Kyiv Oblast 230 entities are registered in the Register of Social-Service Providers in Kyiv Oblast, of which up to 40% belong to the non-state sector. Non-state social-service providers (civil society and charitable organizations, religious institutions, private establishments, and individual entrepreneurs) play an important role in ensuring the accessibility and diversity of social support, responding promptly to the needs of various population categories. Such entities provide social services to individuals and families in difficult life circumstances, according to identified individual needs, including through social contracting, public-private partnerships, and joint projects with state and local self-government authorities. Work on developing the social-services market, including engaging non-state providers, continues systematically in Kyiv Oblast. Kirovohrad Oblas The oblast's social-protection system ensures the operation of 15 territorial social-service centres, 31 social-service provision centres, 2 social-service provision departments under the executive committees of city, settlement and village councils, and 12 oblast-subordinated residential-care institutions, of which: 3 are general-profile, 8 are psychoneurological, and 1 is for children, with a total capacity of 1,900 bed spaces. Social-service institutions provide a wide range of services: home care, institutional care, social adaptation, counselling, sign-language interpretation, physical escort for visually impaired persons, work with families/children/youth, targeted in-kind and cash assistance, representation of interests, information provision, mediation, social prevention, and others. Services are provided in accordance with the state standards for social-service provision approved by the Ministry of Social Policy of Ukraine. During 2025, the above-mentioned institutions provided various social services to approximately 35,000 citizens. Social services are delivered promptly and accessibly to everyone who needs them, regardless of place of residence, social status or other factors, and are tailored to the specific needs of each person or family requiring them. The population is informed about the list of social services, their content and the procedure for obtaining them, as well as about the social-service providers operating in the oblast/community, through informational websites and print media, in a format accessible to persons with any health impairments. Luhansk Oblast Territorial communities of Luhansk Oblast have restored the operation of 14 social-service providers under relocation conditions. The level of social-service coverage exceeds 90% of persons/families who need such services. Lviv Oblast Pursuant to an instruction of the Secretariat of the Cabinet of Ministers of Ukraine dated 21.05.2021 No. 16454/0/2-21 and a letter of the Office of the President of Ukraine dated 20.05.2021 No. 02-01/1194 on continuing implementation of Presidential Decree No. 30 of 29.01.2021, "On Certain Measures to Ensure a Social Service" (hereinafter — the Decree), including the tasks set out in the second and third paragraphs of Article 1(1) of the Decree, the Oblast State Administration's Department of Social Protection is organizing and carrying out work to identify and inspect non-state-sector social-service providers (hereinafter — Providers) offering temporary or permanent residence to elderly citizens, persons with disabilities, homeless persons, persons released from places of deprivation of liberty, and persons dependent on narcotic drugs or psychotropic substances, in territorial communities of the oblast. During inspections conducted over the 12 months of 2025, 8 non-state-sector facilities offering temporary or permanent residence to such categories of persons were identified in Lviv Oblast. As of 01.01.2026, work continued with non-state social-service providers on processing documents for inclusion in the Register of Non-State-Sector Social-Service Providers. |  | Kyiv Oblast 541740,0 |  |  |
|  |  |  |  |  | Mykolaiv Oblast In accordance with the Law of Ukraine "On Social Services," work is under way in Mykolaiv Oblast to preserve and develop the network of units providing assistance and services in line with population needs. Mykolaiv Oblast ensures the operation of 52 social-service providers, comprising: 7 territorial social-service centres, 8 social-service centres, and 37 social-service provision centres, which resolve, at the local level, issues related to organizing and providing various types of social services to those in need. To plan the organization and provision of social services, local self-government bodies identify the social-service needs of the territorial community's population. As of 01.01.2026, the number of identified persons requiring social services was 105,711. Of these, 105,711 actually received services, representing 100% of those in need. The structure of territorial centres and social-service provision centres comprises 150 departments, namely: 47 home social-assistance departments, serving 10,688 people; 18 day-care departments, serving 12,723 people; 22 institutional-care departments for permanent or temporary residence of elderly persons and persons with disabilities, currently housing 458 residents (496 people received services during 2025); 1 institutional palliative-care department with capacity for 15 bed spaces, serving 27 people; and 29 departments organizing targeted cash and in-kind assistance, which provided various social services to 64,439 people. An additional 33 departments operated among the social-service providers, serving 17,338 people. Odesa Oblast During 2025, 36,300 families/individuals recognized as being in difficult life circumstances needed social services, of which 35,000 families/individuals, or 96.4%, received them. In total, in 2025, 67,000 families/individuals in difficult life circumstances received social services (including families/individuals whose service coverage continued from the previous year). Poltava Oblast Social-service provision is ensured by 119 social-service providers, including 36 from the non-state sector. Social services covered 110,000 families/individuals in difficult life circumstances, in line with identified needs. Rivne Oblast The oblast has 9 territorial social-service centres, 26 social-service provision centres, 1 centre for social services, and also 3 social-protection departments (hereinafter — institutions), which include social workers, social-service specialists and social inspectors, plus 2 home social-assistance departments, all of which provided social services. In 2025, the oblast's institutions ensured provision of social services to nearly 100 percent of persons/families requiring them (25,900 people). Sumy Oblast. According to the Unified Information System of the Social Sphere, 93 social-service providers are registered in Sumy Oblast: 76 municipally owned (33 centres, 10 territorial centres, 2 home social-assistance departments, 7 social-service centres, 3 socio-psychological rehabilitation centres, 1 mother-and-child centre, 1 social hostel, 7 rehabilitation centres, 12 residential-care institutions), and 17 non-state-owned. Social services are provided in 45 provider institutions in territorial communities (10 territorial social-service centres, 33 social-service provision centres, and 2 home-care service departments). In 2025, 41,600 people were served, or 100% of those in need. Ternopil Oblast To ensure social-service provision to individuals/families according to identified needs, 12 non-state-sector social-service providers operate in the oblast. During 2025, social services from territorial-community providers covered 65,309 families/individuals, raising 9,208 children. Kharkiv Oblast To ensure social-service provision to individuals/families according to identified needs, privately owned social-service providers are engaged. During 2025, private social-service providers served more than 18,900 people. To improve accessibility of social services for residents of territorial communities, an interactive map and a mobile application, "Social Services of Kharkiv Region," have been created. The map displays information on social-service providers, their geographic location, contact details, working hours, and the names of the social services offered. For convenience, an online-appointment service with social-service providers has been introduced, used by more than 13,400 people. Use of the online service allows residents of territorial communities close to areas of active hostilities to receive information and counselling services remotely. Khmelnytskyi Oblast. The network of centres, institutions and units providing social services in Khmelnytskyi Oblast comprises 63 institutions, which provided social services to 108,000 people during 2025. The oblast has 13 privately owned boarding houses for the elderly and 8 non-state-owned organizations, which provided institutional-care/residential services to 1,032 people. A grant project for providing social services to children and families with children was also implemented in the oblast, involving 7 non-state-sector social-service providers. Cherkasy Oblast. The oblast has established an extensive network of social institutions and facilities providing social services. In 2025, 66 institutions/facilities operated, of which 7 are territorial social-service centres and 59 are social-service provision centres. During the reporting period: 49,362 people requiring social services were identified; services were provided to 47,161 people, representing 95.5% of the need. |  | Mykolaiv Oblast 94928,26 Odesa Oblast 502588,6 Poltava Oblast 22652,7 Rivne Oblast 217559,1 |  |  |
|  |  |  |  |  | Chernivtsi Oblast Social services were provided to 83% of persons/families requiring them. Chernihiv Oblast Chernihiv Oblast is implementing the Programme for the Development of Social-Service Provision in Chernihiv Oblast for 2024–2026, aimed at developing social-service provision for vulnerable population groups according to their needs. In territorial communities of the oblast, social-service provision is ensured by 8 territorial social-service centres, 44 social-service provision centres, and 11 non-state-sector providers. During 2025, 48,733 people received social services. Resilience centres operate in 11 territorial communities. The "Day Care for Children with Disabilities" social service is provided in 6 communities; "Support during Inclusive Education" in 3; and "Transportation Services" (for persons with limited mobility, wheelchair users, elderly people, and residents who cannot use public transport for health reasons) in 15. "Social Adaptation Spaces," offering the "University of the Third Age" service, operate in 8 communities; "Mobile Social Services" in 15; "Social Laundry" in 4; and "Social Barbershop/Salon" in 11. 18 institutional-care departments operate for permanent or temporary residence. |  | Chernivtsi Oblast 144608,7 | Chernihiv Oblast 330,0 | Chernihiv Oblast Shortage of qualified staff: communities lack sufficient specialists, resulting in high workload and reduced quality of personal-care assistance. |
|  | 3) Assessing the individual needs of internally displaced persons and ensuring that social services are provided to them according to identified needs | 2027 | internally displaced persons receive at least 80 percent of the social services they need. |  | Vinnytsia Oblast From the first days of the full-scale invasion, Vinnytsia Oblast became a transit hub and began accommodating internally displaced persons in the oblast's social-protection institutions. In total, 1,454 people were admitted to the oblast's social-protection institutions, of whom 421 were in transit. 684 low-mobility internally displaced persons were admitted to the oblast's residential-care institutions. Donetsk Oblast During 2025, 5,986 internally displaced persons (including those outside the oblast) received social services, of whom 301 IDPs residing in the government-controlled territory of the oblast, and 489 who relocated to safer oblasts of Ukraine, received the "home care" service. Ivano-Frankivsk Oblast Assessment of IDP needs is carried out by the community's social manager through completion of a Needs Assessment Report, signed by both parties using digital case-management tools. To resolve complex cases, the social manager coordinates inter-agency interaction, engaging specialists from the medical, educational, rehabilitation and employment sectors. Kirovohrad Oblast In 2025, 4,300 citizens from among internally displaced persons received social services. Poltava Oblast Social-service provision to internally displaced persons in difficult life circumstances is ensured by: 14 residential-care institutions, 8 territorial social-service centres, 47 social-service provision centres, 8 social-service centres, and the State Non-Commercial Enterprise "Myrhorod Sanatorium 'Slava.'" Services covered 5,800 IDPs. Rivne Oblast In 2025, 578 internally displaced persons in the oblast received 99 percent of the social services they needed. Kharkiv Oblast Territorial communities have ensured assessment of the needs of internally displaced persons, based on which social services are provided by social-service provision centres, social-service centres, and territorial social-service centres. Since the start of 2025, more than 25,000 IDPs have received social services. Khmelnytskyi Oblast In 2025, the oblast's social-service providers assessed the needs of 2,344 internally displaced families/individuals; various types of social services covered 3,302 displaced families/individuals. Chernivtsi Oblast Individual needs assessments were conducted for 688 IDPs. Social services provided: information — 1,320; counselling — 955; mediation — 49; representation of interests — 88; social prevention — 246; social support/case management — 90; social adaptation — 170; social integration and reintegration — 48; day care — 39; institutional care — 5; in-kind assistance — 150. As a result of the services provided, recipients obtained: psychological assistance — 328 people; legal assistance — 147 people; employment assistance — 13 people; placement in educational institutions — 31 people; organization of treatment/recuperation — 103 people; resolution of housing and everyday-life problems — 75 people; re-establishing family/community connections — 89 people; and processing/restoring documents for social payments — 314 people. |  |  |  |  |
| 5.Identifying priorities and mechanisms for utilizing the potential of regional growth poles, including stimulating the renovation and effective use of abandoned territories and production facilities in regional growth poles | Conducting an inventory of unused industrial facilities and land for the purpose of renovation or repurposing | 2025—2027 | an inventory conducted of at least 30 industrial facilities and 80 land plots | Ongoing | Vinnytsia Oblast The oblast has compiled a list of 60 premises suitable for renovation or repurposing. 18 industrial-purpose land plots are available. Donetsk Oblast Owing to hostilities in the oblast, destruction of industrial infrastructure from enemy shelling, the unsatisfactory security situation, and the temporary occupation of part of the oblast's territory, an inventory of industrial facilities and land for renovation or repurposing will become possible once the security situation improves, the oblast's territory is de-occupied, and specialists can safely access enterprises. Zhytomyr Oblast To attract potential investors and create a favourable investment climate, work was carried out quarterly to update the database of investment proposals. The oblast currently has 126 vacant land plots and 54 unused production premises. Zakarpattia Oblast The oblast has compiled information on more than 120 investment proposals, land plots, and vacant production areas in Zakarpattia Oblast, publicly available on the official reference portal "Zakarpattia Assistance," under the section "Business – Investment Proposals. Land Plots. Production Areas," or accessible via the link: https://drive.google.com/drive/folders/1fVOWRvnMBScVIVUfa71FfRE73mVXV391 Zaporizhzhia Oblast The Oblast State Administration continuously monitors the activities of enterprises in the region. Industrial enterprises of the state sector of the economy located in the government-controlled territory of the oblast are currently not conducting production activities, including JSC "Zaporizhzhia Production Aluminium Combine," the State Enterprise "Kremniipolimer," and LLC "Zaporizhzhia Titanium-Magnesium Combine." The Oblast State Administration has no levers of influence over the economic activities of these enterprises, including their renovation or repurposing, since the governing body is the State Property Fund of Ukraine. The enterprises are currently undergoing privatization. In addition, the Oblast State Administration has not received any proposals from governing bodies, property owners, or potential investors regarding the repurposing or renovation of these facilities. Ivano-Frankivsk Oblast An inventory has been conducted of 59 unused industrial facilities/premises and 24 unused land plots. Kyiv Oblast Local self-government bodies of Kyiv Oblast's territorial communities are conducting an inventory of unused industrial facilities and land plots. Kirovohrad Oblast Jointly with the oblast's territorial communities, an audit was conducted of more than 50 investment sites. The list of potential facilities includes property complexes of enterprises undergoing liquidation or reorganization, with a view to their subsequent revitalization and/or renovation. To make effective use of vacant greenfield land plots and brownfield facilities, and to attract investment into the economies of territorial communities, including with the support of international partners, information on existing industrial facilities and land plots suitable for investment projects has been updated (63 greenfield sites and 33 brownfield sites). Luhansk Oblast Implementation has not begun. Lviv Oblast Information on land plots and industrial facilities is consolidated on the Investment Attractiveness Dashboard of the Lviv Region Analytical Portal. During 2025, 118 land-plot entries and 19 industrial-facility entries were added. Mykolaiv Oblast On the website "Investment Opportunities of Mykolaiv Region" (https://invest.mk.gov.ua/uk/investytsiini-proekty-ta-propozytsii), the page "Investment Projects, Proposals and Vacant Land Plots" is regularly updated with information on vacant land plots suitable for investment projects, production facilities, logistics centres, commercial real estate, and other business activities. Poltava Oblast Within the "Programme for the Efficient Use of Land Resources of Poltava Region for 2022–2027," an inventory was conducted of municipally owned agricultural land covering 1,102 hectares (223 land plots) and of the land water fund (ponds) covering 143 hectares (23 land plots). Ternopil Oblast The oblast has compiled and continuously updates a catalogue of land plots and vacant production premises, comprising 299 investment sites: 198 greenfield land plots and 101 brownfield plots offered to potential investors. Kherson Oblast Implementation has not begun. Khmelnytskyi Oblast As part of implementing the government's relocation programme, and to promote investment activity in the oblast, a database has been compiled of vacant areas, premises, and mothballed state-, municipal- and privately-owned enterprises. The Oblast Military Administration, together with the oblast's local self-government bodies, has also compiled a database of vacant land plots that can be used to relocate enterprises, offered to potential investors. Cherkasy Oblast The Cherkasy Oblast Military Administration conducts quarterly monitoring of vacant land plots and production premises. This information is published on the "Map of Investment Opportunities of Cherkasy Region" on the oblast's investment portal. As of 01.01.2026, the Map contained information on 86 greenfield sites and 80 brownfield sites. Kharkiv Oblast An inventory of unused industrial facilities and land will be conducted once hostilities in Kharkiv Oblast have ended. Chernivtsi Oblast Should applications be received from business entities regarding a change in the designated use of land, they will be considered at sessions of the oblast commission on the exercise, by the Oblast State Administration (Oblast Military Administration), of powers in the field of land relations. Chernihiv Oblast 5 industrial-purpose land plots have been identified for this purpose. |  |  |  |  |
| 6.Creating conditions for the socio-economic, infrastructural and environmental development of the territories of the Ukrainian part of the Danube region, by taking into account, in sectoral strategies and state and regional development programmes, the priorities and objectives of the EU Strategy for the Danube Region | 1) Developing and approving a Strategy for the Development of Inland Water Transport of Ukraine | 2026 | an act of the Cabinet of Ministers of Ukraine adopted | Not started | Ministry for Communities, Territories and Infrastructure Development The implementation deadline has not yet arrived. |  |  |  |  |
|  | 2) Ensuring that the Danube River Basin Management Plan for 2025–2030 and the priorities and objectives of the EU Strategy for the Danube Region are taken into account when developing regional development programmes | 2025—2027 | regional development programmes approved | Ongoing | Ministry of Economy The Danube River Basin Management Plan for 2025–2030 (RBMP) was approved by Order of the Cabinet of Ministers of Ukraine of 31.12.2024. According to information from oblast state/military administrations on RBMP implementation, 55 measures were incorporated into programme documents in 2025. Zakarpattia Oblast. The share of measures from the Danube River Basin Management Plan for 2025–2030 (Tysa sub-basin) incorporated into regional programmes during the reporting year is 46%. Ivano-Frankivsk Oblast By Decision No. 1361-45/2025 of Ivano-Frankivsk Oblast Council of 19.12.2025, the Environmental Protection Programme of Ivano-Frankivsk Oblast for 2026–2030 was approved, providing for environmental protection measures in areas including: protection and rational use of water resources; waste management; protection and rational use of land; conservation of the nature reserve fund; and others, the implementation of which will help achieve environmental objectives in the Danube river basin (Prut sub-basin). In addition, according to information from local self-government bodies, 6 measures from the Danube River Basin Management Plan have been incorporated into local short- and medium-term planning documents, targeted programmes, and other documents. Odesa Oblast By Order of the Cabinet of Ministers of Ukraine No. 1347-r of 31.12.2024, the Danube River Basin Management Plan for 2025–2030 was approved, under which the priorities and objectives of the EU Strategy for the Danube Region are partially taken into account with regard to improving the state of water resources. For the measure "Clearing of the Kyslytskyi Arm of the Danube River," the Odesa Oblast State Administration (subject to agreement) is a co-implementer together with the Ministry of Agrarian Policy and the State Fisheries Agency, in accordance with the Action Plan for implementing the long-term development plan for Ukraine's irrigation complex until 2030, approved by Order of the Cabinet of Ministers of Ukraine No. 280-r of 25.03.2025, with an implementation period of Q1 2026 – Q4 2030. In addition, implementation of Danube River Basin Management Plan measures is envisaged in local development programmes: 1. The Programme for the Improvement of the Villages of Krynychne, Kosa and Novoozerne for 2025–2027, approved by Decision No. 931-VIII of Krynychne Village Council of 24.12.2024, provides for the revitalization of the Karasulak River (Krynychne territorial community, Bolhrad District, Odesa Oblast). 2. The Programme for the Rational Use of Natural Resources and Improvement of the Environmental Situation in the Territory of Kiliia City Territorial Community, Izmail District, Odesa Oblast, for 2023–2027, approved by Decision No. 1469/VIII/27 of Kiliia City Council of 25.11.2022, provides for the construction of sewage treatment facilities and sewerage networks in the city of Kiliia (Kiliia territorial community, Izmail District, Odesa Oblast). Chernivtsi Oblast During the reporting year, coordination and monitoring were carried out of the implementation of the Danube River Basin Management Plan (Prut and Siret sub-basins) (hereinafter — RBMP). In Chernivtsi Oblast, 20 RBMP measures have been incorporated into programme documents at various levels, namely: 3 measures into the Medium-Term Plan of Priority Public Investments of Vanchykivtsi territorial community for 2026–2028; 11 measures into the Sustainable Development Strategy of Novoselytsia city territorial community for 2021–2029; 4 measures into the Comprehensive Programme "Drinking Water of Chernivtsi Oblast for 2023–2026"; 1 measure into the Comprehensive Fisheries Development Programme of Chernivtsi Oblast for 2025–2030; and 1 measure into the Programme for Financial Support of Municipal Enterprises of the City of Chernivtsi and Contributions to Their Statutory Capital for 2017–2026. |  |  |  | Odesa Oblast Lack of funding for implementing the measures. Proposed solution: attracting funds from the state budget and other sources in 2026. |
| Напрям «Реінтеграція деокупованих територій» |  |  |  |  |  |  |  |  |  |
| 7. Building a personnel reserve of staff to organize governance and provide basic services in de-occupied territories | Strengthening the capacity of local self-government bodies to create conditions for attracting and developing specialists for local self-government bodies, including in the fields of strategic planning, public investment project management, spatial planning, and financial managemenпланування та управління фінансами | 2025- 2027 | a development and experience-exchange programme introduced for attracting and retaining specialists (a personnel reserve) for local self-government bodies, including those capable of ensuring quality management of territorial development and recovery. | Ongoing | National Agency of Ukraine for Civil Service Pursuant to paragraph 1 of part two of Article 14 and part five of Article 35 of the Law of Ukraine No. 3077-IX of 2 May 2023, "On Service in Local Self-Government Bodies" (which enters into force no earlier than 6 months after the end of martial law), NADS Order No. 155-24 of 11 December 2024, registered with the Ministry of Justice of Ukraine on 26 November 2024 under No. 1787/43132, approved the Standard Procedure for Forming and Organizing Work with a Personnel Reserve. The purpose of building this personnel reserve is to ensure prompt filling of vacancies in local self-government bodies through the transparent exercise of the right to serve in such bodies by candidates for local self-government service positions who have a deferred right to occupy such a position. In addition, in 2025, National Agency of Ukraine for Civil Service, together with the Ministry of Youth and Sports of Ukraine and the Higher School of Public Administration, in cooperation with the NGO "Association of Public Advisors of Ukraine," with the support of the UNDP Ukraine project "Civil Society and Youth Support" and funding from the Ministry of Foreign Affairs of Denmark, held the second wave of a youth internship programme in local self-government bodies. The programme's aim is to strengthen the human-resource capacity and institutional capability of local self-government representatives, and to build knowledge and skills for engaging youth in public service, including through developing and supporting the internship programme and introducing onboarding and mentoring tools. As part of this programme, a three-day training was held in August 2025 within the general short-term professional-development programme, "Organizing and Supporting a Youth Internship Programme in Public Authorities." NADS ensured support for the project's implementation and communication with local self-government bodies, UNDP, and the civil society organization. To sum up the results of the internship programme, National Agency of Ukraine for Civil Service took part in organizing a closing event, jointly with UNDP, the Ministry of Youth and Sports, and the NGO "Association of Public Advisors," as part of the project "Synergy: Building the Human-Resource Capacity of Local Self-Government through Youth Engagement," which took place on 9–11 December 2025 in Kyiv. |  |  |  |  |
| 8. Restoring the system of public authority in de-occupied territories and ensuring its resilience | Restoring the operation of territorial bodies of central executive authorities, local executive authorities, and local self-government bodies | 2025—2027 | operations of executive authorities and local self-government bodies in de-occupied territories restored 100 percent | Ongoing | Ministry for Communities, Territories and Infrastructure Development The Government adopted Resolution of the Cabinet of Ministers of Ukraine No. 1748 of 12 December 2025, "Certain Issues Concerning the Reform of Local Self-Government and the Territorial Organization of Power under Martial Law and in Preparation for Ukraine's Accession to the European Union" (drafted by the Ministry for Communities, Territories and Infrastructure Development), which approved the "Specifics of Reforming Local Self-Government and the Territorial Organization of Power under Martial Law and in Preparation for Ukraine's Accession to the European Union" (hereinafter — the Specifics), providing for the development and implementation of a comprehensive state policy on reintegrating temporarily occupied territories into the Ukrainian space and restoring local self-government there following their de-occupation. Among the tasks for reforming local self-government and the territorial organization of power in Ukraine, as set out in the Specifics, is forming an updated territorial basis for public governance, including strengthening the institutional capacity and proper coordination of local self-government bodies and executive authorities. In this area, the following is to be ensured: developing a mechanism for forming a personnel reserve, including for managing territorial communities and regions under critical conditions, drawing on trained specialists ready to work in difficult circumstances; the establishment of military administrations of settlements, as a forced measure, is permitted only on grounds of national security and defence, and their operation must be time-limited, lasting only until the relevant threats are eliminated. Once the situation stabilizes and state-authority institutions resume normal operation, a smooth transition from military to civilian administration must be ensured, along with the restoration of local self-government powers; holding consultations with local self-government bodies and their associations; developing and approving a programme for restoring the system of local self-government bodies and functions after the termination or lifting of the legal regime of martial law or a state of emergency; clearly defining in legislation the criteria for restoring the normal multi-level governance regime, the process and stages of transferring powers, and ensuring the stability and continuity of public authority to restore effective local governance. To date, pursuant to paragraph 3 of the aforementioned resolution, the Ministry for Communities, Territories and Infrastructure Development has drafted proposals for an action plan to implement the Specifics of reforming local self-government and the territorial organization of power under martial law and in preparation for Ukraine's EU accession; public consultations on this draft will be held in the near future to engage a broad range of stakeholders, civil society representatives, experts and academics in its discussion. |  |  |  |  |
| 9. Restoring basic municipal and administrative services in de-occupied territories | Restoring the operation of Administrative Service Centres (ASCs) in de-occupied territories, including the administrative buildings housing them, and equipping them with the necessary equipment and access to information and communication systems, electronic communication systems, and public electronic registers | 2025—2027 | operation of ASCs in de-occupied territories restored 100 percent. |  | State Emergency Service of Ukraine State Emergency Service of Ukraine territorial units carry out relevant outreach work among business entities regarding the administrative service of registering declarations of conformity of a business entity's material and technical base with fire-safety legislation requirements, via ASCs, once their operation has been restored. Donetsk Oblast On 10.04.2023, the ASC of the Executive Committee of Lyman City Council resumed operation, providing 108 types of administrative services. During 2025, the ASC issued 2,370 administrative-service outcomes and conducted 3,450 consultations offline, by phone, and by email. On 08.09.2023, the ASC of Sviatohirsk City Council resumed operation. During 2025, ASC staff issued 358 administrative-service outcomes and conducted 1,476 consultations offline, by phone, and by email. Zhytomyr Oblast 100% operation of the network of ASCs in de-occupied territorial communities of the oblast has been ensured, along with uninterrupted provision of administrative services. Kyiv Oblast During 2023–2024, the operation of ASCs in de-occupied territories was restored 100 percent. Luhansk Oblast Implementation has not begun. Mykolaiv Oblast ASC operations have been restored in all de-occupied territories. Kharkiv Oblast As of 01.01.2026, administrative services were being provided in de-occupied territories at 75 access points (24 ASCs, 48 remote workstations, and 3 mobile ASCs). As of 24.02.2022, services were provided at 27 access points, of which 15 were ASCs and 12 were remote workstations. The number of administrative-service access points has grown by 178%. In 2025, 24 remote workstations were opened in de-occupied territories. ASC operations have not been restored in the Vovchansk city and Dvorichna settlement territorial communities (unable to resume operations, as these communities are located in an active-hostilities zone, in accordance with Order No. 309 of the Ministry for Reintegration of 22.12.2022). All ASCs operating in de-occupied territories have access to information and communication systems, electronic communication systems, and public electronic registers. Kherson Oblast In 2025, basic municipal and administrative services were restored in the de-occupied territories of Kherson Oblast through the resumption of ASC operations in accordance with current Ukrainian legislation. 17 ASCs in communities have been restored, and 32 departments have been relocated from occupied territories, ensuring the operation of 49 centres. Administrative buildings have been equipped with modern computer technology and mobile workstations and connected to information and communication systems, electronic services, and state registers. This has enabled the creation of 102 access points to 15 state registers, providing residents with open and unimpeded access to administrative services. In view of persistent cyber threats from the Russian Federation, protocols for protecting information systems have been developed and implemented, including data backup, multi-level authentication, and access monitoring. ASC staff have completed training in cyber hygiene and incident response, enabling timely detection and neutralization of unauthorized-access attempts. In this way, the institutional capacity of ASCs has been restored, and they have been equipped with equipment, integration with electronic systems, and cyber-defence protocols, ensuring stable, transparent, accessible and secure provision of municipal services to residents of de-occupied territories. Chernihiv Oblast ASCs have been established and operate in all 57 communities of Chernihiv Oblast. |  |  |  | Kharkiv Oblast Unstable situation in the region. Once the situation stabilizes in each territorial community, restoration of full-time (stationary) ASCs is planned, providing the full range of administrative services. |
| 10. Implementing priority measures for the economic and social adaptation and rehabilitation of citizens in de-occupied territories | Implementing a set of measures to support the civilian population | 2025— 2027 | appropriate support provided to the population | Ongoing | Donetsk Oblast During 2025, owing to a deteriorating security situation, business activity declined in the de-occupied communities of Donetsk Oblast (Lyman and Sviatohirsk city territorial communities); nevertheless, humanitarian aid deliveries continued, information and career-guidance online events on employment-service offerings were held, and social and administrative services continued to be provided. As of 01.01.2026, 9 grocery stores were operating in the communities' territory. Banks, ATMs, Nova Poshta branches, filling stations, car-service stations, pharmacies, etc., had ceased operations. Kyiv Oblast To support the economic and social adaptation and rehabilitation of citizens in de-occupied territories, measures are being implemented under corresponding oblast targeted programmes aimed at restoring access to social services, meeting the population's basic needs, providing psychological support, promoting employment through support for small and medium-sized business development, and restoring social-infrastructure facilities and housing stock that were destroyed or damaged. Luhansk Oblast Implementation has not begun. Mykolaiv Oblast A civilian-population support coordination centre operates under the Mykolaiv Oblast Military Administration, along with 4 civilian-population support coordination centres under the Mykolaiv, Pervomaisk, Voznesensk and Bashtanka district military administrations and in the oblast's communities. An IDP council operates under the Mykolaiv Oblast Military Administration, along with 4 IDP councils under the Mykolaiv, Pervomaisk, Voznesensk and Bashtanka district military administrations and in the oblast's communities. As of 01.01.2026, 82,913 internally displaced persons have been registered in Mykolaiv Oblast since 24.02.2022, of whom 48,277 are children. During 2025, 3,257 internally displaced persons used employment-service services, of whom 1,184 received unemployment benefits. With the assistance of the oblast employment service, 691 people were placed in jobs, and 151 internally displaced persons underwent vocational training. 93 internally displaced persons received training vouchers. 790 internally displaced persons participated in socially useful work. Employers received compensation for hiring 304 internally displaced persons. In 2025, 14 microgrants were provided to internally displaced persons for starting and developing businesses, for opening shops, a restaurant complex, a café, a beauty studio, and metal-products manufacturing. In total, during 2025, 32 career-guidance events were held, attended by 355 people. A Mobile Employment Centre (a specially equipped vehicle) operates in the oblast, obtained with the assistance of international aid from the UN Development Programme (UNDP) in Ukraine, within the framework of the Recovery and Peacebuilding Programme, with financial support from the Government of Germany. Since the start of 2025, 6 field visits have been conducted, during which services were provided to 212 residents of communities in Bashtanka and Mykolaiv districts affected by hostilities. 184 international organizations operate in Mykolaiv Oblast, having provided assistance to 96,000 IDPs, including: assistance in preparing for the heating season, support for material and technical resources, provision of multi-purpose cash assistance, and support for families with children affected by hostilities, among other things. In particular, the ILO project "Support for Job Creation and the Development of Social Dialogue in Mykolaiv Oblast" is being implemented, funded by the Embassy of Denmark in Ukraine. Winners will receive up to $3,000 (in hryvnia) to purchase: equipment, tools, and machinery (at least 80% of the budget), and raw materials, supplies, rent, services, etc. (up to 20% of the budget). Priority is given to: IDPs, veterans, people with disabilities and their families, single parents, large families, households with pregnant women or infants, women, and people aged 45+. The project runs through April 2026. Expected results and impact: 750+ people integrated into the labour market, including IDPs and veterans; 400+ people who have undergone retraining and upskilling; 40 grants for starting a business, for entrepreneurship and self-employment; establishment of one tripartite social-dialogue platform in a key economic sector; increased participation of women in traditionally male-dominated fields; and strengthened institutional capacity of stakeholders to participate in social dialogue. Civil society organizations also provide comprehensive support to the war-affected civilian population. In particular, the Assistance Centre of the "Shchedryk" Charitable Foundation provides the following services: 1) individual consultations; 2) socio-psychological assistance; 3) social support/case management and help with processing social benefits; 4) legal counselling and help restoring documents; 5) training, retraining, employment promotion, job placement, and job creation. 225 people completed a two-week training programme in "Business Planning and Small Grants," of whom 83 received grants to develop their own businesses (from €2,300 to €4,500), for a total amount of €331,700; 50 people were successfully placed in jobs at municipal enterprises of the city of Mykolaiv; 6) a children's space (creative, educational and group activities). Kharkiv Oblast To carry out priority measures for the social adaptation and rehabilitation of citizens, 31 social-service providers operate in territorial communities in de-occupied territories. In 2025, social services covered more than 46,000 people. Chernihiv Oblast Since the end of the active phase of hostilities (03.04.2022), the proper functioning of authorities at all levels has been restored in Chernihiv Oblast, enabling the full implementation of state policy on supporting and protecting the civilian population. |  | Kyiv Oblast 8149,0 |  |  |
| 11. Creating conditions for the integration of de-occupied territories into a unified Ukrainian information space, and blocking Russian Federation informational influence | 1)Expanding broadcast access (coverage) for the Ministry of Defence's linear media | November 2027 | additional temporary broadcasting permits obtained | Ongoing | Ministry of Defence Expansion of the information space of the military radio station Army FM in Odesa, Dnipropetrovsk, Sumy, Chernihiv, Kharkiv and Zaporizhzhia oblasts. Implementation of the necessary measures is possible subject to the allocation of financial resources and the receipt of additional temporary broadcasting permits. |  |  |  |  |
|  | 2) Ensuring broadcast provision of audiovisual media and access to audiovisual-service provider networks | November 2027 | broadcasting licences and temporary broadcasting permits issued, and registration of audiovisual-service providers completed. | Not started | The implementation deadline has not yet arrived. |  |  |  |  |
| 12. Introducing a system of mental reintegration and psychological support for residents of de-occupied territories | 1) Introducing a system of mental reintegration and providing psychosocial assistance to the population of de-occupied territories, with the involvement of representatives of the National Mental Health Programme of Ukraine | 2027 | psychosocial assistance provided to 100 percent of residents of de-occupied territories who requested such assistance. | Ongoing | State Labour Service of Ukraine Since the start of 2025, State Labour Service labour inspectors have conducted 13,354 outreach events on the effectiveness of introducing workplace psychosocial support and preventing mobbing and discrimination, reaching 194,491 people (including those from de-occupied territories). Implementation is carried out within allocated budget appropriations. | In 2025, UAH 688.5 million was used under the budget programme "Direction and Management in the Field of Industrial Safety, Occupational Safety and Health, and Labour Legislation Compliance Oversight." |  |  |  |
|  | 2) Implementing measures and programmes to support mental health in the workplace | 2025-2027 | a workplace psychosocial-support system introduced; model documents developed (a programme, an action plan, sections of collective agreements and internal labour-regulation rules, etc.) on mental-health support, and published on the official website of the Ministry of Economy | Ongoing | Ministry of Economy Methodological recommendations for employers and model documents on introducing workplace psychosocial support for employees have been developed (a policy, a programme, an action plan, a needs-assessment questionnaire and a situation-assessment questionnaire, and monitoring and evaluation tools). The methodological recommendations on introducing workplace psychosocial support for employers, with annexes, are published on the official website of the Ministry of Economy, http://www.me.gov.ua, under "Activities"/"Working Conditions"/"Occupational Safety." State Labour Service of Ukraine To create conditions for effective advocacy for implementing workplace psychosocial-support measures, the following was carried out in 2025: - 2 trainers on workplace mental health completed professional training (based at the Ukrainian Catholic University); - a training course for labour inspectors, "Psychosocial Support at Work," was developed for a distance-learning course; - internal training was held for State Labour Service specialists, during which 20 specialists underwent professional development; - with the support of the Mental Health Coordination Centre, 41 specialists were trained in implementing psychosocial support and providing first psychological aid. The State Labour Service and its territorial bodies have implemented workplace psychosocial-support programmes for wartime and the post-war period. In implementing these programmes, the main steps used in rolling out a workplace psychosocial-support programme at the employer level were developed. Methodological recommendations for employers and model documents on introducing workplace psychosocial support for employees (a policy, an action plan, a needs-assessment questionnaire and a situation-assessment questionnaire, and monitoring and evaluation tools) have also been developed and published on the State Labour Service's information portal, pratsia.in.ua. The State Labour Service informs employees and employers about their rights and obligations, about available resources for reducing stress levels, how to recognize stress, how to strengthen mental health, how to support employees and colleagues, and how to create a safe and healthy workplace. The inspector's task is not to control the process but to provide the employer with information and support in implementing a psychosocial-support programme. During 2025, through informational visits, 116,666 business entities were informed about the possibility of introducing a workplace psychosocial-support policy with the assistance of State Labour Service territorial bodies; 1,047 employers have already introduced such a policy. 6,126 seminars on this topic were held, and 11,180 publications and 139 media reports were issued. To disseminate positive practices in introducing workplace psychosocial support, as part of marking Occupational Safety Day, the State Labour Service held an online exhibition of presentations by employers who have introduced psychosocial-support programmes for their employees, titled "Effective Workplace Psychosocial-Support Programmes and Their Implementation." A total of 117 psychosocial-support programmes were submitted for participation, of which 96 were published; open online voting ran until 01.11.2025. In September 2025, the State Labour Service, together with the Mental Health Coordination Centre, conducted a survey of employers to determine the level of employer awareness of the importance of workplace mental-health support, to analyse current practices, barriers to implementing programmes, and organizations' resource needs, and to assess readiness to integrate such approaches into company policies. The survey covered 856 employers of various types — from private companies and state enterprises to public authorities, educational institutions, and civil society organizations. Among sources of information about psychosocial support, respondents most often cited trainings and seminars (22.7%), with State Labour Service inspectors ranking third (14.3%), demonstrating the impact of the State Labour Service's advisory functions. Among the initiators of employee mental-health support measures, State Labour Service bodies also rank third (17.9%). |  |  |  |  |
| Area: "Protection and Restoration of the Natural Environment" |  |  |  |  |  |  |  |  |  |
| 13. Introducing special mechanisms for the restoration and development of territories and water bodies affected by the destruction of the Kakhovka Hydroelectric Power Plant dam | Conducting scientific research on the damage caused and identifying ways to restore territories affected by the destruction of the Kakhovka HPP dam, taking into account long-term environmental damage, including an assessment of the economic impact on the spatial development of regions along the Dnipro river basin and on the operation of the North Crimean Canal and the Kakhovka Main Canalр. Дніпро та функціонування Північнокримського каналу та Каховського магістрального каналу | 2025—2027 | scientifically grounded ways identified for restoring natural resources, destroyed ecosystems and the region's ecological balance, and the agro-industrial complex and infrastructure affected by the destruction of the Kakhovka HPP dam | Not started | The implementation deadline has not yet arrived. |  |  |  |  |
| 14. Ensuring the socio-economic development of territories adjacent to the centralized spent nuclear fuel storage facility (including the Slavutych, Ivankiv and Polissia territorial communities of Kyiv Oblast) | Promoting the restoration and ensuring the operation of a coordination centre for the operational management of fires and emergencies in the Chornobyl Radiation and Ecological Biosphere Reserve | 2027 | operation of the coordination centre ensured | Not started | The implementation deadline has not yet arrived. |  |  |  |  |
| 15. Ensuring the modernization, technical re-equipping and alignment with European standards of regional hydrometeorological observation systems and environmental pollution monitoring systems | 1) Technical re-equipping of regional hydrometeorological observation systems and environmental pollution monitoring systems | 2025-2027 | automated observation stations, instruments and equipment, and computer technology installed; state groundwater monitoring observation stations repaired | Ongoing on a continuous basis | Ministry of Internal Affairs of Ukraine (MIA) During 2025, the State Emergency Service installed automated observation stations, instruments and equipment, and computer technology, and repaired observation stations, for a total of UAH 148,644.69 thousand. This included: instruments and equipment for hydrometeorological activities purchased from the general fund of the state budget for UAH 71,310.0 thousand, and capital repairs of premises for a total of UAH 3,685.1 thousand; hydrometeorological equipment and computer technology purchased from the special fund of the state budget for UAH 1,332.37 thousand, and capital construction, capital repairs, reconstruction and restoration of facilities for UAH 393.7 thousand. In total, from the state budget, modernization and technical re-equipping, construction, capital repairs, reconstruction and restoration of facilities were carried out for UAH 76,721.17 thousand. Using local-budget subventions, instruments and a stationary air-pollution monitoring station were purchased for UAH 7,152.02 thousand. Charitable and humanitarian assistance in kind was received: from the IAEA, in the form of radiological instruments and equipment, worth UAH 21,472.5 thousand; from the UK Met Office, in the form of equipment and computer technology, worth UAH 565.9 thousand; from the Finnish Meteorological Institute, in the form of meteorological equipment, worth UAH 478.8 thousand; from the U.S. Department of Energy, in the form of hydrometeorological equipment, instruments and computer technology, worth UAH 31,689.5 thousand; under the DANSER HORIZONMISS grant agreement, in the form of equipment, worth UAH 94.6 thousand; and from Hala Systems, Unipessoal, Lda. (Lisbon, Portugal), in the form of software, worth UAH 10,470.2 thousand. In total, charitable assistance, humanitarian assistance and grants worth UAH 64,771.5 thousand were received. | Ministry of Internal Affairs of Ukraine 148 644,69 |  |  | State Water Agency In 2022–2025, funding was lacking for the full implementation of the tasks and measures of the National Programme for the Development of Ukraine's Mineral Resource Base for the period until 2030. |
|  | 2) Accreditation of State Water Agency water-monitoring laboratories in accordance with DSTU EN ISO/IEC 17025:2019 | 2025—2027 | our accreditation certificates obtained, and accredited testing-laboratory status maintained | Completed | - Ministry of Economy of Ukraine 4 water-monitoring laboratories have been accredited in accordance with DSTU EN ISO/IEC 17025:2019 (the Water Monitoring Laboratory of the Western Region of the Dniester River Basin Management Authority — accreditation certificate No. 202265 of 10.03.2025; the Water Monitoring Laboratory of the Eastern Region of the Siverskyi Donets River Basin Management Authority — accreditation certificate No. 202269 of 13.01.2025; the Water Monitoring Laboratory of the Northern Region of the Dnipro Reservoirs Water Quality Monitoring Association — accreditation certificate No. 202377 of 04.01.2024; the Water Monitoring Laboratory of the Southern Region of the Black Sea Coast and Lower Danube Rivers Basin Management Authority — accreditation certificate No. 202405 of 29.09.2025). State Water Agency Operation of the AIVS "TYSA" and AIVS "Prykarpattia" automated information and measurement systems has been ensured. The automated water-monitoring system has been accredited for hydrographic measurements, and the operation and data collection of the AIVS TYSA automated system, in accordance with DSTU EN ISO 9001:2015. |  |  |  |  |
|  | 3) Accreditation of laboratories for environmental monitoring in accordance with the requirements of DSTU EN ISO/IEC 17025:2019 | 2025-2027 | accreditation certificates obtained, and accredited laboratory status maintained | Ongoing | Ministry of Economy of Ukraine Two accreditation certificates have been obtained, and accredited testing-laboratory status is being maintained. |  |  |  | State Water Agency In 2022–2025, funding was lacking for the full implementation of the tasks and measures of the National Programme for the Development of Ukraine's Mineral Resource Base for the period until 2030. |
| 16. Establishing a proper system for managing and restoring coastal and marine ecosystems, and promoting the development of mariculture (the commercial breeding and cultivation of marine aquatic living resources) in coastal areas in an environmentally sound manner | Supporting, in the Verkhovna Rada of Ukraine, draft Law of Ukraine "On Stimulating the Economic Development of the Fisheries Sector" (registration No. 12384 of 8 January 2025) | until the Law is adopted | the Law adopted | Ongoing | Ministry of Economy of Ukraine Draft Law "On Stimulating the Economic Development of the Fisheries Sector" (registration No. 12384 of 08.01.2025) was adopted as a basis on 13.05.2025, with further refinement of its provisions in accordance with part 1 of Article 116 of the Rules of Procedure of the Verkhovna Rada of Ukraine. |  |  |  |  |
| 17. Promoting measures for creating forests on land of all forms of ownership, preserving self-seeded forests, identifying land suitable for afforestation by state authorities and local self-government bodies, and assigning to permanent users linear-type protective plantings and forests not currently allocated for use | 1) Restoring forests as part of implementing the environmental initiative "Large-Scale Afforestation of Ukraine," in accordance with the Decree of the President of Ukraine "On Certain Measures for the Conservation and Restoration of Forests," | 2027 | forests restored on an area of 26,000 hectares | Ongoing | Ministry of Economy of Ukraine In 2025, state forestry enterprises under the management of the State Forest Resources Agency of Ukraine carried out reforestation on an area of 18,100 hectares. |  |  |  |  |
|  | 2) Implementing forest-restoration and shelterbelt-reconstruction projects, including the preservation and restoration of natural ecosystems | 2025—2027 | 100 percent reforestation ensured through the establishment of forest plantations | Ongoing on a continuous basis. | Ministry of Economy of Ukraine 100% reforestation has been ensured. In 2025, state forestry enterprises under the management of the State Forest Resources Agency of Ukraine carried out reforestation on an area of 18,100 hectares, of which forest plantations were established on 11,300 hectares, and natural regeneration was ensured on 6,800 hectares. |  |  |  | In accordance with the fourth paragraph of the subsection "Adapting Forests to Climate Change and Transitioning to Nature-Close Forestry Methods, Forming Forests of Natural Composition and Structure" of Section IV, "Tasks Aimed at Achieving the Defined Strategic Goals, Their Implementation Stages, Expected Results at Each Stage, Reflecting the Planned Pace of Achieving Target Indicators, and the Estimated Volume of Necessary Financial, Material/Technical, Human and Other Resources," of the State Forest Management Strategy of Ukraine until 2035, approved by Order of the Cabinet of Ministers of Ukraine No. 1777 of 29.12.2021 (hereinafter — the Strategy), it is envisaged, among other things, to increase forest resilience to climate change through the use of natural regeneration for forest restoration. Also, in accordance with the requirements of Regulation (EU) 2023/1115 of the European Parliament and of the Council of 31 May 2023 on the making available on the Union market and the export from the Union of certain commodities and products associated with deforestation and forest degradation, and repealing Regulation (EU) No. 995/2010 (hereinafter — the Regulation), converting naturally regenerated forests into artificially established forests (creating forest plantations) may in certain cases be considered forest degradation, which would constitute a violation of the Regulation's requirements regarding the prevention of forest degradation. In view of the above, ensuring 100 percent reforestation through the establishment of forest plantations would contradict the Strategy and the requirements of the Regulation. |
|  | 3) Developing a Methodology for classifying plots as self-seeded (naturally afforested) land, with a clear procedure for inspecting such territories and coordinating conclusions with local self-government bodies | 2025—2027 | an order of the Ministry of Economy issued | Not started |  |  |  |  |  |
|  | 4) Classifying state- and municipally-owned land plots as self-seeded plots and transferring them for permanent use to business entities for subsequent forestry management | 2025—2027 | 100 percent classification of state- and municipally-owned land plots as self-seeded plots ensured, and their transfer for permanent use ensured |  | Vinnytsia Oblast 1,622.0 hectares have been classified as self-seeded plots, and decisions have been made to transfer them for permanent use, of which 859.0 hectares will go to state forestry enterprises and 763.0 hectares to municipal forestry enterprises. Zhytomyr Oblast. Self-seeded land planned for transfer to permanent use: 15,890.19113 hectares; transferred to permanent use: 4,368.3935 hectares, i.e., 72.8%. In accordance with the oblast environmental protection fund's expenditure estimate for 2025 (No. 931 of 11.12.2024), no funding is provided for this measure. Zakarpattia Oblast By Order No. 945 of the Head of the Oblast State Administration – Head of the Military Administration of 21.12.2022, the Forestry Development Programme of Zakarpattia Oblast for 2022–2027 was approved. Pursuant to items 1.6.1 and 1.6.3 of the National Security and Defence Council of Ukraine's decision of 29 September 2022, "On the Protection, Defence, Use and Restoration of Ukraine's Forests in a Special Period," enacted by Presidential Decree No. 675/2022 of 29 September 2022, as of 31 December 2025, branches of the Carpathian Forest Office established forest plantations on 389.4 hectares in the oblast and carried out supplementary planting on 264.9 hectares. Measures to promote natural regeneration were carried out on 198.8 hectares. Pursuant to the tasks set out in Presidential Decree No. 228/2021 of 07.06.2021, "On Certain Measures for the Conservation and Restoration of Forests," branches of the Carpathian Forest Office in Zakarpattia Oblast planted 2,003.294 thousand seedlings in 2025. At the same time, it should be noted that in Zakarpattia Oblast, the main share of afforestation measures involves gradual final-felling harvests left for natural regeneration. Implementation of the Presidential Decree continues. Zaporizhzhia Oblast. As of 01.01.2026, local self-government bodies had adopted decisions transferring 79 self-seeded plots totalling 851.4 hectares for permanent use to the State Enterprise "Forests of Ukraine." In addition, during the reporting period, the Working Group for Inspecting Land Plots That May Be Classified as "Self-Seeded Plots" and Forestry-Purpose Land Plots Not Allocated for Use within Administrative-Territorial Units (established by Order No. 110 of the South-Eastern Interregional Forestry and Hunting Management Authority of 18.11.2024, as amended) inspected 24 land plots totalling 371.1147 hectares for subsequent transfer to the State Enterprise "Forests of Ukraine" for permanent use. Ivano-Frankivsk Oblast During 2025, 99 submissions were sent to local self-government bodies regarding identified self-seeded plots totalling 8,529 hectares, for subsequent assignment to permanent forest users. A decision was made to classify 1.0 hectare of municipally owned land as self-seeded. Kyiv Oblast Following consideration of petitions from the State Specialized Business Enterprise "Forests of Ukraine" and its structural units regarding the registration of permanent-use rights to forestry-purpose land plots in Kyiv Oblast, the Kyiv Oblast State Administration (Kyiv Oblast Military Administration) issued 38 orders, on the basis of which property rights were registered for forestry-purpose land plots totalling 11,850.9331 hectares. Kirovohrad Oblast In 2025, 80.99 hectares of state- and municipally-owned land were classified as self-seeded plots. 51 hectares of self-seeded land were transferred to the State Enterprise "Forests of Ukraine" for permanent use in forestry management. Luhansk Oblast Implementation has not begun. Lviv Oblast The Oblast State Administration coordinates work to identify self-seeded plots in the oblast for their transfer to permanent use by forestry enterprises for forestry management. A list of self-seeded plots and land plots suitable for forest establishment, totalling 1,141.56 hectares, has been compiled. This list has been sent to the State Enterprise "Forests of Ukraine," its branch "Carpathian Forest Office," the Western Interregional Forestry and Hunting Management Authority, and the joint-stock forestry company "Halsilliis," for joint processing with the oblast's territorial communities to determine the availability of state- and municipally-owned self-seeded plots and plots suitable for forest establishment, for subsequent transfer to the oblast's forestry enterprises. Mykolaiv Oblast Work is under way on identifying and transferring self-seeded and other afforestation-suitable land plots from territorial communities to state forestry enterprises. Significant territories of Mykolaiv Oblast that were under shelling and along the frontline require substantial demining efforts. Transfer of these territories cannot currently be considered. Poltava Oblast Implementation is ongoing, except for the transfer of land plots for permanent use. Rivne Oblast Potentially self-seeded land plots totalling 62,995 hectares have been identified; 203 submissions, plus an additional 94, have been sent to local self-government bodies, of which the classification of 1,216 hectares as self-seeded plots has been agreed (including 772 hectares transferred to forestry enterprises). Sumy Oblast According to local self-government bodies, 192 land plots totalling 1,669.56 hectares have been classified as self-seeded in the oblast. Ternopil Oblast During 2025, the Oblast Military Administration's Department of Ecology and Natural Resources, together with representatives of the South-Western Interregional Forestry and Hunting Management Authority, the "Podillia Forest Office" branch of the State Specialized Business Enterprise "Forests of Ukraine," and the Kremenets city, Vyshnivets and Melnytsia-Podilska settlement, and Borsukivka, Ivane-Pusteme and Lopushne village councils, inspected 43 self-seeded land plots totalling 737 hectares in their subordinate territories, to assess the feasibility of classifying them as forestry-purpose land; natural regeneration of forests was identified on these plots. Local councils have been recommended to transfer the inspected self-seeded land plots for permanent use to state and municipal forestry enterprises and to municipal enterprises with specialized forestry units. In addition, local councils have adopted decisions changing land-category composition on 52 hectares, and identification work is ongoing on a further 388 plots. Kharkiv Oblast The Department for Environmental Protection and Nature Use of the Kharkiv Oblast State (Military) Administration sent letters to city, settlement and village territorial communities and military administrations of settlements in Kharkiv Oblast, proposing measures to implement these subparagraphs. In particular, regarding the classification of land plots as self-seeded, according to data from the state organization "Ukrderzhlisproekt," as of 16.12.2025, potentially self-seeded state- and municipally-owned land plots in Kharkiv Oblast, identified via the geoportal, total an estimated 63,400 hectares. In accordance with Article 57(1) of the Land Code of Ukraine, the North-Eastern Interregional Forestry and Hunting Management Authority sent 169 submissions to territorial communities (excluding occupied ones) proposing to classify identified land plots as self-seeded, of which positive decisions were received covering a total of 1,069 hectares. Territorial communities that have not adopted positive decisions are conducting a comprehensive review of whether their land plots qualify as self-seeded. According to information from the oblast's territorial communities, work on classifying state- and municipally-owned land plots as self-seeded is ongoing. The Oskil Rural Military Administration reported that, pursuant to a submission from the North-Eastern Interregional Forestry and Hunting Management Authority, 3 land plots totalling 29.9 hectares were classified as self-seeded during 2025. By orders of the Head of the Oskil Rural Military Administration No. 415 of 07.04.2025 and No. 1188 of 01.10.2025, information on the reclassification of land categories to self-seeded land plots was entered into the State Land Cadastre, and permits were issued to the State Specialized Business Enterprise "Forests of Ukraine" to develop land-management projects for allocating the plots. Bohodukhiv City Council of Bohodukhiv District, following a desktop review analysis of self-seeded land-plot availability, identified a potentially afforested municipally owned land plot exceeding 1.0 hectare; the question of its classification as self-seeded will be considered at a forthcoming session of Bohodukhiv City Council. Specialists of Sakhnovshchyna Settlement Council of Berestyn District conducted field visits to identify land plots for afforestation, identifying a self-seeded land plot of approximately 5 hectares within the Shevchenkove starosta district. The Kuniivka Rural Military Administration of Izium District carried out work and, by corresponding orders, approved the reclassification and change of land categories of municipally owned agricultural-purpose land plots to self-seeded land plots totalling 2.3 hectares. To preserve and restore forests, Slobozhanske City Council of Chuhuiv District has incorporated corresponding measures into the Programme on Land Relations, Rational Use and Protection of Land of Slobozhanske territorial community for 2026–2030, to be implemented subject to available funding and the security situation. Work is also under way to transfer linear-type protective plantings for use. In particular, a specialized municipal enterprise, "Forestry" of Kolomak Settlement Council, has been established in Kharkiv Oblast, holding 223.3 hectares of shelterbelt forest strips of Kolomak settlement territorial community for use; the forest-management materials of these enterprises are undergoing approval procedures. In addition, the Department of Housing and Communal Services and Construction of Lozova City Council has already registered 716 hectares of linear-type plantings for use, with work ongoing on registering the remaining 959 hectares for permanent use and conducting forest management surveys. Consideration of land classification as self-seeded is constrained by the absence of a methodology for classifying plots as self-seeded land, with a clear procedure for inspecting such territories. In addition, in some of the region's territorial communities, this work is hindered by ongoing hostilities and contamination of land in certain territorial communities with explosive ordnance. Kherson Oblast The Department for Environmental and Natural Resource Protection of the Kherson Oblast State Administration has appealed to district military administrations of the oblast's de-occupied territories, requesting that they identify self-seeded land plots in the relevant territories. Military administrations of settlements in the oblast's de-occupied territories have been instructed to: 1) carry out work to identify self-seeded land plots in the relevant territories; 2) mark identified land plots on a cartographic base (with reference to cadastral numbers of the nearest land plots or geographic coordinates), indicating the estimated area; and 3) provide consolidated information to the Department for Environmental and Natural Resource Protection of the Kherson Oblast State Administration. Owing to the absence of an approved Methodology for classifying plots as self-seeded land, no plots have been transferred for permanent use to business entities for subsequent forestry management. Khmelnytskyi Oblast As of 01.01.2026, 555.0 hectares have been classified as self-seeded land plots, of which 513.0 hectares have been transferred to permanent users (92.4%). Cherkasy Oblast In 2025: local self-government bodies of the oblast adopted decisions classifying 978 hectares of municipally- and state-owned land plots as "self-seeded land"; land-management project documentation was developed for 610 hectares; and extracts from the State Register of Property Rights to Real Estate were obtained for 602 hectares. Chernivtsi Oblast A decision to classify a plot as self-seeded is adopted by executive authorities or local self-government bodies based on a submission from the territorial body implementing forestry policy. This process involves entering the information into the State Land Cadastre. During 2025, an inventory of land in this category was carried out. Once the information is entered into the State Land Cadastre, the question of registering property rights will be considered. Chernihiv Oblast In Chernihiv Oblast, 82 hectares of such land plots have been classified as self-seeded. |  |  | Vinnytsia Oblast 4800 Cherkasy Oblast 111,4 | Donetsk Oblast Implementation of this measure will only become possible once active hostilities in the oblast end, martial law is terminated or lifted, the territory is de-occupied, demining work is completed, and a comprehensive survey is conducted. Zakarpattia Oblast Territorial communities are not agreeing to petitions for classifying land plots in the "self-seeded" category. Ivano-Frankivsk Oblast There is a lack of response and understanding on the part of local self-government bodies regarding the importance of identifying and transferring self-seeded plots to permanent forest users. Poltava Oblast Lack of measures to ensure implementation of Presidential Decrees No. 228/2021 of 07.06.2021 and No. 675/2022 of 29.09.2022. Rivne Oblast Local self-government bodies have refused requests covering 30,700 hectares, and there has been no response regarding consideration of classifying 24,000 hectares as self-seeded land. Sumy Oblast Changing the designated use of land plots from agricultural to forestry purposes is complicated by communities' lack of interest in reducing agricultural land area and in the resulting loss of revenue from its use. Ternopil Oblast Village, settlement and city councils are not allocating funds for developing land-management documentation to form self-seeded land plots. Kherson Oblast Active hostilities in de-occupied territory and the temporary occupation of the oblast's left-bank part. |
|  | 5) Assigning to permanent users linear-type protective plantings and forests not currently allocated for use | 2025—2027 | 100 percent assignment to permanent users of linear-type protective plantings and forests not currently allocated for use, ensured |  | Vinnytsia Oblast 6,943.2 hectares of linear-type protective plantings and forests not allocated for use have been assigned to permanent users (20.6% of the total area of 33,700 hectares). Zaporizhzhia Oblast As of 01.01.2026, local self-government bodies had adopted decisions transferring 43 municipally owned land plots totalling 667.8 hectares for permanent use to the State Enterprise "Forests of Ukraine." In addition, by Order No. 833 of the Head of the Oblast State Administration, Head of the Oblast Military Administration, of 04.08.2025, 9 land plots totalling 132.0186 hectares, located in Novomykolaivka settlement territorial community, were transferred into state ownership for forestry management and related services. Zhytomyr Oblast In accordance with Resolution of the Cabinet of Ministers of Ukraine No. 650 of 22.07.20, on rules for the maintenance and preservation of agricultural shelterbelts. Land users carry out measures to maintain and preserve shelterbelt forest strips, based on forest-management materials or commission inspections, to determine the need for urgent measures to improve the sanitary condition of shelterbelt forest strips and eliminate the consequences of emergencies (accidents, natural disasters, etc.) in damaged, low-efficiency, thinned or dying plantings that are losing their protective function. In accordance with the oblast environmental protection fund's expenditure estimate for 2025 (No. 931 of 11.12.2024), no funding is provided for this measure. Ivano-Frankivsk Oblast During the reporting year, two letters were sent to the "Carpathian Forest Office" branch regarding three identified forested land plots (forests not transferred): one plot of 146.3266 hectares in Solotvyn territorial community, and two plots totalling 104.4256 hectares in Dolyna city territorial community. Tysmenytsia City Council adopted a decision granting the State Enterprise "Forests of Ukraine" permission to develop a land-management project for allocating land plots totalling 218.6 hectares for permanent use (forests not allocated for use). Kyiv Oblast Local self-government bodies, together with agricultural enterprises and road-maintenance organizations, have begun work to identify linear-type protective plantings and forests not allocated for use, for assignment to permanent users. Lviv Oblast The "Carpathian Forest Office" branch of the State Enterprise "Forests of Ukraine" has registered property rights to self-seeded land plots totalling 51 hectares. Mykolaiv Oblast Linear-type protective plantings have been transferred to the oblast's territorial communities. Sumy Oblast Title documents for land plots are being re-registered, transferring them from the Infrastructure Restoration and Development Service in Sumy Oblast (Road Service in Sumy Oblast) to the State Institution "Infrastructure of Sumy Region." Ternopil Oblast Village, settlement and city councils have inventoried 34.46% of municipal forests, amounting to 63.39 thousand hectares; of 18.4 thousand hectares of inventoried forest-fund land, 6,561.9443 hectares that were held as reserve land have been transferred for use to municipal and state forestry enterprises and to municipal enterprises with specialized forestry units, representing 75.7% of formed forest-fund land plots — including 52.0% in Kremenets District, 69.0% in Ternopil District, and 68% in Chortkiv District. Kharkiv Oblast The Department for Environmental Protection and Nature Use of the Kharkiv Oblast State (Military) Administration sent letters to city, settlement and village territorial communities and military administrations of settlements in Kharkiv Oblast, proposing measures to implement these subparagraphs. In particular, regarding the classification of land plots as self-seeded, according to data from the state organization "Ukrderzhlisproekt," as of 16.12.2025, potentially self-seeded state- and municipally-owned land plots in Kharkiv Oblast, identified via the geoportal, total an estimated 63,400 hectares. In accordance with Article 57(1) of the Land Code of Ukraine, the North-Eastern Interregional Forestry and Hunting Management Authority sent 169 submissions to territorial communities (excluding occupied ones) proposing to classify identified land plots as self-seeded, of which positive decisions were received covering a total of 1,069 hectares. Territorial communities that have not adopted positive decisions are conducting a comprehensive review of whether their land plots qualify as self-seeded. According to information from the oblast's territorial communities, work on classifying state- and municipally-owned land plots as self-seeded is ongoing. Khmelnytskyi Oblast No information has been received from local self-government bodies regarding the assignment to permanent users of linear-type protective plantings and forests not allocated for use. Cherkasy Oblast In 2025: 582 hectares of forest land not allocated for use were transferred for permanent use; petitions for land-management project development were submitted covering 491 hectares; and petitions for approval of land-management projects were submitted covering 162 hectares. Chernivtsi Oblast In accordance with current legislation, the State Enterprise "Forests of Ukraine" is taking action to form land plots under linear-type protective plantings (shelterbelts) and forests not allocated for use, in order to register permanent-use rights. Chernihiv Oblast In Chernihiv Oblast, 233.5 hectares of such land plots have been assigned to permanent users. |  | Ternopil Oblast 153,9 | Cherkasy Oblast 234,0 | Vinnytsia Oblast Lack of land-management documentation, and an undetermined legal status of the land and plantings. Donetsk Oblast Implementation of this measure will only become possible once active hostilities in the oblast end, martial law is terminated or lifted, the territory is de-occupied, demining work is completed, and a comprehensive survey is conducted. Ternopil Oblast Local councils are not allocating funds from territorial-community budgets for implementing measures to inventory municipal forests. |
| Operational Goal 2. Meeting the population's need for quality administrative and public services |  |  |  |  |  |  |  |  |  |
| Area: "Educational Services" |  |  |  |  |  |  |  |  |  |
| 18.Improving the material and technical base of educational institutions, and ensuring the quality of educational services, including in rural areas | 1)Establishing (upgrading) safety classrooms in educational institutions and ensuring their operation | 2025—2027 | 4,500 safety classrooms established and operating in educational institutions | Ongoing | Ministry of Internal Affairs (MIA) As of 01.03.2026, with the involvement of State Emergency Service territorial bodies, 4,286 safety classrooms have been established. Of these, 3,294 safety classrooms are presentable and meet the recommendations approved by MES Order No. 135 of 10.02.2023, "Certain Issues Concerning the Establishment and Operation of Safety Classrooms in Educational Institutions." |  |  |  |  |
|  | 2) Equipping general secondary education institutions with civil-protection shelter facilities, funded from the state budget, to improve students' access to quality in-person education | 2025—2027 | general secondary education institutions equipped with civil-protection shelter-fund facilities to 90 percent |  | Ministry of Education and Science Under the Law of Ukraine "On the State Budget of Ukraine for 2025," Ministry of Education and Science was allocated budget programme 2211810, "Subvention from the State Budget to Local Budgets for Implementing a Public Investment Project to Arrange Safe Conditions in General Secondary Education Institutions (Shelter Arrangement), Including Military (Naval, Military-Sport) Lyceums and Lyceums with Enhanced Military-Physical Training" (hereinafter — the subvention), with total expenditure of UAH 6.2 billion. The procedure and conditions for providing this subvention were approved by Resolution of the Cabinet of Ministers of Ukraine No. 419 of 28 April 2023 (as amended by Resolution No. 1547 of 30 December 2024). Following a commission's selection of project applications and additional financing to complete projects begun in the previous period — which had been financed under the 2024 distribution of the subvention pursuant to Cabinet of Ministers decisions, provided such projects were at least 40 percent complete in terms of total cost — the subvention was allocated to 139 projects. Distribution of the subvention funds was carried out pursuant to Orders of the Cabinet of Ministers of Ukraine No. 127-r of 18 February 2025, No. 221-r of 14 March 2025, No. 357-r of 18 April 2025, and No. 452-r of 09 May 2025. By the end of 2025, UAH 4,237.5 million had been used under the subvention, representing approximately 69% of the allocated amount. According to data from oblast military administrations, as of the end of 2025, of the 139 facilities: 51 facilities had been completed (of which 1 military lyceum out of 3 approved, and 22 projects out of 27 begun in 2024 with readiness of at least 40%), representing 37% of the total number of projects; for 48 facilities, the rate of subvention-fund utilization was 60% or more. |  |  |  |  |
|  | 3) Establishing centres of vocational excellence through the modernization of vocational (vocational-technical) education institutions | 2025—2027 | 10 centres of vocational excellence established | Ongoing on a continuous basis | Ministry of Education and Science In 2025, with support from EU partners and the EIB, Ministry of Education and Science continued work to establish a network of centres of vocational excellence. Under the "Vocational Education in the Eastern Partnership" and "EU4Skills" projects, with KfW support, capital repairs of dormitories and workshops, and equipment procurement, are being carried out at selected educational institutions. Under the "Programme to Support Vocational-Technical Education in Ukraine," with EIB support, investment plans have been prepared for 7 institutions, design and cost-estimate documentation for dormitory reconstruction and preparatory work has been approved, and tender-documentation templates for construction works and equipment have been developed. The "Belgian Initiative to Support Ukraine's Recovery" project, with Enabel support, combines infrastructure measures at educational institutions in Kyiv and Chernihiv oblasts with "soft" components to strengthen management capacity, develop partnerships with business, and finance short-term vocational programmes. |  |  |  |  |
|  | 4) Modernizing workshops and laboratories of vocational and professional pre-higher education institutions | 2025—2027 | at least 80 workshops and laboratories established on a competitive basis | Ongoing on a continuous basis | Ministry of Education and Science In 2025, using state-budget subvention funds to local budgets, 71 educational and production centres (NPCs) were established, of which 52 were in vocational-technical education institutions and 19 in professional pre-higher education institutions; a further 16 will be completed in 2026. In addition, partners funded the establishment of 8 additional NPCs. |  |  |  |  |
|  | 5) Expanding the network of digital education centres in territorial communities affected by the Russian Federation's armed aggression against Ukraine, where children have limited access to offline education | 2025—2027 | at least 8 new digital education centres established in territorial communities | Ongoing on a continuous basis | Ministry of Education and Science In 2025, 108 digital education centres were opened in the following oblasts: Kharkiv, Kherson, Kyiv, Odesa, Mykolaiv, Dnipropetrovsk, Zaporizhzhia, Sumy, and Chernihiv. |  |  |  |  |
|  | 6) Providing educational institutions with teaching aids, computer and multimedia equipment/furniture, funded from the state budget | 2025—2027 | at least 80 percent of educational institutions equipped with teaching aids and equipment, computer and multimedia equipment, and furniture. | Ongoing on a continuous basis | Ministry of Education and Science In 2025, with the support of development partners, 28,140 devices were delivered; in total, as of the reporting period in 2025, 284,506 units of computer equipment had been delivered (with the support of development partners). |  |  |  |  |
|  | 7) Raising the digital competence of teaching staff at general secondary education institutions | 2025—2027 | at least 50 percent of teaching staff have completed training | Ongoing, on a continuous basis | Ministry of Education and Science In 2025, 153,544 teaching and academic staff completed digital-competence training courses provided by in-service teacher training institutes, the State Scientific Institution "Institute for Education Modernization," the "Ranok" Academy, and others. In addition, with the support of international partners, 31,248 teaching staff completed digital-competence development training in 2025. |  |  |  |  |
|  | 8) Ensuring the purchase of school buses to organize transportation of students and teaching staff, including persons with special educational needs, to and from general secondary education institutions, funded from the state budget | 2025—2027 | 90 percent of educational institutions provided with school buses | Ongoing on a continuous basis | Ministry of Education and Science In 2025, 535 school buses were purchased using subvention funds, including 374 specially equipped ones. In addition, 140 school buses, including 100 specially equipped ones, were purchased using the special fund of the educational subvention. |  |  |  |  |
| 19. Creating mechanisms to encourage business representatives to participate in upgrading the material/technical and teaching/production base of higher, professional pre-higher, and vocational (vocational-technical) education institutions | 1) Engaging stakeholders in managing vocational (vocational-technical) and professional pre-higher education institutions, delegating to them a significant share of the founder's functions for state and municipal institutions, through the establishment of supervisory boards | 2027 | supervisory boards established in 100 percent of vocational (vocational-technical) and professional pre-higher education institutions. | Ongoing | Ministry of Economy of Ukraine To engage stakeholders in managing vocational (vocational-technical) education institutions and strengthen ties with the labour market, orders of the Ministry of Economy of Ukraine established supervisory boards for vocational-technical education centres of the State Employment Service. In particular, in 2024, a supervisory board was established for the Poltava Vocational-Technical Education Centre, and in 2025, a further 7 supervisory boards were established (for the Dnipropetrovsk, Ivano-Frankivsk, Lviv, Odesa, Rivne, Sumy, and Kharkiv centres). Supervisory boards ensure the participation of employer representatives, authorities, and the public in managing educational institutions, help increase the transparency and effectiveness of their operations, oversee the quality of educational services and the use of financial resources, and attract additional funding sources for developing the material/technical and teaching/production base. Currently, the supervisory boards operate in accordance with the powers set out in their statutes, participate in forming and monitoring the implementation of the centres' development strategies, analyse their operational results, provide recommendations to management that must be considered, and initiate measures to improve the educational process and infrastructure. More than ten sessions of each supervisory board have been held, resulting in decisions and recommendations aimed at improving the quality of specialist training, strengthening human-resource capacity, and developing partnerships with employers. |  |  |  |  |
|  | 2) Disseminating best practices (experience exchange) in public-private partnership among vocational (vocational-technical) and professional pre-higher education institutions | 2025-2027 | at least five experience-exchange events held annually |  | Ministry of Economy of Ukraine Under the Ukrainian-Swiss project "Public-Private Partnership for Improving Vocational Education in Ukraine," during the reporting period: 350 students and 33 industrial-training instructors took part in master classes organized by partners (the State Enterprise "HERZ UKRAINE," Abicor Binzel Ukraine, DTEK, Paton, and others). In total, since the initiative began, business-led training has covered 701 students and 77 instructors in occupations supported by the Project; 20 excursions to production facilities of HERZ, PATON, DTEK, Abicor Binzel, Ecosoft and others were held, attended by 388 students. Business contributions in monetary terms amounted to UAH 226,000, 30% more than in the first half of 2025 (in total, 46 introductory production-site visits were held in 2025, attended by 885 students). A training was also held for students and industrial-training instructors, led by staff of "Sika Ukraine" LLC, to practise practical skills working with the company's products, which are to be subsequently incorporated into the educational programme for the tiling/cladding-worker occupation. Recommendations on organizing workplace-based training were compiled, based on the research report "Analysis of Vocational-Practical Training in Construction Occupations at Vocational (Vocational-Technical) Education Institutions." A round table, "Transformation of Vocational Education: Optimizing Vocational (Vocational-Technical) Education Institutions of Poltava City Territorial Community," was held, along with five meetings (in Chernivtsi, Zhytomyr, Poltava, Kyiv, and Brovary), at which areas of cooperation between vocational-education institutions and local business partners were identified. Training seminars and webinars for business were held on "Corporate Social Responsibility and Forms of Cooperation with Vocational-Education Institutions," including: a seminar, "Strategies for Beneficial Partnership with Vocational Schools: Models for Measuring and Assessing CSR Effectiveness" (September 2025, Lviv), attended by 28 business representatives; and a seminar, "Welcoming Veterans: A Culture of Return and Tools That Work," attended by 57 representatives of sectoral businesses, sectoral associations, territorial communities, vocational-education institutions, and municipal enterprises. |  |  |  |  |
| 20. Promoting the development of a network of vocational (vocational-technical) and professional pre-higher education institutions in line with the needs of regional and inter-regional labour markets | Developing methodological recommendations on shaping the network of vocational (vocational-technical) and professional pre-higher education institutions | 2025 | The order of the Ministry of Education and Science issued | Completed | Ministry of Education and Science The Cabinet of Ministers of Ukraine adopted Order No. 216-r of 4 March 2026, "On the Approval of Methodological Recommendations on Shaping the Network of Vocational and Professional Pre-Higher Education Institutions." |  |  |  |  |
| 21. Implementing effective career-guidance measures in general secondary education institutions, and social advertising to popularize working-class trades, in order to increase the prestige of vocational (vocational-technical) education among various population groups, including women | 1) Developing a Concept for Career Guidance within the Education System and an action plan for its implementation | 2027 | The order of the Ministry of Education and Science issued | Completed | Ministry of Education and Science Order of Ministry of Education and Science No. 1541 of 24 November 2025 was approved, "On the Approval of the Concept for Career Guidance and Career Counselling within the Education System of Ukraine for 2025–2030, and the Action Plan for Implementing the Concept for Career Guidance and Career Counselling within the Education System of Ukraine for 2025–2030." |  |  |  |  |
|  | 2) Promoting the development of a network of career centres in vocational (vocational-technical) and professional pre-higher education institutions | 2027 | career centres established in at least 70 percent of vocational and professional pre-higher education institutions | Not started | The implementation deadline has not yet arrived. |  |  |  |  |
|  | 3) Promoting awareness of the educational and vocational-educational programmes offered by vocational (vocational-technical) and professional pre-higher education institutions | 2027 | Social advertising created to popularize working-class trades. | Not started | The implementation deadline has not yet arrived. |  |  |  |  |
| 22. Ensuring accessibility, reasonable accommodation and universal design to meet the educational needs of children with special educational needs | ttracting funding (including international technical assistance) to renovate the educational space and the teaching, production and social infrastructure of vocational (vocational-technical) and professional pre-higher education institutions, taking into account accessibility, barrier-free design, energy efficiency and safety | 2027 | renovation of educational spaces increased in at least 60 percent of vocational and professional pre-higher education institutions. | Not started | The implementation deadline has not yet arrived. |  |  |  |  |
| 23.Promoting the development of extracurricular (out-of-school) education in line with the free, well-rounded development of personality, the intellectual and creative abilities and physical qualities of pupils, students and trainees, and the principle of gender equality | 1) Developing the movement of "friends of young rescuer-firefighters" in educational institutions | 2027 рік | 400 demonstration teams of young rescuer-firefighters established in educational institutions | Ongoing | State Emergency Service of Ukraine State Emergency Service of Ukraine cooperates with Ministry of Education and Science on developing the movement of young rescuer-firefighters on the basis of educational institutions. In the regions, State Emergency Service of Ukraine units have also established cooperation with education-management bodies and public/youth organizations to implement the project. To date, 3,160 developing the movement of young rescuer-firefighters units have been established, of which 268 are demonstration units. |  |  |  |  |
|  | 2) Engaging children and youth aged 6 to 18 in physical culture and sport at children's and youth sports schools | 2025—2027 | at least 7.5 percent of children and youth engaged in physical culture and sport | Completed | Ministry of Youth and Sports 8.3% of Ukraine's school-age youth aged 6 to 18 are engaged in regular activities at sports schools. |  |  |  | Children leaving the country due to Russian aggression, significant destruction and damage to sports infrastructure, and a shortage of qualified specialists. |
|  | 3) з Engaging school-age children and youth in primary arts education at arts schools, | 2025—2027 | growth of at least 8 percent in the number of children and youth engaged in obtaining primary arts education | Ongoing | Ministry of Culture The share of school-age children and youth engaged in obtaining primary arts education was 7% in 2024. As of 1 September 2025, 7.4% of learners were obtaining primary arts education. |  |  |  | The unstable attendance of school-age children and youth is due to objective factors linked to Russia's ongoing armed aggression against Ukraine, in particular: deterioration of the security situation in certain regions, which prevents or limits in-person attendance at out-of-school arts education institutions; temporary suspension of operations or relocation of arts schools from areas of active hostilities and frontline zones; internal displacement of children and families, resulting in loss of stable access to arts education institutions; the psychological state of children and their parents, and the priority given to safety and social needs during martial law; and limited staffing and material/technical resources of out-of-school education institutions. At the same time, the governing bodies of arts schools are taking measures to properly ensure the educational process (introducing distance and blended learning formats and creating safe conditions for obtaining primary arts education). |
| Area "Social Services and Building an Inclusive Society" |  |  |  |  |  |  |  |  |  |
| 24. Building a system for the provision of social services in line with population needs, through the modernization of existing types of social services and the introduction of new ones that take gender characteristics into account, including ensuring the development of quality and accessible care services, primarily on the basis of the existing network | Continuing the implementation of a pilot project introducing a comprehensive social service for building resilience in territorial communities | 2025 рік | number of territorial communities that joined the pilot project increased by 15 percent | Ongoing (implementation of the pilot project introducing the comprehensive resilience-building social service) | Ministry of Social Policy The number of territorial communities that joined the pilot project increased by 40% (122 new resilience centres were established). State budget financing in 2025 was 44.6% higher than the amount paid for the service in 2024. In 2025, 9 territorial communities formed teams to provide the comprehensive resilience-building social service outside the provider-selection competition, financed from local budgets and other sources not prohibited by law. Over the course of implementing the pilot project, more than 350 premises inspections and more than 560 checks of compliance with legislative requirements in the provision of the comprehensive resilience-building social service were carried out. | Ministry of Social Policy 391 090,0 |  |  |  |
| 25. Creating a barrier-free environment for all population groups in regions and territorial communities | Conducting monitoring and assessment of the degree of barrier-free accessibility in accordance with Resolution of the Cabinet of Ministers of Ukraine No. 537 of 26 May 2021, "On Approving the Procedure for Monitoring and Assessing the Degree of Barrier-Free Accessibility of Physical-Environment Objects and Services for Persons with Disabilities" | 2025—2027 | inspection carried out of at least 60 percent of physical-environment objects and services. | Completed | Ministry for Communities, Territories and Infrastructure Development Annual monitoring and assessment of the degree of barrier-free accessibility of buildings and structures was carried out, during which 76,600 objects were inspected. In 2025, the monitoring covered not only state- and municipally-owned buildings and structures but also private-sector facilities providing services to the public. The assessment found that: 8.5% of objects are barrier-free; 17.0% are partially barrier-free; and 74.5% are not barrier-free. The highest level of barrier-free accessibility was traditionally recorded at healthcare facilities, Administrative Service Centres, pharmacies, and filling stations. |  |  |  |  |
| 26.Implementing state policy at the regional and local level on preventing and combating human trafficking, domestic violence and gender-based violence, including the provision of assistance to persons who have suffered conflict-related sexual violence, and ensuring equal rights and opportunities for women and men | 1) Conducting joint specialized trainings and seminars for professionals working in the field of preventing and combating domestic violence and gender-based violence, as well as for law-enforcement officers and judges | 2025—2027 | at least seven specialized events held annually | Ongoing on a continuous basis. | Ministry of Internal Affairs With the support of international partners, Ministry of Internal Affairs organized and held 17 trainings for 425 National Police prevention-block officers (patrol police and precinct officers) on "Sexual Harassment as a Type of Administrative Offence: Response, Evidence-Gathering and Prevention." During 2025, National Police investigative-unit staff organized, held, or took part in specialized trainings and seminars (11 events) on documenting and investigating criminal offences related to domestic violence and on gender-equality issues, including: 14.01.2025 in Ivano-Frankivsk and 25.02.2025 in Lutsk, with support from the Government of Canada; 20–21.01.2025 in Kyiv, with support from the NGO "Resource Centre for Non-Governmental Organizations"; 27–31.01.2025, 03–07.02.2025, 17–21.03.2025 and 24–28.03.2025 in Târgu Mureș (Romania), within the "Police Support Programme 2024/2025," training course "Working with Vulnerable Victims/Witnesses"; 14–18.04.2025 in Paris (France), within the framework of technical cooperation between the National School of Judges of Ukraine and the French National School for the Judiciary, training session "Domestic Violence and Specialization of Prosecutors, Judges and Investigators in This Category of Cases"; 29–30.10.2025 and 19–20.11.2025 in Kyiv, workshops devoted to specific issues of forensic-medical, forensic-psychological and other types of expert examinations in criminal proceedings concerning gender-based violence, including domestic violence, and conflict-related sexual violence; 03.12.2025 in Kyiv, a conference on "Justice Oriented towards Survivors of Gender-Based Violence," held by the Ukrainian Women Lawyers' Association "JurFem" with support from the Embassy of Finland in Ukraine. In addition, during 2025, with the assistance of international partners — including the Representative Office of the United Nations Population Fund (UNFPA) in Ukraine, UN Women in Ukraine, and the international consulting LLC "Gender Associations" — 37 trainings on preventing and combating domestic violence and sexual harassment were held for 644 officers of preventive-activity police units. Specialized events on preventing and combating human trafficking, domestic violence and gender-based violence are held at: the National Academy of Internal Affairs; Kharkiv National University of Internal Affairs; Odesa State University of Internal Affairs; Lviv State University of Internal Affairs; Dnipro State University of Internal Affairs; and Donetsk State University of Internal Affairs. | Ministry of Internal Affairs Funding: within expenditures provided for in the State Budget of Ukraine under budget programme code 1007020, "Ensuring the Operation of Bodies, Institutions and Establishments of the National Police of Ukraine." |  |  |  |
|  | 2) Developing and implementing a case-management mechanism for situations of domestic violence, gender-based violence, and conflict-related sexual violence linked to the Russian Federation's armed aggression against Ukraine, oriented towards the needs of survivors, | 2025 | an order of the Ministry of Social Policy issued | Ongoing | Ministry of Social Policy The Ministry of Social Policy, together with the UN Population Fund in Ukraine, is developing a draft regulatory act that will provide for a full cycle of casework for every survivor, regardless of which agency they approach. At the same time, this represents a multidisciplinary approach to working with survivors that will enable the digitalization of service-provision processes and the registration of violence cases. |  |  |  |  |
|  | 3) Ensuring the operation of an interactive map of the network of general and specialized support services for persons who have survived domestic violence, gender-based violence, and conflict-related sexual violence linked to the Russian Federation's armed aggression against Ukraine, and conducting monitoring and evaluation of the quality of services and the capacity of specialized services, oriented towards survivors' needs | 2027 | the interactive map created and operational. | Ongoing | Ministry of Social Policy Contact information on the activities of specialized support services for survivors of domestic violence and gender-based violence has been collected and compiled. On this basis, an interactive map will be created; its functionality is currently being tested prior to full deployment: https://nssu.gov.ua/domashnye -nasilstvo/specializovanisluzhbi-pidtrimki |  |  |  |  |
|  | 4) Developing and approving Methodological Recommendations on applying criteria/indicators for identifying survivors of human trafficking | 2025 | an order of the Ministry of Social Policy issued. | Ongoing | Ministry of Social Policy A draft order of the Ministry of Social Policy, "On Approving Methodological Recommendations on Applying Criteria/Indicators for Identifying Survivors of Human Trafficking," has been drafted and is currently being coordinated among the Ministry's structural units. |  |  |  |  |
| 27. Creating conditions at the regional and local level to achieve equal rights and equal opportunities for women and men in all spheres of public life | Developing and approving local gender-equality programmes that take into account the needs of women and men, boys and girls, including those subject to discrimination on the basis of sex and other grounds | 2025—2027 | local gender-equality programmes approved. |  | Vinnytsia Oblast. The Oblast Programme for Family Support, Prevention of Domestic Violence, Ensuring Equal Rights and Opportunities for Women and Men, and Prevention of Human Trafficking for the period until 2026, approved by Decision No. 299 of the 15th session of the 8th convocation of Vinnytsia Oblast Council of 24.12.2021, remains in force. A Strategy for Ensuring Equal Rights and Opportunities for Women and Men in Vinnytsia Oblast for the period until 2030 has been developed (approved by Order of the Head of the Oblast Military Administration No. 01.01-18/1602 of 25.12.2025), together with an operational action plan for its implementation in 2026–2027 (approved by Order of the Head of the Oblast Military Administration No. 01.01-18/1603 of 25.12.2025). Dnipropetrovsk Oblast. Specialized trainings and seminars are held for specialists of territorial communities of Dnipropetrovsk Oblast working in the field of preventing and combating human trafficking, domestic violence and gender-based violence, as well as for law-enforcement officers. During 2025, 18 such events were held, covering more than 460 people. Donetsk Oblast. Within the scope of this measure, 34 local gender-equality programmes and 1 regional programme were kept in force in Donetsk Oblast in 2025. |  |  |  |  |
|  |  |  |  |  | Zhytomyr Oblast By Order of the Oblast Military Administration No. 1212 of 31.10.2025, the Comprehensive Programme for Family Support, Ensuring Equal Rights and Opportunities for Women and Men, Children's Health and Recreation, and Preventing and Combating Domestic Violence and Human Trafficking for 2026 was approved. Zakarpattia Oblast. By Order No. 832 of 20.09.2023 of the Head of the Zakarpattia Oblast State Administration – Oblast Military Administration, the Regional Action Plan for 2023–2025 on implementing the State Targeted Social Programme for Combating Human Trafficking for the period until 2025 was adopted; and by Order No. 737 of the Head of the Oblast State Administration of 15.12.2020 (as amended by Order No. 686 of 31.07.2023), the Regional Programme on Family and Gender Policy, Prevention and Combating of Domestic Violence, and Combating Human Trafficking for 2021–2025, approved by Decision No. 47 of the Oblast Council of 17.12.2020, was put in place. An oblast coordination council on family, gender equality, demographic development, and the prevention of and response to domestic violence and human trafficking has been established and operates in the oblast, comprising all relevant stakeholders. By Order No. 820 of 03.12.2025 of the Head of the Oblast State Administration – Head of the Oblast Military Administration, the Regional Programme on Family and Gender Policy, Prevention and Combating of Domestic Violence, and Combating Human Trafficking for 2026–2030 was approved. Zaporizhzhia Oblast. Ongoing. By Order No. 223 of the Head of the Oblast State Administration of 06.04.2021 (as amended), the Oblast Action Plan for implementing UN Security Council Resolution 1325 "Women, Peace, Security" for the period until 2025 was approved. Work is currently under way in the oblast on drafting a corresponding plan for the next period. In addition, 4 territorial communities of the oblast (the Bilenke, Mykhailo-Lukashove, Petro-Mykhailivka and Shyrokivka rural territorial communities) have developed and approved local action plans for implementing UN Security Council Resolution 1325 "Women, Peace, Security" for the period until 2025. Ivano-Frankivsk Oblast. The Oblast Comprehensive Social Protection Programme of Ivano-Frankivsk Oblast for 2022–2026, approved by Oblast Council Decision No. 276-10/2021 of 12.11.2021, contains a number of measures aimed at upholding equal rights for women and men, including training and professional development for specialists of social-protection institutions and facilities and social service centres, the production and dissemination of informational materials, and broad information campaigns on gender equality. |  | Zhytomyr Oblast 28,0 |  |  |
|  |  |  |  |  | Kyiv Oblast The Oblast Comprehensive Programme for Family and Child Support in Kyiv Oblast until 2027, approved by Kyiv Oblast Council Decision No. 766-22-VIII of 7 December 2023 (as amended), provides for measures to ensure gender equality that take into account the needs of women and men, boys and girls, including those subject to discrimination on the basis of sex and other grounds. |  | Kyiv Oblast 2419,0 |  |  |
|  |  |  |  |  | Kirovohrad Oblast During 2025, the following remained in force: the Regional Targeted Social Programme for Combating Human Trafficking in Kirovohrad Oblast for the period until 2025, approved by Oblast Council Decision No. 390 of 6 October 2023; and the Oblast Social Programme for Preventing and Combating Domestic Violence and Gender-Based Violence for the period until 2025, approved by Order No. 409-r of the Head of the Oblast State Administration of 19 May 2021. |  | Kirovohrad Oblast 23,0 |  |  |
|  |  |  |  |  | Mykolaiv Oblast By Order No. 495-r of the Head of the Mykolaiv Oblast Military Administration of 17.11.2023, the Comprehensive Social Programme for Family Support, Prevention and Combating of Domestic Violence, and Ensuring Equal Rights and Opportunities for Women and Men in Mykolaiv Oblast for the period until 2026 was approved. Odesa Oblast During 2025, the following regional action plans were implemented in the oblast: implementation of the National Action Plan for UN Security Council Resolution 1325 "Women, Peace, Security" for the period until 2025; a regional action plan for holding the nationwide "16 Days Against Violence" campaign in Odesa Oblast in 2025; observance of World Day against Trafficking in Persons in Odesa Oblast; and implementation of measures under the Comprehensive Programme for Preventing and Combating Domestic Violence and Gender-Based Violence, Ensuring Gender Equality, and Combating Human Trafficking for 2024–2026. Corresponding programmes have been adopted in the districts of the oblast. These programmes take gender considerations into account, thereby helping to ensure equal rights and opportunities for men and women in all spheres of life. Poltava Oblast Work has begun on drafting an Oblast Action Plan for implementing the State Strategy for Ensuring Equal Rights and Opportunities for Women and Men for the period until 2030. Rivne Oblast By Order No. 539 of the Head of the Oblast State Administration – Head of the Oblast Military Administration of 09.09.2025, an operational action plan for implementing, in 2025–2027, the State Strategy for Ensuring Equal Rights and Opportunities for Women and Men for the period until 2030 in Rivne Oblast was approved. |  | Mykolaiv Oblast 8 639,34 |  |  |
|  |  |  |  |  | Sumy Oblast The Oblast Comprehensive Social Protection Programme for 2022–2026, approved by Sumy Oblast Council Decision of 22.12.2021, contains Section X, "Realizing Equal Rights and Opportunities for Women and Men." Ternopil Oblast The oblast ensures the implementation of Order No. 439-r of the Cabinet of Ministers of Ukraine of 2 May 2025, "Certain Issues Concerning the Implementation of the State Strategy for Ensuring Equal Rights and Opportunities for Women and Men for the period until 2030," which approved the Operational Action Plan for implementing, in 2025–2027, the State Strategy for Ensuring Equal Rights and Opportunities for Women and Men for the period until 2030. A corresponding oblast programme will be developed within 3 months after the termination or lifting of martial law. Kharkiv Oblast Paragraph 3 of Order No. 439-r of the Cabinet of Ministers of Ukraine of 02.05.2025, "Certain Issues Concerning the Implementation of the State Strategy for Ensuring Equal Rights and Opportunities for Women and Men for the period until 2030," establishes that oblast state (military) administrations must, within three months after the termination or lifting of martial law, incorporate into local programmes tasks on ensuring equal rights and opportunities for women and men, taking into account the measures of the operational plan. In light of the above, the corresponding regional programme will be developed after the termination or lifting of martial law. Kherson Oblast An oblast interagency council on family, gender equality, demographic development, and the prevention of and response to domestic violence and human trafficking operates in Kherson Oblast, approved by Order No. 85 of the Head of the Kherson Oblast State Administration of 13 February 2014 (as amended by Order No. 460 of the Head of the Kherson Oblast Military Administration of 5 September 2025). During 2025, 1 meeting of the interagency council was held. Khmelnytskyi Oblast By Decision No. 50-6/2021 of Khmelnytskyi Oblast Council of 15.09.2021, the Oblast Comprehensive Programme for Family Support and the Prevention and Combating of Domestic Violence for the period until 2025 was approved; its Section II provides for measures to ensure equal rights and opportunities for women and men. Cherkasy Oblast No local gender-equality programmes were approved in the oblast in 2025. Chernivtsi Oblast By Order No. 1493-r of the Oblast State Administration (Oblast Military Administration) of 14.11.2025, the Operational Action Plan for implementing, in 2025–2027, the State Strategy for Ensuring Equal Rights and Opportunities for Women and Men for the period until 2030 in Chernivtsi Oblast was approved. Chernihiv Oblast In 2025, the following were implemented in Chernihiv Oblast: the Oblast Comprehensive Programme for Family Support, Ensuring Gender Equality, and Combating Human Trafficking for the period until 2025; and the Action Plan for implementing UN Security Council Resolution 1325 "Women, Peace, Security" for the period until 2025 in Chernihiv Oblast. |  | Sumy Oblast 10,0 |  |  |
| 28. Promoting the establishment by local self-government bodies, and ensuring the operation in territorial communities, of social-service providers, including those providing residential social services (social hostels/group homes) | Continuing the implementation of a pilot project to organize the provision, to internally displaced elderly persons and persons with disabilities, of institutional care and supported-living social services under the "money follows the person" principle | 2025 | number of territorial communities that joined the pilot project increased by 15 percent | Ongoing | Ministry of Social Policy The number of territorial communities that joined the piloting of the supported-living service increased by 60%. As of March 2026, agreements on the provision of social services under the "money follows the person" project had been concluded with 707 persons, of whom 345 concerned the provision of institutional-care social services and 362 concerned the provision of supported-living social services. In total, providers of social services under the "money follows the person" principle have currently allocated/created 1,056 bed spaces, including 506 for institutional-care services and 550 for supported-living services. National Social Service (Nastsotssluzhba) As of now, 43 social-service providers offering institutional care and supported living have been included on the list of providers participating in the pilot project. Over the course of implementing the "money follows the person" pilot project, the territorial bodies of the National Social Service carried out 32 monitoring exercises to check compliance with legislative requirements during the provision of social services. |  |  |  |  |
| 29. Ensuring the development of physical culture and sport at the level of territorial communities, including inclusive sports infrastructure, based on the existing network and within available financial resources | 1) Monitoring the number of sports-infrastructure facilities that meet accessibility requirements for all population groups, including persons with disabilities, with regard to physical-culture and sport services | 2025—2027 | annual increase of at least 1 percent in the number of sports-infrastructure facilities meeting accessibility requirements for all population groups | Ongoing | Ministry of Youth and Sports To assess the level of accessibility of physical-culture and sport facilities for persons with disabilities, the Ministry of Youth and Sports conducted, in 2025, an analysis of the provision of sports facilities to the population (broken down by region, excluding areas of active hostilities and temporarily occupied territories). According to 2024 reporting data, the level of provision of sports-infrastructure facilities with barrier-free access for all population groups stands at 36%. |  |  |  |  |
|  | 2) Organizing and holding national sporting competitions to popularize them | 2025—2027 роки | at least five competitions held annually | Completed | Ministry of Youth and Sports 1,360 national competitions were held: 741 national competitions in Olympic sports and 619 in non-Olympic sports. 16,256 athletes took part in the Olympic-sport competitions, and 316,548 athletes took part in the non-Olympic-sport competitions. |  |  |  |  |
|  | 3) Conducting national information and outreach events to support the development of the Olympic movement in Ukraine (seminars, conferences, forums, and other national-level organizational and methodological events) | 2025—2027 роки | at least two events held annually | Completed | Ministry of Youth and Sports The National Olympic Committee of Ukraine held: a national sports and interactive event for children and youth, #OlympicLab, dedicated to the International Day of Sport for Development and Peace; a national project for children and youth, "DoLikeOlympians"; a nationwide campaign, "Olympic Corner"; a national educational sport-and-culture event for children, "Faster, Higher, Stronger — Together!"; National Olympic Day; a national ceremony, "Festival of the Olympic Flag"; a national sport and educational project, "Olympians Inspire — Children Determine Their Future!"; a national Olympic lesson; national sport and educational events for children, "Ukraine Unites Hearts" (winter) and "Ukraine Unites Hearts"; National Olympic Week; a National Olympic Committee seminar with stakeholders of the Olympic movement (Stages I–III); national seminars for coaches and referees in 23 Olympic sports; a seminar for sports journalists; a National Athletes' Forum; a National Forum on Gender Equality in Sport; a "Chat with a Champion" as part of the European Week of Sport #BeActive; and other events. Total participants: more than 1.5 million people. |  |  |  |  |
| 30. Creating conditions for engaging persons and children with disabilities, including those who acquired disabilities as a result of the Russian Federation's armed aggression, in physical culture, sport and physical-culture-and-sport rehabilitation | 1) Holding the national "Believe in Yourself" championship for children with disabilities | 2025—2027 | at least 10 sporting competitions held annually | Completed | Ministry of Youth and Sports In accordance with the Unified Calendar Plan of Physical-Culture, Health and Sporting Events and Competitions for 2025, the Ukrainian Centre "Invasport," from March to June 2025, organized and held — in compliance with all safety requirements and rules — the final competitions of the 32nd "Believe in Yourself" Championship for children with disabilities, dedicated to the 34th anniversary of Ukraine's independence, across 22 sports. The competitions were held at sports facilities of the Western Rehabilitation and Sports Centre of the National Committee of Sports for the Disabled of Ukraine (village of Yavoriv, Lviv Oblast), Chernivtsi, Vinnytsia, the village of Svityaz (Volyn Oblast), Khmelnytskyi, and Kovel (Volyn Oblast). 532 children with disabilities took part in the final competitions across 22 of 24 sports (para-swimming for children with musculoskeletal, visual and intellectual/physical impairments, and swimming for children with hearing impairments; orienteering for children with hearing impairments; badminton for children with hearing impairments; beach volleyball for children with hearing impairments; para table tennis for children with musculoskeletal and intellectual/physical impairments; table tennis for children with hearing impairments; chess for children with musculoskeletal impairments; para athletics for children with musculoskeletal, visual and intellectual/physical impairments; athletics for children with hearing impairments; volleyball for children with hearing impairments; football for children with hearing impairments; football for children with the effects of cerebral palsy (musculoskeletal impairments); and freestyle and Greco-Roman wrestling for children with hearing impairments). 924 medals were awarded: 464 gold, 279 silver and 181 bronze. More than 4,000 children with disabilities took part across all stages of the championship. |  |  |  |  |
|  | 2) Holding national sporting events, as well as physical-culture-and-sport rehabilitation events for persons with disabilities, including disabled war veterans | 2025—2027 | at least 35 sporting competitions, 156 training camps, and 35 rehabilitation-and-sports camps held annually | Completed | Ministry of Youth and Sports To popularize sports for persons with disabilities and to select the strongest athletes for Ukraine's national teams, 59 national sporting competitions were organized and held for persons with disabilities of various categories (two of them using externally raised funds). On the basis of the Western Rehabilitation and Sports Centre of the National Committee of Sports for the Disabled of Ukraine (village of Yavoriv, Lviv Oblast), the Ukrainian Centre "Invasport" organized and held 35 rehabilitation-and-sports camps, during which persons with disabilities recorded 18,062 person-visits aimed at restoring health through physical culture, sport and physical-culture-and-sport rehabilitation. To prepare athletes with disabilities for participation in official international sporting competitions, in accordance with the Unified Calendar Plan of Physical-Culture, Health and Sporting Events and Competitions for 2025, 285 training camps were organized and held in Ukraine, of which 169 were preparation for international sporting competitions, 109 were preparation for participation in the XXV Summer Deaflympics 2025, and seven were preparation for participation in the XIV Winter Paralympic Games 2026. |  |  |  |  |
| 31.Creating conditions for the development and successful self-realization of youth, including through the implementation, in regions and territorial communities, of the National Youth Strategy until 2030 | Holding national events for representatives of youth consultative and advisory bodies aimed at making effective decisions for the country's recovery | 2025—2027 | at least three events held | Completed | Ministry of Youth and Sports During 2025, 2 training sessions were held for youth consultative and advisory bodies in two oblasts: Rivne (attended by 40 people: 25 women and 15 men) and Ternopil (attended by 40 people: 18 women and 22 men). In addition, a National Summary Forum for representatives of youth consultative and advisory bodies was held in Ivano-Frankivsk, bringing together 200 people: 93 men and 107 women. As of now, 664 youth councils operate in Ukraine, of which: 624 are at the local level; 29 at the regional level and in the city of Kyiv; and 11 at the national level. The total number of members of youth councils is 10,893, including: 886 internally displaced persons; 92 persons with disabilities; 46 veterans (men and women); and 110 representatives of national minorities (communities). In addition to youth councils, young people take part in shaping state policy through: student and pupil self-government; civil society organizations; public consultations with authorities; participation in working groups at various levels; and e-democracy tools. Engaging youth in decision-making is one of the key principles of youth policy. |  |  |  |  |
| 32.Promoting the development of civic education and raising the level of social integration of youth | 1) Conducting national trainings for representatives working in youth and children's civil society organizations, to strengthen their competencies for working with youth during the war and in the post-war period | 2025—2027 | at least three trainings held. | Completed | Ministry of Youth and Sports The following were held: a national training for representatives working in youth and children's civil society organizations, to strengthen their competencies for working with youth during the war and in the post-war period (23–25.04.2025 in Kyiv), attended by 30 people; a national training for representatives working in youth and children's civil society organizations, to strengthen their competencies for working with youth during the war and in the post-war period (29–31.05.2025 in Ternopil), attended by 30 people; and a national training for representatives working in youth and children's civil society organizations, to strengthen their competencies for working with youth during the war and in the post-war period (10–12.07.2025 in Rivne), attended by 30 people. |  |  |  |  |
|  | 2) Ensuring the training of specialists working with youth, including under the "Youth Worker" programme | 2025 – 2027 | training of at least 280 specialists ensured | Completed | Ministry of Youth and Sports In 2025, within the "Youth Worker" programme, 50 basic-level trainings were held, graduating a total of 964 programme participants; and 14 specialized trainings were held, graduating a total of 275 programme participants, covering the following topics: "Trauma-Informed Youth Work," "Volunteer Engagement and Coordination," "Advocacy for Youth Policy in the Community," and "Barrier-Free Accessibility in the Youth Sector." |  |  |  |  |
| 33. Promoting the engagement of youth in volunteer activity | Ensuring the training of specialists to promote volunteer activity among youth | 2025 | training of at least 60 specialists ensured | Completed | Ministry of Youth and Sports In 2025, two national trainings were held in Kyiv to prepare representatives of organizations that engage volunteers in their activities, aimed at strengthening their capacity under wartime conditions; as a result, 60 specialists were trained. |  |  |  |  |
| 34. Promoting the development of youth centres and ensuring the quality of the services they provide, including on the basis of the existing network and within available financial resources | Conducting national trainings to train representatives of youth centres | 2025 | at least three trainings held | Completed | Ministry of Youth and Sports In 2025, three national training seminars were held to train representatives of youth centres, aimed at strengthening their capacity and the quality of their operations during the war and in the post-war period. The first, held 24–26 November, brought together 17 people (12 women and 5 men); the second, held 27–29 November, brought together 23 people (21 women and 2 men); the third, held 1–3 December, brought together 13 people (10 women and 3 men). As of February 2026, 643 youth centres and spaces operate in Ukraine, comprising: 114 youth centres (15 oblast-level and 99 city-level) and 529 youth spaces. Most of these have almost fully resumed their operations following the active phase of hostilities and continue not only to implement youth policy but also to provide assistance to the civilian population in their communities. At the same time, 107 youth centres and spaces have ceased operations, including 48 in Donetsk Oblast. In cooperation with the National Youth Centre, ongoing monitoring is carried out of destroyed, damaged and occupied youth infrastructure. As of February 2026, 147 youth-infrastructure facilities have been affected, for a total amount exceeding UAH 270.4 million, including facilities located in temporarily occupied territories: 40 facilities fully destroyed (Donetsk Oblast – 34, Luhansk Oblast – 4, Kherson Oblast – 1, Chernihiv Oblast – 1); 28 facilities damaged (Donetsk Oblast – 15, Sumy Oblast – 2, Kharkiv Oblast – 3, Kherson Oblast – 3, Chernihiv Oblast – 2, Dnipropetrovsk Oblast – 2, Poltava Oblast – 1); and 79 facilities under occupation (Donetsk Oblast – 49, Zaporizhzhia Oblast – 6, Luhansk Oblast – 19, Kherson Oblast – 5). |  |  |  |  |
| Area "Cultural Services and the Formation of National Identity" |  |  |  |  |  |  |  |  |  |
| 35. Creating functionally and organizationally new models of cultural institutions (cultural-service centres, creativity centres, creative hubs, etc.) to support the work of artists, theatrical and performance-based cultural institutions, independent theatres, and musical and artistic ensembles/collectives | 1) Updating the Methodological Recommendations on establishing and organizing the operation of cultural-service centres in territorial communities | 2026 | An order of the Ministry of Culture and Strategic Communications | Ongoing | Ministry of Culture An audit has been conducted of regulatory legal acts requiring amendment in order to create conditions for the introduction and uninterrupted operation of multifunctional cultural institutions. The measure is at the implementation stage. |  |  |  |  |
|  | 2) Developing a model regulation on the basic principles governing the operation of cultural-service centres | 2026 | an act of the Cabinet of Ministers of Ukraine adopted | Ongoing | Ministry of Culture By Order of the Ministry of Economy No. 3073 of 12.12.2025, "On Amending the National Classifier DK 003:2010 'Classifier of Occupations,'" Amendment No. 16 to the Classifier of Occupations was introduced. The document provides for a comprehensive update of job titles and classification groupings in the fields of education, culture, healthcare, social services, and military service. In particular, the Classifier revised the wording of occupations for workers in culture and the creative industries. A number of outdated or duplicated entries were removed. At the Ministry of Culture's proposal, the aforementioned Amendment No. 16 provides, among other things, for the introduction of the job title: "Head (Director) of a Cultural Institution (Establishment, Organization) (Cultural-Service Centre, Club-Type Cultural Institution, Cinema, Theatre, Film Studio, or Other Club Hub)." The measure is at the implementation stage. |  |  |  |  |
|  | 3) Developing and submitting to the Cabinet of Ministers of Ukraine a draft resolution on creating conditions for the uninterrupted operation of cultural-service centres and their structural subdivision | 2026 | an act of the Cabinet of Ministers of Ukraine adopted | Not Started | Ministry of Culture An audit has been conducted of regulatory legal acts requiring amendment in order to create conditions for the introduction and uninterrupted operation of multifunctional cultural institutions. The measure is at the implementation stage. |  |  |  |  |
| 36. Modernizing and informatizing libraries, introducing new information and library services based on information and communication technologies, and ensuring the digitalization of cultural-service provision taking into account the needs and cultural rights of all categories of the population | Ensuring the computerization and internet access of libraries and the digitalization of cultural-service provision | 2025—2027 | computerization ensured in at least 70 percent of libraries | Ongoing | Vinnytsia Oblast. In the oblast's library institutions, 62% of libraries are equipped with computers and 53% have internet access. |  |  |  |  |
|  |  |  |  |  | Volyn Oblast In 2025, measures to modernize the library network were implemented, including work on computerizing libraries, ensuring internet access, and introducing digital services for the provision of cultural services. |  | Volyn Oblast 1072,570 |  | Volyn Oblast. Limited funding, insufficient technical equipment of libraries, and the need to upgrade the material and technical base and to raise the digital competence of staff. |
|  |  |  |  |  | Donetsk Oblast As of 31.12.2025, the 82 reporting libraries have a total of 336 personal computers, of which 126 are for users, 67 of which have internet connections. Computerization and internet connectivity have been ensured for 4 school libraries in general secondary education institutions relocated to safer regions of Ukraine. During the reporting period, no computer equipment or internet equipment was purchased for public libraries. Zhytomyr Oblast Computer-equipment coverage stands at 62% of institutions. The total number of computers is 835, of which 403 are designated directly for users. Internet access has been achieved in 55% of cases. Copying/reproduction equipment: 480 units. Multimedia equipment: 220 units, including 109 projectors and screens. Specialized equipment: only 3 computerized assistive-technology complexes for visually impaired persons have been recorded. |  |  |  | Donetsk Oblast. Under conditions of active hostilities in Donetsk Oblast, partial temporary occupation, and the destruction of settlements, most cultural institutions, including libraries, operate remotely or in a blended format outside the region. |
|  |  |  |  |  | Zakarpattia Oblast The oblast's library network numbers 452 libraries as of 01.01.2026. 259 libraries have computers, i.e., 57.3% are equipped with computers; 169 libraries have computers with internet access. To support librarianship and library informatization, computer equipment was purchased for the Municipal Institution "Zakarpattia Oblast Library for Children and Youth" (a multimedia projector and a laptop) and for the "Zakarpattia Oblast Universal Scientific Library named after Fedir Potushniak" (2 laptops), along with a specialized scanner. Zaporizhzhia Oblast 103 library institutions operate in the government-controlled territory of the oblast; 82 of them have computers (79.6%), and 70 have internet access. 19 libraries of the Zaporizhzhia city territorial community have assistive-technology complexes for the visually impaired. During the reporting period, 28 computers were purchased using own-source revenue and other sources not prohibited by law. In addition, a multifunctional youth space, "KO_LAB," with a focus on ESTEAM education (a combination of entrepreneurship, science, technology, engineering, arts and mathematics), has been established at the Zaporizhzhia Oblast Universal Scientific Library. The "E-book" service operates without interruption. "Digital Education Hubs" operate on an ongoing basis in 16 libraries. Ivano-Frankivsk Oblast Computerization has been achieved in 72.0% of libraries. Kyiv Oblast As of 01.01.2026, internet access is available at the oblast children's library and at 290 libraries of the oblast (38% of the total number); 765 internet workstations for users have been created, of which 200 are in rural libraries; Wi-Fi zones have been opened at 287 libraries. | Zakarpattia Oblast UAH 998 ( UAH 100 – computers and UAH 898 - specialized scanner) |  | Zaporizhzhia Oblast — UAH 512.562 |  |
|  |  |  |  |  | Kirovohrad Oblast As of 1 January 2026, 242 libraries have internet access (46%), of which 172 are rural (38%). In total, 280 libraries in the oblast are computerized (53%), of which 207 are rural institutions (46%). 5 libraries were connected to the internet in 2025. In 2025, library institutions received computer equipment: 1) the Oleksandriia City Centralized Library System received 7 laptops under the "Razom_Hub" project, part of the "eMistechko" programme — "a place for everyone in Ukraine" — an interactive kit (interactive whiteboard and projector), a multifunctional device (MFD), a digital camera, and an audio system; 2) the Yasynuvatka rural library of Pantaivka Settlement Council received a laptop under the "Information Space for Women" project; 3) the libraries of the Kropyvnytskyi Centralized Library System received colour printers and MFDs; the Central City Children's Library and Branch Library No. 10 of the same system received TVs, MFDs and laminators under UNICEF's "Bridge" project; 4) the Municipal Institution "Hryhorivka Central Public Library" and the Podorozhne rural library of Velyka Andrusivka Village Council received 2 laptops, and a colour printer and 2 laminators were purchased for the community's libraries; 5) 4 branches of the Municipal Institution "Public Library" of Ketrysanivka Village Council each received one laptop; 6) the Municipal Institution "Central Public Library" of Onufriivka Settlement Council received a computer and a printer; 7) the Municipal Institution "Haivoron City Public Library" received system units (desktop towers). Luhansk Oblast At present, 10 libraries in Luhansk Oblast operate with computer equipment and internet access. The Luhansk Oblast Universal Scientific Library has implemented an Automated Library Information System (ABIS), modernizing its workflows and enabling it to provide modern information services. Lviv Oblast The introduction of information and communication technologies into library operations has been ensured. Libraries have been computerized and connected to the internet, and user access to digital cultural services has been expanded. The oblast's 1,114 libraries have 1,563 computers, 600 units of copying/reproduction equipment, 479 units of multimedia equipment, and 4 assistive-technology complexes for the visually impaired. Library collections have been replenished. Mykolaiv Oblast 332 of 446 libraries (74.5%) have computer equipment; 285 (63.9%) have computers with internet access. Odesa Oblast Computer equipment has been purchased, and two Digital Education Hubs have been set up in oblast-subordinated public libraries. Poltava Oblast 55.6% of the territorial communities' public libraries have computers. 50.1% of the territorial communities' public libraries have internet access. Rivne Oblast 308 public libraries have been computerized (57.1%), equipped with 1,009 units of equipment; 260 libraries have internet access (858 computers) and offer Wi-Fi zones accessible to the public. Libraries operate as digital-education hubs. Readers have access to electronic catalogues and card indexes, virtual exhibitions, virtual bibliographic reference services, and information posted on websites and social media pages. 22 libraries have their own websites, and 21 maintain electronic catalogues. Sumy Oblast Computerization has been achieved in 275 of 495 libraries, or 56%. Ternopil Oblast To meet the oblast population's information needs, the oblast's libraries have set up: 749 automated workstations with internet access, and 102 libraries have become Digital Education Hubs using the national "Diia. Digital Education" platform. On the pages of the "Ternopilshchyna" regional information portal, a local-history "Book of Remembrance of Heroes of the Modern Russian-Ukrainian War" is maintained, containing more than 2,000 bibliographic entries. At the Ternopil Oblast Children's Library, 27 workstations for staff and 10 workstations for users have been computerized. For digital development and transformation, public libraries of the oblast have introduced the Diia QR/Sharing/API validation/Diia service. Libraries of educational institutions have been equipped with computers featuring specialized assistive devices (magnifiers, adaptive mice) and internet access to provide convenient information access for children with special educational needs. Since 1 January 2025, the Ternopil Oblast Children's Library has switched to electronic user service using the UFD/Library software. Its collection has an electronic catalogue containing 34,920 publications. At the Ternopil Oblast Universal Scientific Library, work has been carried out to populate the database "Consolidated Catalogue of Public Libraries of Ternopil Oblast," into which 6,908 bibliographic records have been entered. In 2025, the "Electronic Library of Local History Publications of Ternopil Oblast" (https://library.te.ua/elektronna-biblioteka/) was expanded by 13 publications, bringing its total to 953 electronic publications. The full-text electronic database "Periodicals of Ternopil Oblast" (https://library.te.ua/periodyka-te-obl/) provides free, prompt access for users to an integrated information resource; 3,880 issues of the oblast's regional newspapers are currently freely accessible. The resource is hosted on the website of the Ternopil Oblast Universal Scientific Library, freely accessible as part of the full-text database "Electronic Library of Local History Publications of Ternopil Oblast," with users able to partially copy and print materials from the resource. In the oblast's general education schools, text-to-speech reading programmes and electronic catalogues are being introduced that children with various impairments can use independently. Special books (Braille, audio) have been entered into a unified nationwide database to make them easy to find and order to match a specific child's needs. |  | Kirovohrad Oblast 92,9 Luhansk Oblast 10,0 Lviv Oblast 12814,6 Mykolaiv Oblast 150,0 Odesa Oblast 225,0 Rivne Oblast 2691,5 | Kirovohrad Oblast 512,4 Mykolaiv Oblast 250,0 | Poltava Oblast Insufficient library funding; quality of internet coverage; power-supply interruptions. Mechanisms for addressing these issues: adopting relevant financial and technological solutions and digitalizing cultural-service provision. Sumy Oblast 163 of 495 libraries are located in areas of active or potential hostilities. |
|  |  |  |  |  | Kharkiv Oblast There are 719 libraries in total in Kharkiv Oblast, of which 587 are operating. 380 libraries have computers, of which 277 are connected to the internet. The total number of computers across the oblast is 1,221, of which 931 have internet access. Kherson Oblast Russian military aggression has caused massive damage to library infrastructure and the material and technical base of libraries. Before the start of Russia's full-scale invasion, 432 library institutions operated in the oblast. According to monitoring data on damage/destruction caused by Russian military aggression, 107 library institutions (including branches) have been affected. For 2025, statistical reports on the activities of 84 libraries (18 libraries and 66 separate structural subdivisions/branches) were submitted. Functioning libraries in the oblast have 504 computers, 199 of which are connected to the internet. Two libraries are under oblast subordination. The buildings of the Municipal Institution "Kherson Oblast Universal Scientific Library named after Oles Honchar" and the Municipal Institution "Kherson Oblast Children's Library named after Dniprova Chaika" have sustained significant destruction as a result of Russian military aggression. The premises where the oblast libraries currently operate are equipped with internet access. Khmelnytskyi Oblast The oblast's public library network comprises 708 institutions, of which: 510 libraries are computerized, 415 libraries have internet access, 345 libraries have Wi-Fi, and 3 oblast libraries are connected to fibre-optic networks. As of 01.01.2026, the overall computerization rate was 72%. The oblast also has 253 registered digital-education hubs based at public libraries. Cherkasy Oblast As of 01.01.2026, the oblast's libraries were equipped with 1,049 units of computer equipment, of which 880 have internet access. The availability of modern computer equipment enables libraries to provide users with a wide range of electronic and information services and ensures access to digital resources, electronic catalogues, online education, and information and communication platforms. In addition, as of 01.01.2026, 56 internet centres and 84 digital-education hubs were operating in the oblast's library institutions, aimed at ensuring free user access to the internet and raising the population's digital literacy. Chernivtsi Oblast As of 01.01.2026, 169 libraries are equipped with computer equipment, comprising 47% of the total number of public libraries in the oblast. As part of support for the oblast's best libraries, the annual oblast "Library of the Year" competition was held. Winning institutions received new computer equipment worth a total of UAH 90,000, an important contribution to modernizing their information space and improving user-service quality. Chernihiv Oblast As of 01.01.2026, 197 libraries in Chernihiv Oblast are equipped with computer equipment (651 computers) — 35.2% — of which 171 libraries (543 computers) have internet access. |  | Kherson Oblast 14,4 Chernivtsi Oblast 90,0 | Kherson Oblast 202,1 | Kherson Oblast. Library infrastructure and material/technical base damaged by Russian military aggression, as a result of which many libraries are not operating. Chernivtsi Oblast. Insufficient local-budget funding for library-network modernization under martial law is slowing progress toward the target of computerizing at least 70 percent of libraries; a phased approach to equipping institutions is therefore being implemented. Chernihiv Oblast. Insufficient funding, an outdated technical base, and low levels of digital skills are delaying library modernization; this can be addressed through investment in information and communication technologies, training for users and staff, and the development of accessible digital services. |
|  |  |  |  |  | Ministry of Culture (MCSC) Libraries under the management of the Ministry of Culture were equipped with computers in 2025 as follows: the Yaroslav Mudryi National Library of Ukraine — 373 computers, of which 342 are connected to the internet. On 22.12.2025, the database "The War for Ukraine's Independence" was presented — an electronic resource containing records of books, materials from scientific-practical conferences, articles from scholarly collections, photo albums, works of art, and other materials devoted to the Russian-Ukrainian war, published (created) starting from 2014 (link: https://surl.li/aosrnh). The National Library of Ukraine for Children — 124 computers (all connected to the internet). On 01.04.2025, training was held as part of the National Online School for Territorial Community Library Staff, "Libraries. Children. Communities," for 534 specialists from Ivano-Frankivsk and Cherkasy oblasts on digitalizing library services, introducing ICT, developing electronic resources, media literacy, and inclusive services for children. On 25.11.2025, a session of the National Online School "Libraries. Children. Communities" was held for 469 library specialists from Volyn and Chernihiv oblasts, devoted to library modernization, the development of digital services, online communication with users, and improving the quality of library services for children in communities. The National Historical Library of Ukraine — 67 computers, of which 66 are connected to the internet. Remote registration with the Library, with issuance of an electronic library-card number, has been enabled. Readers can immediately place electronic orders for needed publications through the Library's Electronic Catalogue. Free Wi-Fi access is provided. In April 2025, the Library received 5 computers (monitor and system unit) from the charitable foundation "Humanitarian Hub 'Zhytomyr,'" 4 of which have been installed in the Electronic Reading Room for users. The Odesa National Scientific Library — 139 computers, all 139 connected to the internet. On 29.09.2025, an electronic periodicals reading room was opened at the Library. Resources include the digital collection "Treasures of Ukraine" — a full-text local-history database of publications from Odesa and Ukrainian media — and Libraria, a digital history of Ukrainian periodicals (up to 1950). The project was made possible thanks to institutional partnership support from the First Ukrainian International Bank (PUMB) and the "Khvylya'91 UA" charitable foundation, which provided the necessary computer equipment. Necessary renovation work was carried out, including laying communication infrastructure and providing high-speed internet connectivity, and new furniture was made in-house by the administrative/economic support unit. The Korolenko Kharkiv State Scientific Library — 159 computers, all 159 connected to the internet. Computer equipment was partially updated in the library's departments: 4 new personal computers, 3 scanners, and 2 multifunctional devices were connected. Computer and scanning equipment was connected for document digitization in the Department of Comprehensive Document Reprography and Insurance-Fund Formation. A barcoding process for city-lending publications has been introduced, along with entry of information into the electronic catalogue, to develop e-lending. On the Library's official website, users can place online orders for electronic copies of articles or book excerpts from the collections of the Library of Congress (USA), as well as access international open-access electronic resources, including the DOAJ database. As a result, all libraries under the management of the Ministry of Culture are equipped with computers connected to the internet, representing 100% computerization of these libraries. |  |  |  |  |
| 37. Forming an optimal and inclusive network of cultural institutions and public libraries that will meet the needs of various population groups | Developing and submitting to the Cabinet of Ministers of Ukraine a draft resolution "On Amending Resolution of the Cabinet of Ministers of Ukraine No. 72 of 6 February 2019," | 2025 | The resolution of the Cabinet of Ministers of Ukraine adopted | Completed | Ministry of Culture Resolution of the Cabinet of Ministers of Ukraine No. 632 of 30 May 2025, "On Amending Resolution of the Cabinet of Ministers of Ukraine No. 72 of 6 February 2019," was adopted. This resolution amends the State Social Standards for Providing the Population with Public Libraries in Ukraine, approved by Resolution No. 72 of the Cabinet of Ministers of Ukraine of 6 February 2019. In preparing the draft act, the main effort was directed at taking into account the requirements of current legislation and the capacity of territorial communities, as well as ensuring citizens' right to library services under the legal regime of martial law. |  |  |  |  |
|  | 2) Implementing a pilot project to introduce a Register of the Basic Network of Cultural Institutions in Vinnytsia and Kyiv oblasts | 2026 | the Register of the Basic Network of Cultural Institutions in Vinnytsia and Kyiv oblasts put into operation | Ongoing | Ministry of Culture By Order of MCSC No. 220 of 07.03.2025, "On Implementing a Pilot Project to Introduce a Register of the Basic Network of Cultural Institutions," a calendar action plan was approved for implementing the pilot project to introduce the Register of the Basic Network of Cultural Institutions (hereinafter — BMZK) in Vinnytsia and Kyiv oblasts; Register users have been identified and trained, and data entry and verification by users from the Vinnytsia and Kyiv Oblast Military Administrations is under way. By Order of MCSC No. 549 of 07.07.2025, the BMZK Register was put into pilot (trial) operation. To verify the registration data of cultural institutions, an agreement on electronic information exchange between the Unified State Register and the BMZK was signed between MCSC and the Ministry of Justice, dated 30.01.2025, No. 7/35/01-25/9/16/43-25. State Agency for Arts and Art Education (Derzhmystetstv). Pursuant to Resolution of the Cabinet of Ministers of Ukraine No. 1001 of 30 August 2024, "On the Procedure for Implementing the Pilot Project to Introduce a Register of the Basic Network of Cultural Institutions in Vinnytsia and Kyiv Oblasts," preparatory measures for implementing the pilot project were carried out during 2025, including developing a step-by-step implementation plan and training users. As part of this work, Derzhmystetstv organized and held 35 training seminars for representatives of local councils and their executive bodies, military administrations of settlements in Vinnytsia and Kyiv oblasts, and heads of cultural institutions and cultural-education institutions under their management, to ensure effective work with the Register. Pursuant to the calendar action plan for implementing the pilot project, approved by order of the Ministry of Culture, and in connection with the Register's launch, Derzhmystetstv, by orders No. 20 of 25.03.2025 and No. 27 of 30.04.2025, designated specialists responsible for administration, coordination, and organizational/methodological support to address urgent issues related to optimizing the Register's operation within the software platform environment, and to the rollout and support of the pilot project's implementation. In June 2025, the Register was put into pilot (trial) operation, after which data entry began regarding Register users and cultural institutions in Kyiv and Vinnytsia oblasts. Derzhmystetstv maintains ongoing communication with Register users, providing methodological consultations and clarifications on urgent issues. As of December 2025, more than 140 public registrars had been registered in the Register, and information had been entered on more than 400 cultural institutions. In addition, the Ministry of Culture of Ukraine, together with Derzhmystetstv, has created a public page for a unified digital platform consolidating information on Ukraine's cultural institutions (https://culture-info.mcsc.gov.ua). |  |  |  |  |
|  | 3) Developing and submitting to the Cabinet of Ministers of Ukraine a draft resolution "On Amending Resolution of the Cabinet of Ministers of Ukraine No. 1775 of 12 November 1998," | 2025 | a resolution of the Cabinet of Ministers of Ukraine adopted. |  | Ministry of Culture By letter dated 01.12.2025 No. 03/120/1269-25, pursuant to a decision of the Governmental Committee on Culture, Arts, State Language and Information Policy, Scientific/Technical and Innovation Activity, and the Development of Education, Science, Youth and Sport, dated 28 November 2025, the Ministry of Culture submitted for consideration by the Cabinet of Ministers of Ukraine a revised draft resolution of the Cabinet of Ministers of Ukraine, "On Approving the State Social Standards for Providing the Population with Club-Type Institutions in Ukraine," paragraph 3 of which provides for declaring null and void Resolution of the Cabinet of Ministers of Ukraine No. 1775 of 12 November 1998, "On Standards for Providing the Population with Club-Type Institutions." |  |  |  | The draft was returned to the Ministry of Culture as the lead drafter, taking into account the provisions of paragraph 4 of Section 16 of the Rules of Procedure of the Cabinet of Ministers of Ukraine, in accordance with an extract from Minutes No. 22 of the Cabinet of Ministers meeting of 05.02.2026. Submission is to be ensured during 2026. |
| 38. Implementing, at the regional and local level, state policy on affirming Ukrainian national and civic identity, and creating conditions for national-patriotic and military-patriotic upbringing and civic education of the population at the level of regions and territorial communities — including by engaging war veterans in developing and implementing relevant programmes — and establishing coordination councils on affirming Ukrainian national and civic identity | 1) утворення координаційних рад з питань утвердження української національної та громадянської ідентичності | 2025 рік | утворено координаційні ради при не менш як 60 відсотків місцевих органів виконавчої влади | здійнюється | Vinnytsia Oblast. The operation of the Coordination Council on Affirming Ukrainian National and Civic Identity under the Oblast State Administration has been ensured. Dnipropetrovsk Oblast. Dnipropetrovsk Oblast has 47 coordination councils on affirming Ukrainian national and civic identity in territorial communities, covering 54.6% of the oblast's territorial communities. A Coordination Council on Affirming Ukrainian National and Civic Identity also operates under the Dnipropetrovsk Oblast State Administration. Donetsk Oblast. During the year, the following operated: the Coordination Council on Affirming Ukrainian National and Civic Identity under the Oblast State Administration; 5 coordination councils under district state administrations; and 35 under military administrations of settlements in Donetsk Oblast. Zhytomyr Oblast. 49 corresponding coordination councils have been established in the oblast, of which: 1 under the Oblast State (Military) Administration, 4 under district military administrations, and 44 under city, settlement and village councils (66% of local self-government bodies now have coordination councils). Zaporizhzhia Oblast. During 2025, work continued on establishing Coordination Councils on Affirming Ukrainian National and Civic Identity (hereinafter — the Coordination Council) under local executive authorities. As of now, the region has established and operates an oblast Coordination Council (Order of the Head of the Oblast State Administration, Head of the Oblast Military Administration, No. 151 of 21.03.2024) and 10 Coordination Councils in territorial communities. Ivano-Frankivsk Oblast. Coordination Councils on Affirming Ukrainian National and Civic Identity have been established under the Kolomyia District State (Military) Administration and Kalush City Council. Kyiv Oblast. In 2025, an expanded field session of the Coordination Council on Affirming Ukrainian National and Civic Identity under the Kyiv Oblast Military Administration was held in Bucha, attended by the heads of the corresponding coordination councils of all 69 territorial communities of Kyiv Oblast. Kirovohrad Oblast. During 2023–2025, a coordination council on affirming Ukrainian national and civic identity operated in the oblast. A draft oblast targeted social programme on affirming Ukrainian national and civic identity for 2026–2028 has now been prepared and submitted to Kirovohrad Oblast Council for approval. Once the programme is approved, the following are planned: updating the composition of the oblast-level coordination council and those in the oblast's territorial communities; and developing local programmes in the oblast's territorial communities. Luhansk Oblast. A Coordination Council on Affirming Ukrainian National and Civic Identity has been established under the Oblast State Administration (Order of the Head of the Oblast State Administration – Head of the Oblast Military Administration, No. 165 of 11.08.2023), along with 28 corresponding consultative and advisory bodies under military administrations of the oblast. Lviv Oblast A Coordination Council on Affirming Ukrainian National and Civic Identity is operating. Mykolaiv Oblast Pursuant to Order No. 116-r of the Head of the Oblast Military Administration of 02.04.2024, a coordination council on affirming Ukrainian national and civic identity has been established under the Mykolaiv Oblast Military Administration. Poltava Oblast By Order No. 473 of the Head of the Oblast Military Administration of 10.07.2023, the Coordination Council was established and its official composition approved. Coordination Councils have been established in 15 communities of the oblast and in 1 district state administration (25%). Rivne Oblast The Oblast Targeted Social Programme on Affirming Ukrainian National and Civic Identity for the period until 2028 is being implemented in the region (Order of the Head of the Oblast State Administration – Head of the Oblast Military Administration, No. 692 of 10.12.2024). Under the programme, 48 events were held during 2025, reaching 66,700 people. An Oblast Coordination Council on Affirming Ukrainian National and Civic Identity has been established and operates in the oblast (Order of the Head of the Oblast State Administration – Head of the Oblast Military Administration, No. 270 of 29.05.2024). During 2025, 4 sessions of the Council were held. In addition, corresponding coordination councils have been established and operate in 16 territorial communities of the oblast (25%). Sumy Oblast By Order No. 164-OD of the Head of the Sumy Oblast State Administration – Head of the Oblast Military Administration, of 09.04.2024, a coordination council on affirming Ukrainian national and civic identity was established under the Sumy Oblast State Administration, and Regulations on its operation were approved. In 2025, 4 sessions of the Coordination Council were held. 34 coordination councils have been established in territorial communities of the oblast, representing 67% of the total number of communities. Ternopil Oblast By Order No. 159/01.02-01 of the Head of the Oblast Military Administration of 22 March 2024, a coordination council on affirming Ukrainian national and civic identity was established under the Oblast Military Administration, and its composition was approved. Kharkiv Oblast In territorial communities of Kharkiv Oblast (Berestyn city, Bohodukhiv city, Zlatopil city, and Starovirivka rural communities), coordination councils on affirming Ukrainian national and civic identity have been established by decisions of the respective self-government bodies. Kherson Oblast At the oblast level, by Order No. 232 of the Head of the Kherson Oblast State Administration of 17 May 2023, a coordination council on affirming Ukrainian national and civic identity was established under the Kherson Oblast State Administration. The composition of the coordination council was updated in 2025. Coordination councils on affirming Ukrainian national and civic identity have also been established, pursuant to Resolution of the Cabinet of Ministers of Ukraine No. 364 of 18 April 2023, in all district state (military) administrations and in 44 of the 49 territorial communities of Kherson Oblast. It should be noted that, despite the difficult security situation in the oblast — including the temporary occupation of its left-bank part (Henichesk, Kakhovka (except two settlements), and Skadovsk districts) and constant enemy shelling of the right-bank part — the military administrations of settlements ensure the implementation of state policy on affirming Ukrainian national and civic identity. Work in this area is carried out through organizing distance-learning educational formats, upbringing and cultural/educational activities, and engaging youth in creative initiatives and public events with a patriotic focus. The relevant structural units of the Oblast Military Administration carry out systematic work on the patriotic upbringing of youth and the promotion of Ukrainian history, statehood, and national values. Khmelnytskyi Oblast By Order of the Oblast Military Administration No. 187/2024-r of 12.03.2024, a Coordination Council on Affirming Ukrainian National and Civic Identity was established under the Oblast State Administration (Oblast Military Administration). Cherkasy Oblast To ensure inter-agency cooperation in implementing state policy on affirming Ukrainian national and civic identity, a coordination council on affirming Ukrainian national and civic identity operates in Cherkasy Oblast (Order of the Cherkasy Oblast Military Administration No. 234 of 28.05.2024). One session was held in 2025. Corresponding councils have also been established and operate in 33 territorial communities of the oblast. Chernivtsi Oblast 42 coordination councils on affirming Ukrainian national and civic identity have been established in the oblast, including: under the Chernivtsi Oblast State Administration (Oblast Military Administration) (Order No. 823-r of 05.09.2023); under all 3 district state administrations (district military administrations); and under 38 village, settlement and city councils. |  | Rivne Oblast 612,4 |  |  |
|  |  |  |  |  | Chernihiv Oblast Coordination councils on affirming Ukrainian national and civic identity have been established under the Chernihiv Oblast State Administration, under 5 district state administrations (100%), and under 27 local self-government bodies (47.4%). |  |  |  | Chernihiv Oblast The establishment of coordination councils is hindered in communities located in immediate proximity to the border, owing to the security situation and limited organizational capacity. In addition, small territorial communities face insufficient staffing capacity to form a full membership for such consultative and advisory bodies. |
|  | 2) Approval of regional and local programmes for affirming Ukrainian national and civic identity | 2027 | at least 25 regional/local programmes approved | Ongoing | Ministry of Youth and Sports The oblast state administrations (military administrations) and the Kyiv City State Administration are continuing the process of developing and approving regional programmes for affirming Ukrainian national and civic identity. During the reporting period, such programmes were approved by the corresponding orders of the heads of the Zhytomyr, Rivne, Ternopil, Kherson, Khmelnytskyi, Chernivtsi, Vinnytsia, Volyn, Kyiv, Luhansk, Mykolaiv, Dnipropetrovsk, Chernihiv, Sumy, Donetsk, and Zaporizhzhia oblast state administrations (military administrations). Draft orders on the approval of corresponding programmes have been prepared by the heads of the Kirovohrad and Cherkasy oblast state administrations (military administrations). |  |  |  |  |
|  | 3) Organisation of military-patriotic education events involving veterans | 2025–2027 | at least 10 events to be held annually | Ongoing on a continuous basis | Ministry of Defence of Ukraine Within its area of competence, the Ministry took part in annual events marking anniversaries, memorial and historic dates, and international days related to honouring war veterans, persons with special merit to the homeland, participants of the Revolution of Dignity, defenders of Ukraine's independence, sovereignty and territorial integrity, and events related to the formation of national unity and statehood and the proclamation of Ukraine's independence. In total, 75 events were held during 2025, 42 of them with the participation of senior state leadership, during which 393 state awards were presented to service members and 90 to families of fallen service members; 21 Battle Flags, 10 honorary titles, and 18 honorary distinctions of the President of Ukraine were awarded; and 38 housing certificates were issued to service members and their family members. Ministry of Internal Affairs (MIA) In 2025 the MIA held 20 military-patriotic education events with the participation of war veterans. It took part in and coordinated 12 events at security-oriented and national-patriotic education lyceums of the MIA — meetings with fighters of the 12th Special Purpose Brigade of the National Guard "Azov". From 17–20 August 2025 a series of seminars was organised on "Psychological and pedagogical foundations of educating students at security-oriented and national-patriotic lyceums" for 14 staff members and 7 candidates for positions at MIA lyceums of this type. On 30 August 2025, with 524 representatives of MIA educational institutions taking part, participants joined the eighth "Honouring warriors, running for Ukraine's heroes" run in memory of defenders who died in the Russian-Ukrainian war; officers of the National Police also took part in the same event. On 13 September 2025 participants took part in the MIA Running Cup, which brought together war veterans and MIA staff on the running course. On 20–21 September 2025 workshops on making motanka dolls were organised, led by a collector of traditional folk dress and project manager for the rehabilitation of service members, veterans and their families in Khmelnytskyi region, Tamara Yanina — wife of a fallen "Azov" regiment fighter, Oleksii Yanin — held in Vinnytsia and Ivano-Frankivsk at MIA security-oriented and national-patriotic lyceums. On 29 September 2025, to mark Defenders of Ukraine Day, open training sessions (a sports masterclass) were organised for students of MIA security-oriented and national-patriotic lyceums and cadets of MIA higher education institutions; the event's head coach was Andrii Shevchenko — a war veteran and multiple-time judo and sambo champion of Ukraine, Europe and the world. On 30 September 2025, MIA representatives, lyceum students and cadets of MIA educational institutions — athletes who won international competitions in 2022–2025 — visited the "Recovery" rehabilitation centre in Kyiv, where MIA fighters undergo recovery and rehabilitation. On 3 December 2025, MIA representatives together with cadets of the National Academy of Internal Affairs (NAIA) visited veterans, organised a cultural programme and decorated the space at the "Recovery" rehabilitation centre in Kyiv. In total, under MIA coordination, MIA higher education institutions held over 1,000 national- and military-patriotic events, as well as over 1,500 volunteer events. In turn, MIA higher education institutions have created conditions for national-patriotic, military-patriotic education and civic education of the population. Staff of the Andrii Pryimachenko Ivano-Frankivsk MIA Lyceum co-organised 50 military-patriotic education events involving war veterans. The National Police of Ukraine held 206 patriotic events with the participation of police officers and veterans of internal affairs and police bodies who are combat participants and take part in repelling Russia's armed aggression against Ukraine. In addition, police officers in Zaporizhzhia launched the "Travel Ukraine with SOB" nationwide marathon for children. At the same time, events for the national-patriotic education of youth involving war veterans are held on an ongoing basis in schools and lyceums, including MIA security-oriented and national-patriotic lyceums. The Administration of the State Border Guard Service of Ukraine implemented 5 nationwide events with a total of 350 participants and overall reach of over 60,000 people. These included: the nationwide seminar "Ukrainian Border" (50 participants, reach of 25,000 people, 8 war veterans involved); the nationwide training camp "Dzhura-Prykordonnyk" (200 participants, reach of 25,000 people, 13 war veterans involved); the nationwide patriotic creative competition "Emerald Lyre" (100 participants, reach of 5,000 people, 11 war veterans involved); the 3rd nationwide scientific and educational forum "Border of Courage and Heroism" in Lviv, Lutsk and Rivne (over 300 participants, reach of 10,000 people, 26 veterans involved); and the nationwide patriotic event "Kordon Race" in Lviv (1,450 participants, reach of 3,000 people). With the involvement of war veterans, participation was taken in: the nationwide adaptive competition among veterans "BESTRONG GAMES" (Lviv), which brought together over 120 participants from various regions of Ukraine (6 veterans involved); and stages of the nationwide military-patriotic game "Sokil" ("Dzhura"). Extracurricular education clubs implement an additional training programme within the nationwide children's and youth military-patriotic game "Sokil" ("Dzhura") under the separate track "Dzhura-Prykordonnyk" (advanced level, 2-year programme). With the participation of service members and war veterans, 73 military-patriotic education events at the local and regional level were held. The following events were implemented with the participation of National Guard of Ukraine units: 1) as part of preparing citizens for national resistance, sessions were held at 260 educational institutions ("Lessons of Valour" and special courses); sessions were held at 28 social protection institutions; excursions were organised for representatives of educational institutions and NGOs to the deployment sites of 6 National Guard military units; 15 training camps were held for young people. Total number of participants — 8,470. 2) As part of holding and developing the nationwide children's and youth military-patriotic game "Sokil" ("Dzhura"), 20 training camps/masterclasses were held; 15 events were organised to set up locations at camps, festivals and competitions; instructors (dog handlers, sappers, medics) were involved in 47 demonstration performances, classes and trainings; 18 demonstrations of weapons, equipment and gear were held. Audience reach — approximately 14,300 people. 3) As part of information-awareness and educational events and campaigns, over 680 events were held. Estimated number of direct participants — approximately 51,500 people. Total reach (including media, social media audience, viewers) — approximately 879,500 people. 4) As part of events for affirming Ukrainian national and civic identity involving service members and war veterans, over 90 events were held. Estimated number of direct participants — over 70,000 people. Reach via media, podcasts, exhibitions and festivals — over 200,000 people. During 2025, State Emergency Service (SES) units held 34 life-safety and patriotic education events for children and young people in general education institutions, with the participation of rescuer-veterans. State Border Guard Service of Ukraine [As above — 5 nationwide events, 350 participants, over 60,000 reach, with the same events listed: "Ukrainian Border" seminar, "Dzhura-Prykordonnyk" training camp, "Emerald Lyre" competition, "Border of Courage and Heroism" forum, "Kordon Race", BESTRONG GAMES, "Sokil"/"Dzhura" game stages, and 73 local/regional military-patriotic education events.] Ministry of Culture Libraries within the Ministry of Culture's purview held the following military-patriotic education events involving war veterans: On 20 March 2025, the Yaroslav the Wise National Library hosted a literary and artistic evening, "Poetry in Pixels", as part of National Poetry Reading Week. Through the lens of musical interpretation of poetic works and their own verses, specially invited guests shared their work: Honoured Artist of Ukraine and Armed Forces officer Dmytro Linartovych, and composer and Russian-Ukrainian war veteran Ihor Dvyhalo. On 11 November 2025, the presentation took place of the English-language edition of the chronicle book "In a Ring of Fire: The Defence of Luhansk Airport" (Folio, 2025). The English edition was presented by a group of authors: Yurii Rudenko, a reserve officer and veteran who took part in the defence of Luhansk Airport, and volunteers Serhii and Anastasiia Hlotov, together with Oleksandra Liashenko, coordinator of the English-language edition. Invited guests included Andrii Zelenskyi, a service member and participant in the defence of Luhansk Airport, and Colonel Vadym Sukharevskyi, former commander of the Unmanned Systems Forces of the Armed Forces of Ukraine and currently deputy commander of the "Skhid" (East) operational command, who also took part in the airport's defence and joined the presentation online. In 2025 the National Library of Ukraine for Children launched the artistic-patriotic project "Vyshyvanka for a Hero", in which young readers create unique embroidered protective shirts by hand for prominent defenders of Ukraine. Children chose the Head of the Security Service of Ukraine, Lieutenant General Vasyl Maliuk, as the project's first hero. Within another project, "Camouflage: Stories of the Unconquered", meetings were held with actor and service member Oleksandr Pecherytsia and SBU Major General Yuliia Laputina. On 20 June 2025, the National Historical Library of Ukraine hosted the presentation of the publications "Chronicle of the War in the Azov and Black Sea Operational Zones, 2024" and "Hunting the Cruiser Moskva", dedicated to important events of the Russian-Ukrainian war at sea. The event was attended by Volodymyr Savchenko, a Captain 1st Rank and head of the NGO "Association of Veterans of the Ukrainian Navy". The Odesa National Scientific Library, as part of the nationwide campaign "Library of the Ukrainian Soldier", handed over new domestically published books to service members, represented by Captain 1st Rank of the Ukrainian Navy Oleksandr Pavlovskyi. A creative meeting was held with writer and Russian-Ukrainian war veteran, literary prize laureate Vitalii Zapeka, along with the presentation of his novel "Tomorrow Is Again Today" (2025). On 26 September 2025, during the 16th "Forum of Good Deeds: The Power of Civic Action", with the participation of military personnel, volunteers, educators and cultural figures, the patriotic meeting "Heroes: The Faces of War" was held, dedicated to service members and veterans who continue their mission in the civic sector. On 20 October 2025, a creative meeting took place with Ukrainian writer and volunteer Liudmyla Okhrimenko. The event was attended by Tetiana Tepliuk, a medic of the "Azov" regiment and participant in the defence of Mariupol, to whom Liudmyla Okhrimenko dedicated her novel "Godmother". On 19 January 2025, the V.H. Karamzin Kharkiv State Scientific Library held the presentation of the poetry collections "The Oskil Grows Salty with Tears" and "Fiery Barrage" by Oleh Boroday — a teacher, musician, poet and service member. On 23 February 2025 the meeting "Life Between a Gunshot and a Muse" was held with artists and soldier-poets Oleh Boroday and Oleksandr Samus. On 12 March 2025 the presentation of the book "Kharkiv: 20 Conversations About Unbreakable Spirit" was held with co-authors: Serhii Huzchenko, a colonel who led the defence of the city of Kharkiv in February–April 2022, Kostiantyn Nemichev, founder of the "KRAKEN" special unit and an officer of the Defence Intelligence of Ukraine (DIU), and Serhii Zhadan, a poet, civic activist and service member. In total, libraries under the Ministry of Culture's purview held 12 thematic events during the reporting period. On the initiative of the National Academy of Fine Arts and Architecture (NAFAA), the art project "Gallery of Heroes" was launched in 2023, in which the Academy's students paint portraits of Armed Forces service members undergoing treatment and rehabilitation in healthcare institutions, including military hospitals. The project aims to record the chronicle of the Ukrainian people's heroic struggle against Russian aggression by creating artistic images of Ukraine's defenders, as well as to provide moral support to service members through art. An important part of the project is that, once portraiture is complete, service members receive their portraits as a gift, while some of the artworks are transferred to the NAFAA Art Museum collection, forming a contemporary artistic archive of wartime. During 2025, as part of the "Gallery of Heroes" project and related art initiatives involving NAFAA, a number of exhibitions were held, including the "Memory of the Maidan: Portraits of Heroes" exhibition at the Verkhovna Rada of Ukraine, the "Gallery of Heroes – 2025" art project at the National Military Medical Clinical Centre "Main Military Clinical Hospital", and NAFAA student plein-air sessions. In addition, in 2025 personal exhibitions of artist-defenders of Ukraine were held at NAFAA. |  |  |  |  |
|  | 4) Holding seminars and training, retraining and professional-development courses for war veterans to work in the field of affirming Ukrainian national and civic identity | 2025-2027 | at least 40 events held | Ongoing | Ministry of Defence In accordance with Section V of the Catalogue of Professional Development (Additional Training/Retraining) Courses at higher military educational institutions, military training units of higher education institutions, and pre-higher vocational military education institutions, approved by the Deputy Minister of Defence of Ukraine on 17 February 2024, 11 professional-development courses for the corresponding categories of service members and employees were envisaged during the reporting period. During 2025, professional development was provided to a total of 172 trainees, of whom 105 were war veterans. Ministry of Veterans Affairs of Ukraine 8 training courses were held for instructors in the basic training of Ukrainian citizens for national resistance. | Ministry of Veterans Affairs of Ukraine 1246,1 |  |  |  |
| 39. Strengthening the status of the Ukrainian language, and promoting its development and popularisation | 1) Facilitating the creation of a competitive national product | 2025—2027 | grant support provided to at least 87 projects | Completed | Ministry of Culture The Ukrainian Cultural Foundation (the Foundation) has ensured active support for the creation of a competitive national cultural product. As of the end of 2025, following a competitive selection process, the Foundation supported 229 grant projects (including 4 agreements pending termination) for a total amount of UAH 193,572.2 thousand under the programmes "Culture During the War", "Societal Resilience Through Culture", "Cultural Heritage", and "Culture. Regions". | 193572,20 |  |  |  |
|  | 2) Providing state support for the purchase of Ukrainian-language books | 2025—2027 | state assistance for book purchases provided to at least 660,501 people | Ongoing | Ministry of Culture According to the Ukrainian Book Institute, as of 2 January 2026, state assistance for book purchases had been provided to 245,740 people. | 223 230 |  |  |  |
|  | 3) Preparing and distributing Ukrainian-language book editions, including electronic | 2025—2027 | at least 214 new literary works by Ukrainian authors supported | Ongoing | Ministry of Culture In 2025 the Ukrainian Book Institute supported 76 projects for publishing new literary works by Ukrainian authors, in a total quantity of 111,500 copies. | 23 353,50 |  |  |  |
| 40. Implementing measures for the protection and preservation of cultural heritage | 1) Developing and approving scientific-design documentation defining the boundaries and use regimes of monument territories, monument protection zones, and historic areas of populated places | 2025—2027 | scientific-design documentation approved |  | Vinnytsia oblast The authorised cultural heritage protection body reviewed and approved: registration documentation for 2 cultural heritage sites; and 14 design/scientific-design documents on works at monuments and their protection zones. Volyn oblast In 2025, work was organised on developing scientific-design documentation defining boundaries and use regimes for territories of cultural heritage monuments, their protection zones, and historic areas of populated places. The work is carried out in cooperation with local self-government bodies and specialised research institutions. Dnipropetrovsk oblast By order No. 75 of the Oblast Administration's Department of Culture, Tourism, Nationalities and Religions dated 3 December 2025, the boundaries and use regimes of the territories and protection zones of locally significant architectural monuments were approved in accordance with the scientific-design documentation for the "Income House of the First Katerynoslav House Society" (protection nos. 102, 103, 104, 105, Starokozatska St.; nos. 72, 74, 74-a, 74-b) and the locally significant historical monument "Building of the former 4th police precinct, where I. V. Babushkin (1873–1906), a professional revolutionary and student of V. I. Lenin, was imprisoned in June–July 1902 and where 8 participants of the Horlivka armed uprising (9–17 December 1905) were executed" (protection No. 1535, Battalion Dnipro Boulevard, 2). Donetsk oblast In Donetsk oblast, 8 cities are included on the List of Historic Populated Places of Ukraine, approved by Cabinet of Ministers Resolution No. 878 of 26 July 2001: Bakhmut, Horlivka, Donetsk, Kramatorsk, Makiivka, Mariupol, Sviatohirsk, and Sloviansk. As of 31 December 2025, historical-architectural framework plans (HAFPs) have been developed and approved for 7 of these — Bakhmut, Makiivka, Horlivka, Sloviansk, Mariupol, Sviatohirsk. An HAFP for Donetsk has not been developed (the city has been occupied since 2014). The scientific-design documentation "Historical-Architectural Framework Plan of the City of Kramatorsk Defining the Boundaries and Use Regimes of the Historic Area and Monument Protection Zones" was submitted by Kramatorsk City Council to the Ministry of Culture on 27 December 2024 and the approval procedure is ongoing. Development of HAFPs has been completed for all cities of Donetsk oblast under Ukrainian government control that are included on the List. Zhytomyr oblast 20 protection agreements for cultural heritage sites were concluded; registration documentation was prepared for 2 cultural heritage sites. Zakarpattia oblast A technical passport was prepared for the nationally significant architectural monument "Rotunda" (protection No. 070051), Uzhhorod, Muzeinyi lane, 2; architectural measurements and a technical-condition survey of the monument were carried out. Ivano-Frankivsk oblast As of 1 January 2026, historical-architectural framework plans have been developed for populated places (with approved cultural-heritage monument protection zones) in: Ivano-Frankivsk, Bolekhiv, Burshtyn, Dolyna, Kolomyia, Nadvirna, Rohatyn, Solotvyn, Voinyliv, and Tlumach. Kyiv oblast This measure is not being implemented. Kirovohrad oblast The Ministry of Culture and Strategic Communications of Ukraine approved the scientific-design documentation "Historical-Architectural Framework Plan of the Town of Novoukrainka, Novoukrainka District, Kirovohrad Oblast, Defining the Boundaries and Use Regimes of Monument Protection Zones and Historic Areas", which has been forwarded to Novoukrainka Town Council for approval, taking into account a technical correction. Luhansk oblast: Implementation has not begun. Lviv oblast: As of 2025, there are 55 historic populated places in Lviv oblast, of which 33 have duly developed and approved scientific-design documentation defining the boundaries and use regimes of locally significant monuments and their protection zones. During 2025, 1 scientific-design document was approved defining the boundaries and use regime of the protection zone of the locally significant architectural monument — the Palace ("Marmurovyi Palace" sanatorium), 1938 (protection No. 951-Lv), at 2 Parkova Square, Morshyn, Stryi district, Lviv oblast. Mykolaiv oblast During 2025, no scientific-design documentation defining boundaries and use regimes of monument territories, protection zones, or historic areas of populated places was approved. Odesa oblast In 2025, 1 scientific-design document defining the boundaries and use regime of monument protection zones was approved. Rivne oblast In the oblast, 8 of 13 populated places have approved historical-architectural framework plans defining the boundaries and use regimes of historic areas (the towns of Dubno, Ostroh, Korets, and the settlements of Mlyniv, Berezne, Stepan, Hoshcha and Klevan). Sumy oblast In 2025, no scientific-design documentation was submitted for approval. 8 technical land-management documents were approved establishing the boundaries of regime-forming cultural heritage sites. Ternopil oblast In 2025, scientific-design (research) documentation was approved defining the boundaries and use regimes of protection zones for locally significant monuments within land plots at 7 S. Kachaly St. and 4 Rodyny Barvinskykh St. in the city of Ternopil, along with the corresponding land-management documentation. Kharkiv oblast 16 populated places of Kharkiv oblast are included on the relevant list. Historical-architectural framework plans (HAFPs) have been developed and approved for Liubotyn, Kharkiv, Iziium, Chuhuiv, and Kupiansk. The HAFP for Krasnokutsk has been submitted for approval to the Ministry of Culture of Ukraine. Development of the HAFP for Balakliia has been completed, with the documentation agreed by the Department of Culture and Tourism of the Kharkiv Oblast Military Administration and to be submitted by the developer to the Ministry of Culture. The HAFP for Merefa is at the stage of revision to address comments. HAFPs are under development for Bohodukhiv, Valky, Krasnohrad, and the settlements of Zolochiv and Sharivka. Work has begun on developing the HAFP for Zmiiv. Development has not begun for Vovchansk (located in an active combat zone) and the settlement of Kehychivka (the question of removing Kehychivka from the List of Historic Populated Places of Ukraine is being worked through). Kherson oblast A historical-architectural framework plan and the boundaries and use regimes of monument protection zones and historic areas have been approved for de-occupied settlements of the oblast (Beryslav, Kherson). At the same time, development and approval of scientific-design documentation defining the boundaries and use regimes of territories of archaeological, historical and monumental-art monuments has not been carried out. Khmelnytskyi oblast In the oblast, 1 relevant scientific-design document has been approved for the settlement of Nova Ushytsia (Order of the Ministry of Culture and Strategic Communications of Ukraine No. 379 of 30 April 2025). A further 5 historical-architectural framework plans (for the settlements of Krasyliv, Letychiv, Antoniny, Yarmolyntsi, and Stara Syniava) are under review at the Ministry of Culture. Cherkasy oblast No relevant scientific-design documentation was approved in Cherkasy oblast during 2025. Chernivtsi oblast During 2025, at meetings of the Advisory Council on Cultural Heritage Protection under the Department of Culture of the Chernivtsi Oblast State Administration (Military Administration), the historical-architectural framework plan for the settlement of Putyla, Vyzhnytsia district, Chernivtsi oblast, was considered, defining the boundaries and use regimes of monument protection zones and historic areas. Chernihiv oblast In 2025, no such documentation was submitted for approval to the Chernihiv Oblast State Administration. Ministry of Culture During the first half of 2025, the draft HAFP for Kovel was agreed (Ministry of Culture and Strategic Communications letter No. 11/13/22-25 of 24 January 2025) and its historic area was approved (Order No. 32 of 21 January 2025); in addition, orders of the Ministry approved the historic areas of the historic populated places of Nova Ushytsia (Order No. 379 of 30 April 2025) and Boguslav (Order No. 312 of 3 April 2025). The Ministry conducts monthly monitoring of the status of commissioning, developing and approving historical-architectural framework plans and the boundaries/use regimes of historic areas of Ukraine's historic populated places, by collecting, systematising, summarising and updating relevant information received from oblast military administrations, pursuant to the protocol decision following the video conference at the Office of the President of Ukraine of 13 March 2023, No. 41-01/306, on stepping up work on developing and approving HAFPs for populated places in Ukraine's regions. During the second half of 2025, the draft HAFP for Krasyliv was agreed (Ministry letter No. 11/113/687-25 of 19 November 2025) and its historic area approved (Order No. 773 of 16 September 2025); the draft HAFP for Yampil, Vinnytsia oblast, was agreed (Ministry letter No. 11/113/831-25 of 30 December 2025) and the boundaries of its historic areas approved (Order No. 1122 of 30 December 2025). Under review (considered by the Scientific-Methodological Council, being finalised): Bila Tserkva, Olevsk, Bershad, Voronizh, Lanivtsi, Kalush, Lukiv, Sosnytsia, Kamin-Kashyrskyi, Stara Syniava, Novoukrainka, Chyhyryn, Lysianka, Horodyshche, Holovne, Ustyluh. Submitted to the Ministry for the first time and currently being processed: Radyvyliv, Halych, Dashiv, Sniatyn, Kramatorsk, Putyla, Balakliia. | Zakarpattia oblast 99,998 | Sumy oblast 195,2 | Lviv oblast 120,0 | Volyn oblast Lack of adequate funding for producing scientific-design documentation; lengthy development timelines. Kyiv oblast Limited capacity of budgets at all levels has slowed the pace of developing scientific-design documentation. Luhansk oblast Under Order No. 376 of the Ministry for Communities, Territories and Infrastructure Development of Ukraine dated 28 February 2025, most of Luhansk oblast is classified as temporarily occupied territory, with the remainder classified as an area of active combat. All immovable cultural heritage sites are located in temporarily occupied territory of the oblast or in areas of active combat, to which there is currently no access. Given this, developing and approving scientific-design documentation defining the boundaries and use regimes of monument territories, protection zones and historic areas of populated places is not possible. Implementing this measure will become possible after the de-occupation of the oblast's territory, the implementation of appropriate security measures, and the restoration of access to monuments. Lviv oblast Under paragraph 6 of the first part of Article 141 of the Law of Ukraine "On the Protection of Cultural Heritage", the procedure for determining the boundaries and use regimes of a monument's territory and for approving the corresponding scientific-design documentation is to be established by the Cabinet of Ministers of Ukraine. Currently, no such procedure exists. Sumy oblast No Cabinet of Ministers regulatory acts have been adopted regarding the procedure for determining and approving the use regimes of cultural heritage monuments, the boundaries and use regimes of their territory, or the composition and content of scientific-design (research) documentation. Due to the military aggression, funding for developing scientific-design documentation defining boundaries and use regimes of monument territories, protection zones and historic areas is limited. Kherson oblast There are discrepancies in the developed urban-planning documentation, namely between the General Plan of Kherson and the historical-architectural framework plan of Kherson. These cannot be quickly resolved due to Russia's armed aggression against Ukraine. The oblast's territory is classified as an area of active combat and territory temporarily occupied by Russia, and access to monuments is limited/impossible. A significant share of monuments have suffered damage/destruction. |
|  | 2) Ensuring the update and population of the "State Register of Immovable Monuments of Ukraine" information and communication system | 2025—2027 | an increase of at least 10 percent secured in the number of cultural heritage sites entered in the register |  | Vinnytsia oblast Population of the State Register of Immovable Monuments of Ukraine has been carried out for the category "monuments of national significance" — 110 nationally significant monuments; entry of monuments in the category "locally significant monuments" has begun. Volyn oblast In 2025, work continued on populating the "State Register of Immovable Monuments of Ukraine" ("Yepamyatka") information and communication system. As of 1 March 2026, information on 164 cultural heritage sites has been entered. Dnipropetrovsk oblast In the "card" mode, 91 nationally significant monuments (53 protection numbers) have been entered into the register; in "draft" mode, 40 locally significant monuments. Donetsk oblast As of 24 February 2022, there were 7,541 cultural heritage sites in the part of Donetsk oblast under Ukrainian government control. The Oblast Administration has entered 6,719 nationally and locally significant monuments into the register. Zhytomyr oblast 40% (105) new cultural heritage sites were entered in the register over the year (of which 33 are nationally significant and 72 locally significant). Zakarpattia oblast The oblast has 1,764 material cultural heritage monuments under state protection requiring preservation: 506 archaeological, 468 historical, 76 monumental art, 489 architectural/urban planning, 41 landscape-park art, 175 landscape, and 9 science and technology monuments. Zaporizhzhia oblast The "eRegister" is currently operating in test mode. The Oblast Administration and the Zaporizhzhia Regional Cultural Heritage Protection Centre are entering data on sites of archaeology, history, monumental art, and science and technology. As of 20 January 2026, geographic coordinates (WGS-84) have been clarified for 468 archaeological sites, 15 decisions on state registration have been uploaded, and information on 63 archaeological, historical and monumental-art monuments has been entered (currently in draft status). Ivano-Frankivsk oblast Basic information on 2,800 immovable heritage sites of various types, including 110 nationally significant sites, has been processed and uploaded to the electronic system. Kyiv oblast 52 monuments have been entered into the register. Kirovohrad oblast 5,538 cultural heritage sites have been entered into the register (including 240 in 2025). Luhansk oblast In 2025, data on 52 cultural heritage sites (18 nationally significant, 34 locally significant) were entered and verified in the register. Lviv oblast As of the end of 2025, 9 cultural heritage site records have been created, and information on a further 42 sites is prepared in "draft" status. Mykolaiv oblast During the reporting period, 35 nationally significant monuments were entered into the register. Odesa oblast Information on 4,493 cultural heritage sites (100%) of Odesa oblast has been entered into the register. Updating and supplementing information on individual monuments is carried out on an ongoing basis. Poltava oblast Registration documentation for 25 cultural heritage sites was reviewed. The number of newly identified sites increased by 7. Rivne oblast 41 updated data cards on cultural heritage sites (2.5%) have been entered into the register. Ternopil oblast As of 1 January 2026, 4,920 monuments and cultural heritage sites (history, archaeology, monumental art) have been entered into the declaration system, of which 70 are records, plus 132 nationally significant cultural heritage monuments in the category of architecture and urban planning. Kharkiv oblast: 56 sites have been entered into the register; population is ongoing. Kherson oblast: Updating and population of the register is ongoing. Geographic coordinates and point codes have been entered for historical and monumental-art monuments, along with data on 15 nationally significant archaeological monuments located in the de-occupied part of the oblast. Khmelnytskyi oblast Last year the oblast digitised registration documentation for cultural heritage sites already entered in the register, to support its population. Cherkasy oblast During 2025, information on 85 cultural heritage sites was updated and entered into the register. Chernivtsi oblast All historical and cultural monuments located in Chernivtsi oblast (100%) have been entered into the register. Work on updating and supplementing information is ongoing. Chernihiv oblast 100% of nationally significant archaeological, historical and monumental-art monuments of Chernihiv oblast have been entered into the register (32 archaeological, 9 historical, 1 monumental art). Ministry of Culture During 2025, the Ministry developed a draft Cabinet of Ministers resolution "On implementing a pilot project for introducing the information and communication system for the registration of immovable cultural heritage sites of Ukraine — the 'State Register of Immovable Monuments of Ukraine'". This draft was approved by Cabinet of Ministers Resolution No. 93 of 28 January 2026. Population and verification of entries in the Register is underway. |  |  |  | Volyn oblast Need for ongoing methodological support and user training for the system. Kirovohrad oblast Insufficient financial resources of local budgets; lack of initiative from certain local self-government bodies; inadequate exercise by local self-government bodies of their powers to initiate and commission historical-architectural framework plans, leading to litigation and delays in establishing boundaries and use regimes for monument territories and historic areas. Lviv oblast It is additionally noted that the Procedure for implementing the pilot project for introducing the information and communication system for immovable cultural heritage registration ("State Register of Immovable Monuments of Ukraine") was approved by Cabinet of Ministers Resolution No. 93 of 28 January 2026. Sumy oblast The pilot project for introducing the information and communication system for immovable cultural heritage registration ("State Register of Immovable Monuments of Ukraine") was launched pursuant to Cabinet of Ministers Resolution No. 93 of 28 January 2026. |
|  | 3) Developing and approving an algorithm for assessing status, entering and making changes in the register regarding cultural heritage sites in temporarily occupied territory of Ukraine | IV квартал 2025 року | Order of the Ministry of Culture issued and registered with the Ministry of Justice of Ukraine | буде розроблено протягом 2026 року | Ministry of Culture This order will be developed during 2026. At the same time, the Ministry has drafted a Cabinet of Ministers resolution "On implementing a pilot project for introducing the information and communication system for the registration of immovable cultural heritage sites of Ukraine — the 'State Register of Immovable Monuments of Ukraine'" and submitted it to the Cabinet of Ministers of Ukraine for consideration. This system will display and accumulate information on cultural heritage sites located throughout the whole territory of Ukraine, and the draft resolution sets out requirements for officials of oblast and Kyiv City state administrations (military administrations) to enter register data and copies of documents on immovable cultural heritage sites into the Register. |  |  |  |  |
| 41. Implementing measures to memorialise events related to the Russian Federation's armed aggression | Creating museum exhibitions and memorial complexes dedicated to events related to the Russian Federation's armed aggression against Ukraine | 2025—2027 | at least 25 new museum exhibitions and memorial complexes created |  | Vinnytsia oblast Museums in the oblast have created 62 museum exhibitions (temporary displays) dedicated to events related to Russia's armed aggression against Ukraine, which are continually updated and supplemented with new material. Volyn oblast Museums are implementing a range of exhibition, display and cultural-educational projects with a national-patriotic focus, and events are held to honour the memory of soldiers and participants of the Russian-Ukrainian war, including meetings with Volyn journalists and service members. Dnipropetrovsk oblast Museums in the oblast have created 14 museum exhibitions dedicated to events related to the Russian Federation's armed aggression against Ukraine. Donetsk oblast The Donetsk Regional Local History Museum held the cultural-artistic campaign "Born Free", including the presentation of the exhibition "The Face of Resistance" and a motivational meeting, "In Their Own Words: Stories of Volunteers". Staff of the Donetsk Regional Art Museum organised and opened the regional art exhibition "The East: A Level of Freedom", organised the art campaign "Unbreakable Donetsk Region: Sites of Resistance", held the cultural-artistic campaign "Sunflower of Memory", an art-therapy interactive event "Amulets of Strength" within the "Art-Unity" cultural-artistic campaign, and an interactive session creating a collective art canvas, "Tree of Life of Ukraine". Zhytomyr oblast 10 exhibitions were created: 1. Novoboriv Local History Museum — permanent exhibition since 2025, "The Price of Freedom". 2. Zviahel Local History Museum — exhibition "Angels Who Hold Up the Sky". 3. Terekhiv Museum — temporary exhibition of photographs from the start of the invasion, by Yefrem Lukatsky (Associated Press), Dmytro Kozatskyi ("Azov", photos from Azovstal) and other members of the National Union of Photo Artists of Ukraine. 4. Korovyntsi Museum — exhibition "A Life for Ukraine". 5. Museum of the History of Ovruch Region — exhibition dedicated to current events. 6. Korosten Museum — permanent exhibition "The Full-Scale Invasion". 7. Slovechansk Museum of Partisan Glory — permanent exhibition dedicated to the full-scale invasion. 8. Museum of Precious and Decorative Stone — permanent exhibition "The Path of Struggle: The History of the Russian-Ukrainian War". 9. Baranivka Museum — exhibition "For Ukraine, for Freedom, They Gave Their Loyal Lives". 10. Korostyshiv Folk Historical Museum — permanent exhibition of Russian-Ukrainian war artefacts. Using local budget funds, the oblast has arranged 97 Alleys of Glory and memory alleys, installed 421 memorial plaques, is installing memorial markers (gravestones) at the graves of fallen (deceased) defenders of Ukraine, arranging and maintaining memorial complexes, and purchasing and installing state flags at the graves of fallen (deceased) service members. Zakarpattia oblast A permanent exhibition operates at the T. Lehotskyi Zakarpattia Regional Local History Museum. 17 museum institutions in the oblast have computers with internet access; information/electronic kiosks have also been installed (worth UAH 280,000). Zaporizhzhia oblast 4 communal museums operate in the government-controlled part of the oblast, carrying out ongoing memorialisation activities related to the War for Independence of Ukraine, including: the Zaporizhzhia Regional Local History Museum, which runs the exhibition "War for Independence", continually supplemented with new material — and with the support of the Ukrainian Cultural Foundation has created the exhibition "Prisms of Memory: Names of the Unconquered"; the Novomykolaivka Local History Museum, which has created a permanent exhibition "The Russian-Ukrainian War and the Participation of Novomykolaivka Residents"; and the Vilniansk Local History Museum, which has created a permanent exhibition on the War for Independence of Ukraine. In addition, in 2025 the Zaporizhzhia Regional Universal Scientific Library hosted the exhibition "Azov: Angels of Mariupol", and the Zaporizhzhia Regional Philharmonic hosted the photo exhibitions "Philharmonic Defence in Action" and "Heroes Never Die". In total, 7 museum exhibitions dedicated to these events have been created and are in operation. Ivano-Frankivsk oblast Museums in the oblast have created and maintain exhibitions demonstrating the history of the Russian-Ukrainian war. Permanent exhibitions operate at the Stepan Bandera Ivano-Frankivsk Regional Museum of the Liberation Struggle and its branches — the "Demianiv Laz" Museum Complex and the Stepan Bandera Historical-Memorial Museum — as well as at the Kalush Municipal Museum and Exhibition Centre, the "Boikivshchyna" Local History Museum of Tetiana and Omelian Antonovych, and the Museum of the History of the City of Kolomyia. A temporary exhibition by the 10th "Edelweiss" Mountain Assault Brigade, "Portal Into War / On the Front Line", is showing at the Museum of Ethnography and Ecology of the Carpathian Region, a branch of the Y. Kobrynskyi National Museum of Hutsul and Pokuttia Folk Art in Yaremche. Kyiv oblast In 2025, museum institutions created and continually update exhibitions dedicated to honouring the memory of fallen defenders of Ukraine. The "Rooms of Heroes" exhibition at the Yahotyn Historical Museum was visited in 2025 by 767 combat veterans and 594 internally displaced persons (IDPs). Museums run cycles of tours and educational events for students, IDPs, and community residents. Museum collections are being expanded with artefacts of the Russian-Ukrainian war. Kirovohrad oblast Museums in the oblast have created 5 new museum exhibitions dedicated to events related to the Russian Federation's armed aggression against Ukraine. In 23 museum institutions, existing exhibitions on this topic are continually supplemented with new documents and artefacts. The oblast is also actively participating in the national project "Routes Through Places of Memory", and has submitted proposals to the Ministry for Communities and Territories Development of Ukraine and the State Tourism Development Agency for creating a unified nationwide tourist route covering 6 locations: 1) the Alley of Glory at the Fortress Ramparts Memorial Complex in Kropyvnytskyi; 2) the memorial screen with photographs of local soldiers killed in the Russian-Ukrainian war in Kropyvnytskyi; 3) the exhibition of the Russian-Ukrainian war "Ukraine: The Flame of War" at the Central Ukrainian Regional Local History Museum (Kropyvnytskyi); 4) the Monument to the Patriots of Ukraine, living and fallen, in the settlement of Kompaniivka; 5) the memorial-religious complex in honour of the Archangel Michael in the village of Yosypivka; and 6) the complex of religious buildings in honour of the Intercession of the Theotokos in the village of Tyshkivka. The total route length is 110 km. Work continues on further implementing the national project "Routes Through Places of Memory" by the Kropyvnytskyi, Novomyrhorod, and Kompaniivka councils. Luhansk oblast Until May 2025, a temporary exhibition operated in rented premises of the Rubizhne Municipal Museum in Kyiv, based on banner displays: "I'm from Ukraine, Bring Me Home!", "Frontier of Victory", "Rubizhne — This Is Ukraine", and "Rubizhne: Memorial of Heroes". Following a missile strike on Kyiv on 24 April 2025, the building where the museum rented premises was damaged. The equipment and exhibits were relocated to Dnipro and Vinnytsia and placed in humanitarian hubs of the Rubizhne community. At present, establishing memorial complexes dedicated to events related to the Russian Federation's armed aggression against Ukraine is not possible due to the significant occupation of the oblast's territory. Lviv oblast Creation of the exhibition of contemporary Ukrainian reportage photography "Strength of Spirit: Ukraine, War, People" at the Lviv Historical Museum. Mykolaiv oblast Thematic exhibitions dedicated to recent history and the heroism of Ukrainian defenders have been arranged in 15 museum institutions of the oblast (60%). Existing exhibition material is continually supplemented and updated. Mykolaiv oblast has actively joined the creation of a unified tourist route incorporated into the national digital museum of war memory, which will support the development of patriotic and memorial tourism and the formation of national identity. Memory route sites in Mykolaiv oblast include: the Battle for Bashtanka — Checkpoint No. 3 (Bashtanka urban community); the Defence of Voznesensk — the demolition of the road bridge over the Mertvovod River (Voznesensk urban community); the Mykolaiv International Airport communal enterprise (Kostiantynivka rural community, Mykolaiv district); and the building of the Mykolaiv Oblast Military Administration, destroyed by Russian occupiers (Mykolaiv, oblast centre). Odesa oblast The Odesa Museum of Local History is updating the interactive exhibition "They Defended Ukraine!" and creating the section "Heroes Never Die! Odesa Region", dedicated to honouring soldiers from Odesa region who fell during Russia's armed aggression against Ukraine. Poltava oblas The first five sites of Poltava region included in the national project "Routes Through Places of Memory" have been presented. All communal museum institutions in the oblast have created thematic exhibitions, displays, or information sections covering events related to Russia's armed aggression against Ukraine and aimed at preserving historical memory and honouring Ukraine's defenders. Rivne oblast 14 museum institutions of the oblast have created 53 exhibitions. Sumy oblast Museum exhibitions have been created in 9 museum institutions. Ternopil oblast Museums in the oblast have held events honouring the events and heroes of the Russian-Ukrainian war, including opening permanent thematic exhibitions. On 14 March 2025, the Ternopil Oblast Council's Museum of the National-Liberation Struggle of Ternopil Region presented an updated version of the "Volunteers" exhibition hall, featuring new chevrons and photographs. During August–September 2025, the Ternopil Regional Local History Museum, the Ternopil Regional Art Museum, and the Museum of the National-Liberation Struggle of Ternopil Region held the exhibition project "Ternopil Region: Light for the World" for Ukraine's Independence Day, with the participation of veterans of the current Russian-Ukrainian war. In the village of Lishnia, Kremenets district, a memorial pantheon church was built in honour of the Heroes who gave their lives fighting Russian occupiers. A memorial chapel in the village of Zarvanytsia, Ternopil district, is dedicated to fallen Heroes. The Ternopil Regional Centre for the Protection and Scientific Study of Cultural Heritage Monuments maintains a register of graves, monuments and memorial markers to Defenders of Ukraine killed during the Russian-Ukrainian war. As of 1 January 2026, the preliminary register includes 1,587 graves and 483 memorial markers (including memorial plaques, tablets, banners, and stands). Kharkiv oblast Within the project of a unified route through places of memory run by the Ministry for Communities, Territories and Infrastructure Development, 16 memory sites have been identified in Kharkiv oblast. In Kharkiv oblast, the recording of eyewitness accounts covering the resistance of the Ukrainian people, crimes of the Russian occupying authorities, and other events of the Russian-Ukrainian war — including during the occupation of certain districts of the oblast — is carried out by the M.F. Sumtsov Kharkiv Historical Museum, the National Museum of Military History of Slobozhanshchyna, and representatives of rural, settlement and urban territorial communities in the oblast. Kherson oblast In 2025, as part of building new museum exhibitions and displays, the Kherson Regional Local History Museum implemented patriotic and local-history exhibition projects. In particular, the photo exhibition "Unbreakable Kherson Region" was created and displayed, including travelling shows in other regions of Ukraine, covering the resistance and resilience of Kherson region under armed aggression. In addition, the banner exhibition "Along the Ways of the Free Steppe" (on the history of Kherson region) was prepared and presented, dedicated to the historical development of the region from earlier eras to the present. The cultural-artistic exhibition "Unbreakable Kherson" was presented in Vilnius, Lithuania. A presentation of the documentary photo exhibition "Libraries of Kherson Region: Russia's Crimes Against Ukrainian Culture" was organised in Lviv. For Children's Protection Day, an exhibition of children's drawings was presented as part of the project "Messages from Kherson's Children to the World". The exhibition "Art of No Freedom: Russian Captivity Through a Civilian's Eyes" was organised in Kherson. In de-occupied communities of Kherson oblast, memorialisation activities related to Russia's armed aggression against Ukraine were carried out. In particular, in the Borozenske, Myliv, Novoraisk and Kochubeivka territorial communities, and in settlements of the Vysokopillia community, alleys of glory and memorial spaces dedicated to fallen service members from those communities were created and opened, including using information materials, photo portraits, and honouring those missing without a trace. Within the national project "Unified Route Through Places of Memory", 7 memory locations have been arranged and opened in the oblast. Oblast-level memorialisation initiatives are being implemented, including the projects "Open-Air Museum" and the memory site for civilian Heroes of Kherson region, "Honour Each One, Remember All", involving the development of concepts, identification of locations, field work, and the formation of future memorial and museum spaces. Khmelnytskyi oblast The oblast ensures memorialisation of events related to Russia's armed aggression through the creation of separate exhibitions and displays. In particular, 3 permanent exhibitions operate (at the Khmelnytskyi Regional Local History Museum, the Museum of Propaganda of the Khmelnytskyi Oblast Council, and the "Mezhybizh" State Historical-Cultural Reserve), along with other memorial exhibitions in all museum institutions of the oblast. Cherkasy oblast In 2025: an exhibition complex dedicated to Junior Lieutenant of the Armed Forces of Ukraine Oleksandr Riaboshlyk was created; an exhibition complex dedicated to Cherkasy native and Junior Sergeant of the Armed Forces of Ukraine Yaroslav Bezrukov was created; an exhibition complex of trophy reconnaissance aircraft and FPV drones (handed over by the State Border Guard Service of Ukraine) was created; and an exhibition complex of a collection of sleeve and chest insignia of Ukraine's Security and Defence Forces was maintained. Chernivtsi oblast The Chernivtsi Regional Local History Museum runs the permanent exhibition "For Ukraine, For Her Freedom", dedicated to the events of the Revolution of Dignity and the start of Russia's armed aggression against Ukraine, and the permanent exhibition "In Defence of Freedom", covering events of the Revolution of Dignity and the start of Russian armed aggression through a regional lens. The Novodnistrovsk Historical Museum operates an exhibition section, "Hall of Military Glory", covering the heroic struggle of the Ukrainian people for independence and the repelling of Russia's armed aggression. The exhibitions are continually supplemented with new items. Chernihiv oblast Museums in Chernihiv oblast have created and maintain 31 permanent museum exhibitions dedicated to this topic. To honour the memory of those killed in the Russian-Ukrainian war, a set of memorialisation measures has been implemented in Chernihiv region, including the opening of memorial complexes and markers in Chernihiv, Nizhyn, Pryluky and Snovsk, and the arrangement of Alleys of Heroes and memorial steles in over 20 settlements of Koriukivka and Chernihiv districts. In addition, digital memorialisation tools are being actively introduced: touch-screen terminals with data on fallen soldiers have been installed in 4 communities, and stands for the Unified All-Ukrainian Memory Route with QR-code access to a VR museum of destruction have been arranged in the villages of Yahidne, Lukashivka and Novoselivka. | Zakarpattia oblast 300,0 | Zhytomyr oblast 4312,0 Odesa oblast 40,0 Kherson oblast 60,0 ("Along the Ways of the Free Steppe") | Lviv oblast 5,0 | Luhansk oblast Under Order No. 376 of the Ministry for Communities, Territories and Infrastructure Development dated 28 February 2025, most of Luhansk oblast is classified as temporarily occupied territory, with the remainder classified as an area of active combat. In the government-controlled part, six museums have resumed operation, though most lack their own or leased premises suitable for displaying exhibitions. Nonetheless, preparatory work for the future creation — after de-occupation of the oblast — of exhibitions covering the history of the Russian-Ukrainian war is underway in the oblast's museums: research work is being carried out and archives of oral histories are being created, among other things. Banner exhibitions based on the collected material are being displayed at humanitarian headquarters of Luhansk oblast's territorial communities, as well as in museums and other institutions in Ukraine and abroad. Kherson oblast Buildings of oblast museums damaged as a result of Russian military aggression. |
| Area "Medical Services" |  |  |  |  |  |  |  |  |  |
| 42. Ensuring the functioning of a capable public health system in the regions and territorial communities | 1) Ensuring the functioning of regional public health coordination councils | 2025 | quarterly meetings of regional coordination councils to be held |  | Vinnytsia oblast In 2025, 3 meetings of the coordination council were held, at which 11 issues were considered. Dnipropetrovsk oblast In 2025, 4 meetings of the Regional Public Health Coordination Council under the Dnipropetrovsk Oblast State Administration were held (established by order of the Head of the Oblast Administration No. R-87/0/3-24 of 27 February 2024, as amended). Donetsk oblast During 2025, 4 meetings of the regional coordination council were held. Zhytomyr oblast 4 meetings of the regional public health coordination council were held; 14 issues were considered. Zakarpattia oblast To ensure the functioning of a capable public health system in communities, Zakarpattia oblast has established and operates the Regional Public Health Coordination Council, the Oblast Council for Coordinating the Response to the Spread of Tuberculosis and HIV, and the Council for Coordinating the Work of Primary Care Institutions of Zakarpattia oblast. Under the work plan, the coordination councils meet quarterly to consider current issues and subsequently formulate recommendations for territorial communities. Zaporizhzhia oblast To ensure the effective implementation of state policy in public health at the regional level, the Regional Public Health Coordination Council of Zaporizhzhia Oblast was established by order of the Head of the Oblast Administration/Military Administration No. 462 of 23 April 2025. At council meetings (10 July 2025; 27 October 2025), current issues aimed at improving the health of the regional population were considered, including: the status of implementing immunisation measures in the oblast; problems with the use of antimicrobial drugs in healthcare institutions; the introduction of a systematic HPV vaccination programme as an effective tool for cancer prevention; and safeguarding children's health in educational institutions under blended learning. Ivano-Frankivsk oblast By order of the Oblast Administration No. 11 of 13 January 2023 (as amended by order No. 128 of 2 April 2025), the composition of the public council was approved, with its meeting schedule formed by the coordinator — the Ivano-Frankivsk Regional Centre for Disease Control and Prevention of the Ministry of Health of Ukraine. Kyiv oblast At quarterly meetings of the Regional Public Health Coordination Council in 2025, issues considered included the results of population immunisation coverage in 2024 and plans for 2025 and 2026, the epidemic situation regarding HIV infection, tuberculosis, hepatitis and STIs and the implementation of screening programmes, the results of the pilot programme "Save a Schoolchild's Eyesight", and the approval of a regional action plan for implementing the Strategy for Controlling Malignant Neoplasms for 2026. Kirovohrad oblast: During 2025, 4 meetings of the coordination council were held. The council's work during the year focused on the following key areas: 1) preventive work — regional action plans were developed and implemented for key health dates (fighting tuberculosis, HIV/AIDS, hepatitis, strokes and cancer), including large-scale information campaigns and screenings for early detection of pathologies; 2) immunoprophylaxis and infection control — ongoing monitoring of vaccination-plan implementation for vaccine-preventable infections was ensured, an analysis of antibiotic resistance in oblast healthcare institutions was conducted, and measures for the rational use of antimicrobial drugs were introduced; 3) mental and social support — under the "Ty Yak?" ("How Are You?") initiative, events were held for World Mental Health Day, breastfeeding support programmes were introduced, and access to medico-social services was expanded for vulnerable population groups; 4) environmental safety — an analysis of drinking-water quality in the region was carried out, control over environmental risks and prevention of particularly dangerous diseases (including rabies) was strengthened, and an assessment of the effectiveness of the regional tobacco-control strategy was conducted. Luhansk oblast 4 meetings of the regional public health council were held, considering issues of immunisation, infection control, the formation of a healthy educational environment, communication, and recovery/wellness. Lviv oblast By order of the head of the Military Administration No. 27/0/5-24VA of 16 January 2024, "On establishing the Regional Public Health Coordination Council in Lviv Oblast", the Regional Public Health Coordination Council of Lviv oblast was established. Meetings are held according to the work plan approved by the chair of the Regional Council, but no less than once every three months. Mykolaiv oblast The Regional Public Health Coordination Council in Mykolaiv region operates as an advisory body under the Mykolaiv Oblast Military Administration, established to ensure interaction between government bodies, healthcare institutions, and the public. The council's membership includes representatives of the Oblast Military Administration's structural units, heads of healthcare institutions, and public associations working in public health. The council's activities are aimed at implementing the 10 essential public health operations of the WHO, disease prevention, and control of infectious and chronic diseases. During 2025, 4 council meetings were held, resulting in management decisions that helped improve population access to medical services, strengthen intersectoral cooperation, and introduce modern approaches to care delivery. Odesa oblast The Regional Public Health Coordination Council under the Odesa Oblast Military Administration operates as an advisory body. The council coordinates the response to infectious and non-communicable diseases, ensures immunoprophylaxis, and develops strategies for the region's public health system. Meetings are held on an ongoing basis. Poltava oblast Meetings of regional coordination councils are held quarterly. Rivne oblast By order of the head of the Oblast State Administration/Military Administration No. 55 of 15 February 2024 (as amended by order No. 611 of 10 October 2025), the Regional Public Health Coordination Council of Rivne Oblast was established. In 2025, 2 meetings of the coordination council were held (31 March and 30 September). Sumy oblast 2 meetings of the regional council were held (23 April 2025, 18 December 2025), at which the work plans for 2025 and 2026, strategic directions for developing the regional public health system, and changes to the disease-prevention system, among other things, were considered. Ternopil oblast A public health coordination council operates under the Ternopil Oblast Military Administration (order of the head of the Military Administration No. 22/01.02-01 of 23 January 2024), which considers current public health issues quarterly. Kharkiv oblast The Regional Public Health Coordination Council of Kharkiv oblast was established in 2024. Four meetings of the coordination council were held in 2025. Khmelnytskyi oblast: To develop the public health system in Khmelnytskyi oblast, protect population health, prevent disease, and improve quality and life expectancy, a regional Public Health Coordination Council was established under the Khmelnytskyi Oblast Military Administration in 2024; 6 meetings have been held since the council began work. Cherkasy oblast By order of the Cherkasy Oblast Military Administration No. 217 of 20 May 2024, a coordination council of the Cherkasy Oblast State Administration on public health was established as a standing advisory body under the Cherkasy Oblast Military Administration. Chernivtsi oblast: 4 meetings of the Chernivtsi Regional Public Health Coordination Council under the Oblast State Administration (Military Administration) were held, at which the following issues were considered: implementing an intersectoral "One Health" approach to preventing zoonotic infectious diseases; cooperation with the oblast's communities on preventing non-communicable diseases, including information and awareness events; introducing, applying and maintaining HACCP systems (standing procedures based on hazard-analysis and critical-control-point principles) at inpatient healthcare facilities to ensure compliance with food-safety legislation; medical services for students who have come to study at oblast educational institutions from other localities but whose medical service agreements are concluded at their place of residence; countering the spread of antimicrobial resistance in Chernivtsi oblast; the status of implementing the action plan through 2025 under the National Strategy for Controlling Malignant Neoplasms through 2030; an analysis of key immunoprophylaxis indicators and the availability of immunobiological preparations in Chernivtsi oblast for the first 6 months of 2025; measures to prevent the spread of tuberculosis among the population of Chernivtsi oblast; and the status of implementing measures under the Concept for Developing Mental Health Care in Ukraine through 2030. Chernihiv oblast: In 2025, 4 meetings of the regional public health coordination council were held. |  |  |  | Luhansk oblast Under Order No. 376 of the Ministry for Communities, Territories and Infrastructure Development dated 28 February 2025, most of Luhansk oblast is classified as temporarily occupied territory, with the remainder classified as an area of active combat. Because of this, meetings are held in an online format. |
|  | 2) Approval of regional and local public health programmes | 2025 | approval of regional and local public health programmes ensured in all regions of Ukraine | Ongoing | Vinnytsia oblast Development of regional and local public health programmes is planned to begin in 2026. Dnipropetrovsk oblast Dnipropetrovsk oblast operates the oblast programme "Health of the Population of Dnipropetrovsk Region for 2020–2026". Donetsk oblast By order of the Head of the Oblast Administration/Military Administration No. 264/5-25 of 14 April 2025, the Regional Programme for Early Diagnosis and Control of Cancer in Donetsk Oblast through 2028 was approved. The oblast also has in place a Strategy for the Development of Immunoprophylaxis and Population Protection from Vaccine-Preventable Infectious Diseases in Donetsk Oblast through 2030, along with an operational plan for its implementation in 2024–2025, approved by order of the head of the Oblast Administration/Military Administration No. 204/5-24 of 4 April 2024. Zhytomyr oblast The oblast programme "Health of the Population of Zhytomyr Region" for 2025 was approved by order of the Zhytomyr Oblast Military Administration No. 814 of 17 October 2024. Zakarpattia oblast The Comprehensive Programme for Supporting the Healthcare Sector of Zakarpattia Oblast for 2026–2028 was approved by order of the head of the Oblast State Administration/Military Administration No. 827 of 3 December 2025 (as amended by order No. 193 of 19 March 2026). Kyiv oblast Kyiv oblast is implementing the Kyiv Oblast Programme "Health of Kyiv Region" for 2024–2026, approved by decision of the Kyiv Oblast Council No. 762-22-VIII of 7 December 2023 (as amended in 2025). Kirovohrad oblast A draft Strategy for Developing the Public Health System in Kirovohrad Oblast through 2030 has been prepared. Luhansk oblast The "Operational Plan for Implementing in 2026–2028 the Strategy for Developing Immunoprophylaxis and Protecting the Population of Luhansk Oblast from Vaccine-Preventable Infectious Diseases through 2030" has been prepared for approval. In 11 territorial communities of the oblast, the "TB-Free Territorial Community" initiative is being implemented, with 11 corresponding local programmes adopted. Lviv oblast The Regional Action Plan for Combating Antimicrobial Resistance for 2024–2026, approved by minutes of the Regional Public Health Coordination Council of Lviv Oblast meeting No. 1 of 29 March 2024. The plan for implementing additional immunisation measures against pertussis, tetanus and diphtheria in Lviv oblast, approved by minutes of the Regional Public Health Coordination Council meeting No. 2 of 16 July 2024. The plan of measures to preserve schoolchildren's dental health in Lviv oblast for 2024–2026, approved by minutes of the Regional Public Health Coordination Council meeting No. 3 of 4 November 2024. The Regional Public Health Strategy for Lviv Oblast for 2026–2030, approved by minutes of the Regional Public Health Coordination Council meeting No. 3 of 19 December 2025. Mykolaiv oblast Mykolaiv region has regional and local public health programmes aimed at developing healthcare institutions and preventing disease, including through the Oblast Programme for the Development of Healthcare Institutions for 2025–2027 and the activities of the regional public health coordination council. Primary focus is on improving material and technical infrastructure and countering infectious and non-communicable diseases. Odesa oblast Odesa oblast has the oblast targeted programme "Health of Odesa Region for 2024–2026", aimed at improving the quality of medical services, disease prevention, and implementation of public health measures, including combating infectious and non-communicable diseases. Poltava oblast Pursuant to subparagraph 3 of paragraph 1 of Article 12 of the Law of Ukraine "On the Public Health System", the oblast annually develops and implements Regional Plans for the Functioning and Development of the Public Health System. Rivne oblast A draft oblast public health programme has currently been developed and is pending approval by the head of the Military Administration. Sumy oblast To support the development of public health services and raise population awareness of healthcare achievements and medical reform, 19 round tables, 35 radio appearances and 91 TV appearances were held, 126 publications were made on institutional websites and 210 on social media; on promoting a healthy lifestyle, 36 round tables, 100 radio appearances and 40 TV appearances were held, with 272 publications on institutional websites and 311 on social media. Ternopil oblast By order of the head of the Oblast Military Administration No. 71/01.02-01 of 9 February 2024, the oblast approved a plan of measures for implementing the National Action Plan on Non-Communicable Diseases to achieve global sustainable development goals. Kharkiv oblast The Department of Health Care of the Kharkiv Oblast State (Military) Administration, together with specialists of the Kharkiv Regional Centre for Disease Control and Prevention of the Ministry of Health of Ukraine, has prepared a draft order of the head of the Oblast Military Administration "On establishing a working group to develop a regional public health programme in Kharkiv oblast". Certain public health measures are included in the comprehensive oblast programme "Health of Slobozhanshchyna" for 2023–2025, approved by decision of the Oblast Council No. 464-VIII of 24 December 2022 (as amended). Khmelnytskyi oblast Development of the Khmelnytskyi Oblast Public Health Programme is planned for 2026. In the meantime, 3 corresponding local programmes are in place (in the Khmelnytskyi, Shepetivka, and Slobidsko-Kulchiivtsi territorial communities). Cherkasy oblast: This measure was not implemented in the oblast in 2025. Chernivtsi oblast The oblast implemented the Regional Programme for the Development and Support of Oblast Communal Healthcare Institutions for 2023–2025, approved by order of the Oblast State Administration/Military Administration No. 1483-r of 12 December 2022. By decision of the 48th session of the Vyzhnytsia Town Council (8th convocation) of 18 June 2025, the programme "Public Health of the Vyzhnytsia Urban Territorial Community for 2025–2028" was approved. Chernihiv oblast In 2025, Chernihiv oblast implemented: the "Oblast Programme for the Development and Support of Chernihiv Oblast Council Communal Healthcare Institutions and Improving the Provision of Medical Services to the Population for 2022–2025"; the "Programme of Social Support for Defenders of Ukraine, Their Family Members, and Persons Affected by the Military Aggression of the Russian Federation on the Territory of Chernihiv Oblast, for 2024–2026"; the "Oblast Programme for Early Diagnosis of Certain Types of Cancer Among the Population of Chernihiv Oblast for 2025–2030"; and the "Oblast Programme for Mental Health Care and Psychosocial Support of the Civilian Population in Chernihiv Oblast for 2024–2025". |  | Kyiv oblast 343742,4 Luhansk oblast 200,4 Chernihiv oblast 192727,5 | Kyiv oblast 79200,0 Chernihiv oblast 120056,9 | Donetsk oblast Implementation of the programme is complicated by the security situation arising from active combat in the oblast, a shortage of personnel, and funding priorities directed toward supporting the defence forces and building protective structures. Kyiv oblast Due to limited capacity of budgets at all levels and of extra-budgetary funding sources, implementation of measures under the "Health of Kyiv Region" programme in 2025 reached only 47.8% of the volumes envisaged by the programme. |
|  | 3) Conducting training on the readiness of forces and resources to prevent, respond to, and counter threats to public health and sanitary-epidemiological wellbeing of the population | 2025–2027 | At least 10 simulation exercises to be held | Ongoing | Ministry of Health of Ukraine During 2025, specialists of the Ministry of Health's Public Health Department, Medical Services Department, the "Public Health Centre of the Ministry of Health of Ukraine" state institution, regional Centres for Disease Control and Prevention, and the "Ukrainian Scientific-Practical Centre for Emergency Medical Care and Disaster Medicine" state institution took part in a number of regional command-staff exercises with civil-protection command bodies and forces of the territorial subsystem of the unified state civil-protection system, including in Vinnytsia, Ternopil, and Ivano-Frankivsk oblasts. The theme of the exercises was "Actions of civil-protection command bodies and forces of the territorial subsystem of the unified state civil-protection system in the relevant oblast to organise measures for the accident-free operation of critical infrastructure facilities and the protection of the population and territories under martial law and during the recovery period to eliminate the consequences of military operations", which included, among other things, practising response procedures for the possible use of weapons of mass destruction (nuclear weapons). Participation was also taken in a command-staff exercise with civil-protection command bodies of the unified state civil-protection system on responding to possible use of chemical weapons, in Lviv. Ministry of Internal Affairs (MIA): Representatives of the SES central apparatus and the National Police took part on 18 March 2026 in a tabletop simulation exercise, "Response to a Chemical Accident", at the Bogomolets National Medical University. The tabletop simulation was devoted to the actions and interagency coordination of emergency services in responding to a hypothetical emergency. State Border Guard Service personnel took part in 13 training events on radiation, chemical and biological protection, and in "training of trainers" courses. Administration of the State Border Guard Service of Ukraine State Border Guard Service personnel took part in 13 training events on radiation, chemical and biological (RCB) protection, including: a course on responding to a radiological/nuclear incident; a training session on "Detecting radiation using backpack-mounted detection systems, including on passenger trains"; command-staff exercises on RCBN (radiological, chemical, biological, nuclear) crimes in Ukraine and on responding to possible use of chemical weapons or their components; an educational seminar for discussing and exchanging practical experience on innovations in organising the RCBN protection training process; "training of trainers" courses on "Detecting radioactive and nuclear materials at controlled border areas, checkpoints and roadblocks located on transit routes toward EU countries" and "Countering the proliferation of weapons of mass destruction"; a training seminar for the 2nd cohort of the World Laboratory Leadership Programme; a national training on "Strengthening biosafety and biosecurity measures at state border crossing points and improving interagency coordination"; practical field training on responding to radiation, chemical, biological and nuclear incidents; an international basic course on responding to chemical emergencies; a training on "Countering illicit trafficking of radioactive and nuclear materials"; and a training course on the use of dosimetry equipment and the conduct of individual dosimetric monitoring of personnel using licensed software. |  |  |  |  |
| 43. Creating conditions for the prevention of infectious and non-communicable diseases, and ensuring population immunisation in territorial communities in accordance with the Schedule of Preventive Vaccinations | 1) Organising and implementing immunoprophylaxis measures, including vaccination of the population in accordance with Ukraine's Schedule of Preventive Vaccinations | 2025-2027 | vaccination of at least 95 percent of the target population group, and at least 80 percent of target population groups who missed scheduled immunisation in previous years due to age |  | Vinnytsia oblast In 2025, the full primary vaccination series against diphtheria, pertussis and tetanus was administered to all planned first-year-of-life children (6,609 people); 94.3% of children aged 18 months received revaccination. Among 6-year-olds, 83.1% were vaccinated against diphtheria and tetanus; among 16-year-olds, 88.2% received revaccination; and 100% of adults were covered. Against poliomyelitis: 100% at age 1 year, 95.8% at 18 months, 91.7% at 6 years, and 88.9% at 14 years. Against measles, mumps and rubella, the first dose was given to 99.2% of 1-year-olds and, at age 6, to 90.9%. Against Haemophilus influenzae infection, 86.0% of 1-year-olds were vaccinated. 99.2% of children under 1 year received the required three doses against hepatitis B. 91.8% of children were vaccinated against tuberculosis. Dnipropetrovsk oblast BCG-1 (Bacillus Calmette–Guérin))— 84.5%; against poliomyelitis, Polio-3 by age 1 — 93.4%, Polio-4 at 18 months — 92.9%, Polio-5 at 6 years — 97.8%, Polio-6 at 14 years — 94.7%; against pertussis, diphtheria and tetanus, DTP-3 by age 1 — 95.8%, DTP-4 at 18 months — 92.9%; against diphtheria and tetanus, DT at 6 years — 86.1%, Td at 16 years — 89.3%, Td for adults — 83.6%; against measles, mumps and rubella, MMR-1 at age 1 — 95.4%, MMR-2 at age 6 — 93.7%; against Haemophilus influenzae, Hib-3 at age 1 — 89.4%; against hepatitis B, HepB-3 by age 1 — 88.9%. Donetsk oblast For 2025, Donetsk oblast's vaccination rate was below the national average for only 4 indicators: BCG by age 1 — 72.3% (national 74.4%); polio by age 1 — 66.6% (national 79.6%); DTP by age 1 — 66.3% (national 79.6%); DTP by 18 months — 75.5% (national 78.0%). All other indicators are at or significantly above national levels. Zhytomyr oblast The average scheduled-vaccination coverage rate for the oblast is 96.1%; the average coverage rate for vaccinations administered outside the schedule is 61%. Zakarpattia oblast Overall vaccination coverage in the region is 86.5%: 86.0% received vaccination on schedule, and 87.0% received revaccination, of those planned. At the same time, immunisation coverage among target groups reaches the recommended 95% threshold only for vaccinating 1-year-olds against measles, mumps and rubella (95.0%); vaccination of at least 80% of target groups who missed scheduled immunisation in previous years due to age was achieved across all indicators. Zaporizhzhia oblast To counter the spread of vaccine-preventable infections, immunoprophylaxis measures are carried out on an ongoing basis. Based on 2025 results, target immunisation indicators for the government-controlled population were achieved across all age groups and antigens. Under the Schedule of Preventive Vaccinations, coverage reached: poliomyelitis — 97.4% of children; diphtheria, pertussis and tetanus — 95.6% of children; Haemophilus influenzae infection — 96.8% of children; measles, mumps and rubella — 97% of children; hepatitis B — 97.9% of children. All healthcare institutions are 100% supplied with the necessary immunobiological preparations for vaccination, both from carryover stock from previous years and from centralised supply in 2025 funded by the state budget and humanitarian aid. Ivano-Frankivsk oblast Immunoprophylaxis indicators for the oblast in 2025: BCG-1 — 92.6%; Polio-3 — 90.3%; Polio-4 — 91.0%; Polio-5 — 93.1%; Polio-6 — 93.8%; DTP-3 by age 1 — 93.9%; DTP-4 (18 mo.) — 96.1%; DT (6 yrs) — 85.1%; Td (16 yrs) — 91.1%; Td (adults) — 99.8%; Hib-3 — 86.0%; MMR-1 — 96.4%; MMR-2 (6 yrs) — 89.8%; hepatitis B-3 — 84.6%. Immunisation work continues in line with planned vaccination volumes for all age categories. Kyiv oblast For 2025, vaccination coverage reached 60.7% of the child population and 41.1% of the adult population (compared to national figures of 59.9% for children and 50.6% for adults). Kirovohrad oblast The oblast achieved vaccination of at least 95% of the target population group and at least 80% of target groups who missed scheduled immunisation in previous years due to age. Luhansk oblast The annual planned coverage of preventive vaccinations against diphtheria and tetanus for the adult population and 16-year-old adolescents reached 100%. Other scheduled vaccinations for children were not planned for 2025, though routine vaccination of children was resumed during the year (596 vaccinations administered). Of 9 primary care centres in the oblast with agreements with the National Health Service of Ukraine (NHSU), 8 provided vaccinations in 2025. As of early 2026, all 9 NHSU-contracted primary care centres have resumed vaccination, representing 100% coverage. Monthly monitoring of immunoprophylaxis status is conducted. Lviv oblast Immunoprophylaxis coverage under Ukraine's Schedule of Preventive Vaccinations by age, across prevention of ten infectious diseases, was 87.10% in 2025. The matter of implementing measures to develop immunoprophylaxis and protect the population from vaccine-preventable infectious diseases was considered at a meeting of the Oblast Commission on Technogenic-Ecological Safety and Emergency Situations on 22 March 2023, resulting in approval of the Strategy for Developing Immunoprophylaxis and Protecting the Population from Vaccine-Preventable Infectious Diseases for 2023–2025 in Lviv Oblast, and the corresponding action plan. Mykolaiv oblast In 2025, 155,989 vaccinations were administered under the schedule. In addition to schedule-based vaccinations, there are recommended vaccines — against influenza, hepatitis A, rotavirus, meningococcal and pneumococcal infections, chickenpox, tick-borne encephalitis, and HPV — which residents purchase at their own expense. During 2025, 3,724 "non-mandatory" vaccinations were administered, most commonly against influenza. During 2025, 3,107 people sought antirabies care for animal bites at healthcare institutions in the oblast, and antirabies vaccination was prescribed to 1,609 people. Odesa oblast In Odesa oblast, vaccination is carried out under the National Schedule of Preventive Vaccinations for target population groups who did not receive scheduled vaccinations in previous years due to age. Poltava oblast The scheduled-vaccination completion rate in the oblast was 94.4%. Rivne oblas In 2025, 95.7% of the oblast's target population group was vaccinated, and 87.5% of target groups who missed scheduled immunisation in previous years due to age. Sumy oblast The population immunisation rate for the reporting year was 94.8%, including: BCG-1 — 94.4%; Polio-3 — 92%; Polio-4 — 92%; Polio-5 — 94.4%; Polio-6 — 97.7%; DTP-3 — 94.1%; DTP-4 — 94.2%; DT — 93%; Td (16 years) — 97.7%; Td (adults) — 95.8%. Ternopil oblast During the reporting period, immunoprophylaxis measures were organised and implemented, including population vaccination under Ukraine's Schedule of Preventive Vaccinations. Healthcare institutions carried out scheduled and supplementary vaccinations for children and adults, ensured proper storage and transport of vaccines in compliance with cold-chain requirements, and conducted information and awareness work on the importance of vaccination for disease prevention. Kharkiv oblast According to the Public Health Centre of the Ministry of Health of Ukraine, as of 1 January 2026, across 31 monitored vaccination-coverage indicators for Kharkiv oblast: 13 indicators were recorded at 95.1%–99.1%, exceeding corresponding national figures; 10 indicators — at 82.3%–92.5%, also exceeding national figures; 2 indicators — 93.6% and 92.5% — approximately matching national averages (93.5% and 92.9% respectively); and 6 indicators somewhat lower than national figures — 42.2%–92.4% (versus 49.1%–94.6% nationally). Khmelnytskyi oblast Last year, the oblast ensured vaccination in accordance with the Schedule of Preventive Vaccinations. The average completion rate for scheduled vaccinations was 82.9%. Immunoprophylaxis measures included vaccination: against poliomyelitis among children under 1 year — 88% (national figure 85.2%), at 18 months — 87.4% (83.6%), at 6 years — 77.4% (82.6%), at 14 years — 74% (79%); against pertussis, diphtheria and tetanus at under 1 year — 88.6% (86.6%), at 18 months — 90.8% (84.7%); against diphtheria and tetanus at 6 years — 72.8% (75.4%), at 16 years — 76.2% (80%), and among adults — 70% (83.3%); against measles, mumps and rubella (MMR), first dose coverage among 1-year-olds was 91.3% (88.8%), second dose at age 6 was 87.5% (84.2%); against hepatitis B-3, children under 1 — 86.4% (83.1%); against tuberculosis, under 1 — 84.3% (80.7%); against Haemophilus influenzae among 1-year-olds — 87.1% (81.8%). Cherkasy oblast During 2025, scheduled vaccination in Cherkasy oblast was carried out by 88 healthcare institutions holding NHSU agreements and providing vaccination services using centrally supplied immunobiological preparations. Using the "UkrVak-08" system, a ranking of primary care institutions in the oblast by vaccination-coverage results was compiled, based on the number of registered patients. To achieve strategic immunoprophylaxis goals, active work was carried out through mobile vaccination sessions, involving staff of the Cherkasy Regional Centre for Disease Control and Prevention and medical personnel of healthcare institutions in the oblast's territorial communities. In 2025, 54 trips were made to 77 settlements in the oblast, using two specialised buses ("vaccine buses"), during which 2,550 vaccinations were administered to adults (1,278 people) and 369 to children (209 people of various ages). During 2025, information and communication work on immunoprophylaxis was carried out — participation in 8 briefings at the Cherkasy Oblast Military Administration, 6 TV segments, 4 radio appearances, 41 articles in the media, 345 online publications, and distribution of 19,300 copies of printed materials received from partner organisations, the Ministry of Health of Ukraine, and the Public Health Centre of the Ministry of Health of Ukraine. In 2025, compared to 2024, Cherkasy oblast maintained an upward trend in vaccination-coverage indicators, except for coverage of children against Haemophilus influenzae type B, where a decline was recorded in the "under 1 year" and "1 year" age categories. 5 indicators in the oblast reached and exceeded 95%: polio vaccination at 18 months, 6 years and 14 years, hepatitis B vaccination in children "under 1 year", and MMR vaccination at "1 year". Other indicators did not reach strategic targets, although the oblast was fully supplied with immunobiological preparations. Chernivtsi oblast Target-group vaccination rates: children under 1 year — polio 92.55%, DTP 93.9%, hepatitis B 91.1%; children aged 1 year — MMR 93.3%, Haemophilus influenzae 97.3%; children aged 18 months — polio 90.9%, DTP 92.0%; children aged 6 years — MMR 94.1%, polio 93.2%, DTP 82.8%. Target groups who missed scheduled immunisation in previous years due to age were vaccinated at rates ranging from 50% to 82.2%. Chernihiv oblast Chernihiv oblast ensures an uninterrupted process of routine immunisation at all primary care institutions using vaccines supplied by the Ministry of Health of Ukraine. To achieve the target coverage rate of 95%, primary care physicians systematically monitor and catch up on missed vaccinations. During 2025, medical personnel received professional-development training on cold-chain compliance and measles prevention. To inform the population, information on vaccine availability is regularly updated on healthcare-institution resources, and the National Immunisation Portal is promoted. | Zaporizhzhia oblast 6227,1 Luhansk oblast 8,9 | Luhansk oblast 0,9 | Zaporizhzhia oblast 438,6 Luhansk oblast 276,0 | Luhansk oblast It is not possible to reliably assess the overall vaccination coverage rate for the population of Luhansk oblast, since the registered population is dispersed across other regions of the country and abroad. Primary care centres therefore plan vaccination for the registered population that can actually reach a vaccination point. To increase vaccination coverage, during 2025 healthcare institutions carried out 17 mobile-team outreach trips for population vaccination, vaccinating 137 people. Mobile-team outreach trips for 2026 are planned at humanitarian hubs, shelters, support centres, places of temporary residence for IDPs, and healthcare institutions across Luhansk oblast. Family physicians inform the entire registered population of vaccination timing by age and provide guidance on obtaining vaccinations. |
|  | 2) Ensuring supply of medical immunobiological preparations to healthcare facilities | 2025-2027 | 100 percent of healthcare facilities supplied with medical immunobiological preparations | Completed | Ministry of Health In 2025, the supply of medical immunobiological preparations (vaccines) to healthcare facilities in Ukraine was carried out centrally, through procurement funded from the state budget, aimed at implementing the Immunization Development Strategy. The priority is the uninterrupted supply of vaccines in accordance with the Preventive Vaccination Schedule, ensuring a stable stock level, and modernizing logistics. As part of the 2025 state-budget-funded procurement, the following types of vaccines were contracted: 1. Diphtheria and tetanus toxoid with reduced antigen content (Td) / TETADIF, suspension for injection, 0.5 ml (1 dose); 5 ml vials (10 doses), manufacturer — BB-NCIPD Ltd., Bulgaria. Contracted quantity: 2,397,500 doses. Delivered to the central warehouse: 1,000,000 doses on 26.08.2025, 1,397,500 doses on 26.02.2026. 2. Vaccine for tuberculosis prevention / BCG VACCINE "AJ VACCINES", powder and solvent for solution for injection, suspension; 1 vial of powder and 1 vial of solvent, manufacturer — AJ Vaccines A/S, Denmark. Contracted quantity: 402,400 doses. Delivered to the central warehouse: 189,480 doses on 09.01.2026. Under the terms of the contract, a further 106,000 doses are due by 26.05.2026, and 106,000 doses by 28.08.2026. 3. Vaccine for the prevention of measles, mumps and rubella. Quantity: 360,000 doses by 31.07.2026. 4. Rabies vaccine. Total quantity: 288,205 doses. Delivered: 28,100 doses on 27.06.2025, 85,150 doses on 29.12.2025, 45,300 doses on 27.03.2026 (incoming quality control in progress). Under the terms of the contracts, 129,655 doses are due by 30.06.2026. | 459 642,7 | - | - | - |
| 44.Creation of a Unified Portal of Vacant Positions in State and Municipal Healthcare Facilities | ensuring that information on vacancies is posted on the Unified Web Portal of Vacant Positions in State and Municipal Healthcare Facilities | 2027 | recruitment for vacant positions conducted through the Unified Web Portal of Vacant Positions in State and Municipal Healthcare Facilities | Ongoing | Vinnytsia Oblast Posting of information on vacant positions on the Unified Web Portal in state and municipal healthcare facilities has been ensured. Electronic distribution (e-rozpodil) of graduates of higher education institutions has been carried out. Donetsk Oblast Announcements of vacant positions are published within 10 working days of the position being created or vacated. Ivano-Frankivsk Oblast Maintenance and systematic updating of the Unified Web Portal of Vacant Positions in municipal healthcare facilities has been ensured. Recruitment to fill vacant positions takes into account data from the Unified Portal. Kyiv Oblast Recruitment for vacant positions is being conducted through the Unified Web Portal of Vacant Positions in State and Municipal Healthcare Facilities. Kirovohrad Oblast 75 municipally owned healthcare facilities operate in the oblast; they have registered on the Unified Portal of Vacant Positions, ensured that information on available vacancies is kept up to date, and recruitment for vacant positions is under way. Lviv Oblast All healthcare facilities under the authority of the health department operate through the Unified Web Portal of Vacant Positions in State and Municipal Healthcare Facilities. Poltava Oblast Recruitment for vacant positions is being conducted through the Unified Web Portal of Vacant Positions. Rivne Oblast 100 percent of healthcare facilities in the oblast conduct recruitment for vacant positions through the Unified Web Portal of Vacant Positions in State and Municipal Healthcare Facilities. Kharkiv Oblast Recruitment for vacant positions has been conducted through the Unified Web Portal of Vacant Positions in State and Municipal Healthcare Facilities. Khmelnytskyi Oblast All healthcare facilities in the oblast are registered on the Unified Web Portal of Vacant Positions in State and Municipal Healthcare Facilities. Facility heads have been informed of the need to comply with recruitment requirements using the web portal's functionality. In addition, in 2025 an electronic rating-based system for distribution to internships (internatura) started operating for the first time, under which 178 positions for the oblast's intern physicians were registered. Chernivtsi Oblast Healthcare facilities in the oblast ensure that information on vacancies is posted on the Unified Web Portal of Vacant Positions in State and Municipal Healthcare Facilities. Recruitment for vacant positions in the oblast's municipal healthcare facilities is also carried out using the information and communication system "Unified Web Portal of Vacant Positions in State and Municipal Healthcare Facilities." 148 vacancies have been published on the web portal. |  |  |  |  |
| 45.Ensuring access to necessary medical services, medicinal products and medical devices under the Medical Guarantees Program | 1)Ensuring implementation of the "Mobile Pharmacy Points" project | 2025-2027 | at least 15 regions of Ukraine engaged in project implementation |  | Vinnytsia Oblast In order to ensure access for residents of remote rural settlements in the oblast where no stationary pharmacy establishments exist, to medicinal products and medical devices — including under the "Affordable Medicines" program — the oblast military administration signed a "Memorandum on Cooperation in Healthcare" in 2025 with LLC "Farmatsiia Vinnychchyny" concerning the establishment and commissioning of mobile pharmacy points across the oblast. In 2025, with the assistance of the State Enterprise "Ukrvaktsyna" of the Ministry of Health of Ukraine, a mobile pharmacy point route began operating for the villages of the Ulaniv community in Vinnytsia Oblast. Dnipropetrovsk Oblast In 2025, the private enterprise "Ekspres-Apteka," part of the "ANC" pharmacy network, launched a mobile pharmacy service in Dnipropetrovsk Oblast. Trips are made twice a month to the settlements of the Sviatovasylivka community, Dnipro district. Zhytomyr Oblast The project has been implemented in 53 villages across 3 communities as part of the "Innovations to Overcome HIV" project, supported by the U.S. Agency for International Development (USAID). Zakarpattia Oblast One "Mobile Pharmacy Point" No. 1 of Pharmacy No. 11, LLC "FARM SIM'IA," has been engaged in project implementation. Zaporizhzhia Oblast Within the framework of the "Mobile Pharmacy Points" project, 3 mobile pharmacy points (hereinafter — MPPs) operate in the government-controlled territory of the oblast, with routes covering 43 settlements in Zaporizhzhia district. The MPPs provide the ability to purchase medicinal products, including those subject to reimbursement under the "Affordable Medicines" program. Ivano-Frankivsk Oblast 3 mobile pharmacies operate in the oblast, selling medicines in Verkhovyna, Kalush, and Kolomyia districts along pre-agreed routes. Kirovohrad Oblast All 49 territorial communities in the oblast are engaged in the "Mobile Pharmacy Points" project. Luhansk Oblast In accordance with the List of Territories Where Hostilities Are (Were) Conducted or Which Are Temporarily Occupied by the Russian Federation, approved by Order No. 376 of the Ministry for Communities, Territories and Infrastructure Development dated 28.02.2025, most settlements in Luhansk Oblast are currently under occupation, while active hostilities continue in the rest of the territory. The infrastructure of settlements located in the active hostilities zone has been destroyed, access to these territories is restricted, and the civilian population is absent. In the government-controlled territory, 12 primary care healthcare facilities have resumed operations, issuing prescriptions under the "Affordable Medicines" reimbursement program. In 2025, 27,472 prescriptions were issued under this program. The commercial activity of pharmacy networks, including the delivery and sale of medicines under the "Mobile Pharmacy" project, will be resumed after the de-occupation of the oblast's territory. Lviv Oblast The mobile pharmacy point of the Municipal Enterprise of Lviv Oblast Council "Interhospital Pharmacy No. 272" carries out an important social mission, supplying medicinal products to residents of remote settlements in Lviv Oblast. The pharmacy point serves 8 routes in Sambir district (9 settlements) and Drohobych district (17 settlements), with a frequency of twice a month. Over the entire period, more than 100 trips have been made. In 2025, 1,231 prescriptions were dispensed under the "Affordable Medicines" program, averaging 127 prescriptions per month. This list includes cardiovascular medicines, medicines for treating bronchial asthma, medicines for treating type II diabetes, and others. In addition to this program, the pharmacy supplies the population with prescription and over-the-counter medicines at the population's own expense, as well as medicines compounded on-site with individual ingredients and prices. Mykolaiv Oblast Mykolaiv Oblast has joined the implementation of the "Mobile Pharmacy Points" project. Two mobile pharmacy points operate in the oblast, serving 9 territorial communities covering 54 rural settlements. This makes it possible to ensure access for residents of remote settlements to necessary medicinal products. Transportation of medicinal products is carried out in compliance with the established temperature regime, using specialized equipment — refrigerators and cabinets for storing medicines. Residents can obtain information on the schedules and arrival times of mobile pharmacy points from family doctors, as well as from local self-government bodies, with which the relevant routes are agreed. Oversight of the activities of mobile pharmacies is entrusted to the State Service of Ukraine on Medicines and Drugs Control. Odesa Oblast Mobile pharmacies operate along 4 approved routes. Poltava Oblast A pilot project on the operation of mobile pharmacy points, run jointly with "Ukrposhta," has been introduced in all communities of the oblast. Rivne Oblast Under the "Mobile Pharmacy Point" project, the "Podorozhnyk" pharmacy network serves 153 remote villages, while individual entrepreneur A.M. Kostiuchko serves 5 remote villages. Sumy Oblast In 2025, 2 mobile pharmacy points began operating (Romny and Konotop districts). Ternopil Oblast Two mobile pharmacy points (MPPs) operate in the oblast: LLC "Farmastor," which serves 24 settlements in Ternopil district, and LLC "Iron West" (20 settlements in Kremenets district). Kharkiv Oblast The "Mobile Pharmacy Points" project, launched in the oblast in March 2025, supplies medicines to more than 100 remote and de-occupied settlements that lack stationary pharmacies. Specially equipped vehicles of the Municipal Enterprise "Oblast Pharmacy Warehouse" deliver medicines to the local population, including under the "Affordable Medicines" program. Khmelnytskyi Oblast Implementation of the "Mobile Pharmacy Points" project has been ensured in the oblast, in particular: - settlements with the least provision of pharmacy establishments in rural areas have been identified; - corresponding mobile pharmacy point routes have been developed and approved; - a mobile pharmacy point schedule has been drawn up and service to remote settlements of Shepetivka district has been ensured. Cherkasy Oblast The Cherkasy Oblast Municipal Enterprise "Farmatsiia" operates in the oblast. Through mobile pharmacy points, the Cherkasy Oblast Municipal Enterprise "Farmatsiia" dispenses both prescription and over-the-counter medicinal products, including medicinal products subject to reimbursement under the state guarantee program for medical care of the population. All prescription medicines are dispensed exclusively against a paper or electronic prescription. As of 31.12.2025, the Cherkasy Oblast Municipal Enterprise "Farmatsiia" had approved 25 routes for its 2 mobile pharmacy points, along which retail medicine trade is carried out; other routes are in development. Chernivtsi Oblast Since September 2024, a Mobile Pharmacy Point established by PE "Harmoniia-2000" has been operating in Chernivtsi Oblast. Trips along Route No. 1 are made on the second and fourth Wednesday and the second and fourth Thursday of each month. The main range of medicines sold at the mobile pharmacies includes medicines for cardiovascular diseases, type 2 diabetes, seasonal illnesses, and non-steroidal anti-inflammatory drugs. Medicinal products are stored and transported in specially equipped refrigerators and cabinets, with due observance of the required temperature regime to ensure the safety and effectiveness of the medicinal products. The "Harmoniia 2000" pharmacy network has joined the "National Cashback" program. In 2025, medicinal products worth UAH 483,519 were sold through the mobile pharmacy points, of which UAH 193,407 was under the "Affordable Medicines" reimbursement program. Chernihiv Oblast To supply residents of remote and affected communities in Chernihiv Oblast with medicines (including under the "Affordable Medicines" program), the operation of mobile pharmacy points (MPPs) has been organized. In 2025, two specialized vehicles were equipped for the Municipal Enterprise "Liky Chernihivshchyny," which made 90 trips to 76 settlements, serving 7,699 citizens. In addition, an MPP operated by the State Enterprise "Ukrvaktsyna" of the Ministry of Health of Ukraine additionally operates in the de-occupied territories of the oblast. Prompt informing of the population about routes and schedules is carried out through dedicated Telegram and Viber channels, "Mobile Pharmacy 'TUT'." |  | Lviv Oblast 350,0 |  | Donetsk Oblast There are no mobile pharmacy points due to the security situation. Luhansk Oblast Implementation of the measure will be possible after the de-occupation of the oblast's territories, the cessation of active hostilities, and the conduct of security and stabilization measures. |
|  | 2) Ensuring the delivery of medicinal products to the population by postal operators, including under the "Affordable Medicines"(“Доступні ліки”) program | 2025-2027 | an increase of at least 5 percent in the number of orders for medicinal products through postal operators ensured |  | Vinnytsia Oblast On the issue of improving access for residents of remote rural settlements in the oblast to medicinal products, including under the "Affordable Medicines" program, the activity of the oblast military administration is aimed at increasing the activity of primary-level healthcare facilities in cooperation with JSC "Ukrposhta" to ensure delivery of medicinal products under prescriptions issued by family doctors to remote rural settlements of the oblast through JSC "Ukrposhta" branches. During 2025, across the oblast as a whole, 6,155 orders for medicinal products were made under the "Ukrposhta. Pharmacy" project. Work to ensure the accessibility of medicinal products and medical devices, including under the "Affordable Medicines" program, for residents of remote rural settlements in the oblast is ongoing. Dnipropetrovsk Oblast As part of the state "Affordable Medicines" program, JSC "Ukrposhta" implements the "Ukrposhta. Pharmacy" project in Dnipropetrovsk Oblast, under which free delivery of medicines to residents of territorial communities is carried out. Since the project's launch, 6,228 orders have been processed, of which 3,588 were in 2025. Donetsk Oblast During 2025, the number of orders in the oblast made through JSC "Ukrposhta" for rural areas amounted to 141, including 35 orders for medicinal products under the "Affordable Medicines" program. Zhytomyr Oblast In 2025, 1,439 orders for medicinal products were made through "Ukrposhta." Zakarpattia Oblast In some districts of the oblast, work has begun on the delivery of medicinal products to the population by postal operators, including under the "Affordable Medicines" program, but it remains insufficient. Zaporizhzhia Oblast Within the framework of the "Ukrposhta.Pharmacy" project, free delivery of medicines (including under the "Affordable Medicines" program) to JSC "Ukrposhta" branches has been ensured in the government-controlled territory of the oblast, in particular in settlements lacking pharmacies. The oblast state administration, local self-government bodies, and general practitioners/family doctors continuously inform the population about the possibilities of the "Ukrposhta.Pharmacy" project. Relevant informational materials have also been placed on stands in healthcare facilities and at points where medical care is provided. Ivano-Frankivsk Oblast 47 mobile "Ukrposhta" branches operate (mobile postal points serving settlements from vehicles or mobile facilities). The "Ukrposhta Pharmacy" project has been launched, implemented with the assistance of the Ministry of Health of Ukraine, to develop medicine delivery and sale services in the oblast. Kirovohrad Oblast 12 primary healthcare centers, in cooperation with postal operators, deliver medicinal products to the oblast's population. All 4 districts of the oblast are covered. Lviv Oblast The "Ukrposhta. Pharmacy" medicine delivery program is actively operating in the oblast. As of 31.12.2025, more than 4,000 prescriptions have been issued, of which 3,231 were under the "Affordable Medicines" program. Mykolaiv Oblast The "Ukrposhta. Pharmacy" project is being implemented in Mykolaiv Oblast, providing for delivery of medicinal products through stationary and mobile branches of JSC "Ukrposhta." The service ensures access for the population, including residents of remote and front-line settlements, to necessary medicinal products. The service can also be used to obtain, free of charge or with partial co-payment, medicines for treating the most common chronic diseases under the "Affordable Medicines" program. Odesa Oblast Work is under way to increase the number of orders. Poltava Oblast 33 mobile pharmacy point trips were carried out; under the Government's "Affordable Medicines" program, 2,395 prescriptions were issued and medicines were dispensed against 2,121 prescriptions. Rivne Oblast Under the "Affordable Medicines" program: - 560 thousand prescriptions were issued for 760 medicinal products; - 492.3 thousand prescriptions were redeemed. Orders for medicinal products are placed through the "Ukrposhta" postal operator. Sumy Oblast 4,506 units of medicinal products were sent through postal operators, which is 11.4% more than in 2024. Ternopil Oblast Since October 2024, the "Ukrposhta. Pharmacy" project has been implemented, providing delivery of medicines to remote settlements and support for patients when placing orders; a total of 4,387 medicinal products have been delivered. Kharkiv Oblast According to data from the Ministry of Health of Ukraine on the implementation of key government healthcare initiatives, the number of orders for medicinal products through Ukrposhta is 6,740, which allowed the oblast to rank 1st among Ukraine's regions in 2025. Khmelnytskyi Oblast Implementation of the "Affordable Medicines" program has been ensured, including informing the population about the possibility of ordering medicinal products through postal operators. Last year, about 800 residents of the oblast used the service of ordering and receiving medicinal products through JSC "Ukrposhta." Cherkasy Oblast As of 31.12.2025, doctors at healthcare facilities in the oblast had issued a total of 3,483,811 electronic prescriptions for medicinal products under the Government's "Affordable Medicines" reimbursement program, of which 3,022,578 were redeemed by pharmacy establishments. In March 2025, an online meeting was held with representatives of the Cherkasy Oblast State Administration's Healthcare Department and Ukrposhta regarding the "Ukrposhta. Pharmacy" project, which ensures citizens' access to medicinal products regardless of place of residence. According to operational information, in 2025 there were no orders for medicinal products by residents of Cherkasy Oblast through the "Ukrposhta. Pharmacy" online service or by phone. Chernivtsi Oblast In 2025, the Ministry of Health launched a joint project with Ukrposhta. Ukrainians living in remote villages where there are no pharmacies and access to medicines is limited can order them through Ukrposhta's contact center. Delivery is free of charge. Medicines can be ordered by phone, and the postal operator will deliver them free of charge through stationary or mobile branches. The service also offers medicines under the "Affordable Medicines" program, the cost of which is partially or fully compensated by the state. In Chernivtsi Oblast in 2025, [data was provided] through the "Ukrposhta. Pharmacy" service. Cherkasy Oblast Delivery of medicines is carried out by the postal operators "Ukrposhta" and "Nova Poshta," often in partnership with pharmacy networks (for example, Liki24, Apteka ANC). "Ukrposhta" offers free delivery under the "Affordable Medicines" program (by prescription) through the hotline 0 800 300 545, while "Nova Poshta" offers courier delivery and delivery to branches. Patients can receive cardiovascular, diabetes (type 2), and asthma medicines by prescription under the "Affordable Medicines" program. | Rivne Oblast 237 000,0 |  |  | Donetsk Oblast The organization of delivery is affected by logistical and security factors related to martial law and the specifics of infrastructure operation in certain communities of the region. |
|  | 3) Ensuring public access to information on the list and cost of medical care services that may be provided for payment by legal entities and individuals | 2025-2027 | MOH orders issued | Ongoing | Vinnytsia Oblast In order to ensure transparency and inform citizens, the oblast military administration facilitates access to information on the list and cost of medical services that may be provided by healthcare facilities on a paid basis (by legal entities and individuals). This information is published directly by healthcare facilities on their official websites or information stands in accordance with the requirements of current legislation. Dnipropetrovsk Oblast The list of medical care services for the population that may be provided for payment by legal entities and individuals, and their cost, are posted by all healthcare facilities of the oblast on information stands inside the facility and/or published on the website (if available). Donetsk Oblast The measure is implemented within the framework of medical services that may be provided for payment by legal entities and individuals within the limits of the law. In 10% of facilities there is access to information on the availability and cost of paid medical services. The relevant information is posted on stands in outpatient departments, primary care centers, administrative units, registration desks, as well as on the official websites of healthcare facilities. Zhytomyr Oblast The number of healthcare facilities providing information to the population has grown by 10%. Zakarpattia Oblast On the official websites of cluster-level and supra-cluster-level healthcare facilities, informing of the population regarding the list and cost of services provided for payment by legal entities and individuals has been ensured. Zaporizhzhia Oblast Currently, paid medical services are provided to the population by 23 municipally owned healthcare facilities located in the government-controlled territory of the oblast. Information on the list of medical services and their cost is provided by healthcare facilities on an ongoing basis by posting materials on their own official websites, social media pages, and information boards and stands located at these facilities. Ivano-Frankivsk Oblast Information on the list and cost of medical care services that may be provided for payment by legal entities and individuals is published and systematically updated on facilities' information stands. Kirovohrad Oblast Medical staff at healthcare facilities providing paid services conduct broad informing of the population regarding the list and cost of medical care services provided for payment by legal entities and individuals. Luhansk Oblast Healthcare facilities post information on stands inside hospital premises, as well as on social media pages. Lviv Oblast The list of medical care services for the population that may be provided for payment by legal entities and individuals, and their cost, are published on the websites of healthcare facilities and posted on information stands inside healthcare facilities. Mykolaiv Oblast 100% of healthcare facilities in the oblast ensure that the population is informed about the list and cost of medical care services that may be provided on a paid basis. The relevant information is posted in places accessible to patients within facility premises, as well as on the official websites or informational resources of medical institutions. Patients are able to freely review the list of services, their cost, and the terms under which these services are provided. Odesa Oblast Facilities that provide paid services ensure that the population is informed. 100% of facilities provide paid services. Poltava Oblast All medical facilities ensure that the population is informed about the list and cost of services. Rivne Oblast A 10 percent increase has been ensured in the number of healthcare facilities that inform the population, including regarding the provision of paid services. The relevant information is posted on official websites in 41 facilities and on information stands (notice boards) in 56 facilities. Sumy Oblast The list and cost of medical care services provided for payment by legal entities and individuals is published on the websites of healthcare facilities in the oblast and posted on information boards in facilities. Ternopil Oblast Paid services are being introduced in healthcare facilities of the oblast; information about them is available on the official resources of healthcare facilities and on the relevant information stands. Kharkiv Oblast Within the framework of the medical guarantees program, in accordance with contracts concluded with the National Health Service of Ukraine (NHSU), the population receives free medical care. Information on the list and cost of medical services that are not financed under the state guarantee program for medical care of the population is posted on the websites and information stands of all healthcare facilities in the sectoral network. Khmelnytskyi Oblast In all 30 facilities of the capable network for inpatient specialized medical care, up-to-date information on the list of paid medical services and their cost has been posted on their own websites and on information stands in places accessible to visitors, etc. Chernivtsi Oblast Work is under way in the healthcare facilities of the oblast to ensure open public access to information on the list and cost of medical services that may be provided on a paid basis. This information is posted and updated on the official websites of facilities, on information stands within medical institutions' premises, and is also brought to patients' attention through other available communication channels. Chernihiv Oblast The provision of paid medical services in the healthcare facilities of the oblast is carried out in accordance with the requirements of Resolution of the Cabinet of Ministers of Ukraine No. 781 dated 05.07.2024, "Certain Issues of Providing Medical Care Services to the Population for Payment by Legal Entities and Individuals." To uphold the principles of openness, up-to-date lists of services and approved tariffs are published on the official websites of facilities, as well as on information stands in publicly accessible places. |  |  |  |  |
|  | 4) Approval of lists of medicinal products and medical devices subject to reimbursement under the state guarantee program for medical care of the population | 2025-2027 | MOH orders issued | ongoing on a continuous basis | Ministry of Health Order of the Ministry of Health No. 1409 dated 10.09.2025, "On Approval of the Lists of Medicinal Products and Medical Devices Subject to Reimbursement under the State Guarantee Program for Medical Care of the Population, as of 28 August 2025," included 705 items of medicinal products (including insulins and combination preparations) and 42 medical devices (IVD glucose test strips (in vitro diagnostics)). The list of medicinal products contains: 595 medicinal products, 38 insulin preparations, and 30 combination medicinal products. The Ministry of Health issued Order No. 324 dated 16.03.2026, "On Approval of the Lists of Medicinal Products and Medical Devices Subject to Reimbursement under the State Guarantee Program for Medical Care of the Population, as of 05 March 2026." This order takes effect on 31 March 2026, and Order of the Ministry of Health No. 1409 dated 10 September 2025 becomes void. In the updated list, the reimbursement program is expanded to include new medicines for cardiovascular disease, diabetes, and respiratory diseases. |  |  |  |  |
| 46. Organizing a capable network of cluster-level and supra-cluster-level healthcare facilities, including through the creation of rehabilitation departments | 1) Creation of rehabilitation departments in cluster-level healthcare facilities in accordance with population needs for medical services, taking into account demographic and migration processes | 2025-2027 | rehabilitation departments created in 100 percent of cluster-level healthcare facilities | Ongoing | Vinnytsia Oblast During 2025, the number of facilities providing inpatient rehabilitation care to adults and children increased from 19 to 24 municipal healthcare facilities: 4 supra-cluster facilities, 5 cluster facilities, 6 general hospitals, and 9 facilities not included in the capable network. The number of facilities providing outpatient rehabilitation care increased from 14 to 19 facilities: 3 supra-cluster facilities, 3 cluster facilities, and 6 general hospitals. In 2025, according to NHSU data, 23,192 rehabilitation services were provided: Package No. 53 "Rehabilitation Care for Adults and Children in Inpatient Settings" — 15,129 services; Package No. 25 "Medical Rehabilitation of Infants Born Prematurely and/or Ill, During the First Three Years of Life" — 785 services (according to healthcare facility data, 18,096 patients were treated on an inpatient basis, including 16,760 patients in municipal facilities); Package No. 54 "Rehabilitation Care for Adults and Children in Outpatient Settings" — 7,278 services (according to healthcare facility data, 16,530 patients were treated on an outpatient basis, including 5,732 patients in municipal facilities). Dnipropetrovsk Oblast Rehabilitation departments have been created in 100 percent of cluster-level healthcare facilities — 16 facilities. Donetsk Oblast During 2025, inpatient rehabilitation care was provided at 3 healthcare facilities in the oblast, and outpatient rehabilitation care at 8 facilities. All facilities have concluded contracts with the National Health Service of Ukraine (hereinafter — NHSU). Zhytomyr Oblast Rehabilitation departments have been created in 5 cluster-level (100%) and 2 supra-cluster-level (100%) healthcare facilities in the oblast. Zakarpattia Oblast Rehabilitation departments have been created in 100 percent of cluster-level healthcare facilities in the oblast. Zaporizhzhia Oblast In accordance with the requirements of paragraph 5 of Resolution of the Cabinet of Ministers of Ukraine No. 174 dated 28.02.2023, "Certain Issues of Organizing a Capable Network of Healthcare Facilities," as amended, proposals for determining the final capable network of healthcare facilities in Zaporizhzhia Oblast will be submitted for approval to the Ministry of Health of Ukraine within six months after the end or cancellation of martial law. Preparatory work is currently under way. Rehabilitation departments have been created in 100% of potentially cluster-level healthcare facilities located in the government-controlled territory of the oblast. 13 municipally owned healthcare facilities have concluded contracts with the National Health Service of Ukraine (hereinafter — NHSU) under the medical guarantees program for rehabilitation service packages. Ivano-Frankivsk Oblast Rehabilitation departments operate in all 10 cluster-level facilities, and rehabilitation care is provided by multidisciplinary teams. Kirovohrad Oblast In 2025, inpatient rehabilitation departments operated in 10 healthcare facilities, including 220 beds for adults and 85 beds for children. Of the total number of rehabilitation beds, these beds operated in 2 multi-profile supra-cluster healthcare facilities and 4 cluster-level healthcare facilities. As of 1 January 2026, an inpatient rehabilitation department has been created at the Municipal Non-Profit Enterprise "Novoukrainka City Hospital"; after its opening, the figure will reach 100%. Luhansk Oblast In accordance with Resolution of the Cabinet of Ministers of Ukraine No. 174 dated 28.02.2023, "Certain Issues of Organizing a Capable Network of Healthcare Facilities," Luhansk Oblast submits proposals for determining the capable network of healthcare facilities and draft hospital district development plans within six months after the end or cancellation of martial law. In 2025, one hospital in the oblast concluded a contract for the provision of inpatient rehabilitation services, namely: the Municipal Non-Profit Enterprise of Lysychansk City Council "Lysychansk Multidisciplinary Hospital," where round-the-clock accommodation of service members is possible and which has an inpatient department (20 beds). Since the start of 2025, the service has been provided to 381 individuals. As of now, three healthcare facilities in the oblast have concluded such a contract: the Municipal Non-Profit Enterprise "Rubizhne Central City Hospital" of Rubizhne City Council, Luhansk Oblast, opened a 20-bed inpatient department in 2026; the Municipal Non-Profit Enterprise "Sievierodonetsk City Multidisciplinary Hospital" of Sievierodonetsk City Council opened a 20-bed inpatient department in 2026; and the Municipal Non-Profit Enterprise of Lysychansk City Council "Lysychansk Multidisciplinary Hospital." In total, services were provided to 84 individuals in 2026. Lviv Oblast Rehabilitation departments have been opened in 7 out of 7 cluster-level healthcare facilities in Lviv Oblast. Contracts with NHSU under the "Rehabilitation Care for Adults and Children in Inpatient Settings" package are in place for 6 facilities (one facility was not contracted in 2025, as it was awaiting a centralized delivery of rehabilitation equipment from the Ministry of Health of Ukraine). Mykolaiv Oblast Resolution of the Cabinet of Ministers of Ukraine No. 174 dated 28 February 2023 established the procedure for forming and operating hospital districts and hospital clusters. In accordance with paragraph 5 of this resolution, the Mykolaiv Oblast State Administration must submit proposals for determining the capable network of healthcare facilities and draft hospital district development plans for approval by the Ministry of Health within six months after the end or cancellation of martial law. At the same time, healthcare facilities contracted with the National Health Service of Ukraine ensure a full cycle of rehabilitation care — both inpatient (6 facilities) and outpatient (7 facilities) — introducing modern restorative treatment technologies and creating comfortable conditions for patients, including "hero wards," and deploying assistive technology rooms; teams of specialists guarantee an individualized patient care pathway. Odesa Oblast 8 out of 13 (61.5%) cluster-level healthcare facilities provide inpatient rehabilitation under package 53 (inpatient rehabilitation). Poltava Oblast Rehabilitation departments have been created in all cluster-level healthcare facilities. Rivne Oblast 3 projects were implemented in 2025. Two healthcare facilities were commissioned. Rehabilitation departments have been created in healthcare facilities: 100 percent of cluster-level facilities; 71.4 percent of supra-cluster-level facilities. Sumy Oblast Rehabilitation departments have been created at 15 healthcare facilities, of which 5 are cluster-level (100%). Ternopil Oblast In the oblast, 7 inpatient rehabilitation departments have been opened at 7 cluster-level healthcare facilities. Kharkiv Oblast In accordance with population needs for medical services, inpatient rehabilitation departments have been created in 15 out of 17 cluster-level and supra-cluster-level healthcare facilities that have a contract with NHSU. Khmelnytskyi Oblast Rehabilitation departments have been created in all 9 cluster-level healthcare facilities in the oblast (100%). In addition, inpatient rehabilitation care departments operate in 3 more general healthcare facilities (Khmelnytskyi Oblast Hospital for War Veterans, the Specialized Medical-Sanitary Unit in Netishyn, and the Khmelnytskyi Oblast Center for Medical Rehabilitation and Palliative Care for Children). The above-mentioned 12 healthcare facilities are contracted with NHSU under package 53 of medical services, "Rehabilitation Care for Adults and Children in Inpatient Settings." In 2026, 2 more multi-profile supra-cluster facilities plan to organize corresponding departments (Khmelnytskyi Oblast Hospital, Khmelnytskyi Oblast Children's Hospital). Cherkasy Oblast By Order of the Cherkasy Oblast Military Administration No. 708 dated 22.11.2023, the capable network of healthcare facilities of the Cherkasy hospital district was approved, with the capable network comprising: 7 supra-cluster healthcare facilities; 6 cluster-level healthcare facilities; 14 general healthcare facilities. As of 31.12.2025: rehabilitation departments operated in 3 cluster-level healthcare facilities of the capable network; in 2025, contracts were concluded with NHSU on the medical care of the population under the medical guarantees program for the provision of medical services in the area of "Rehabilitation Care for Adults and Children in Inpatient Settings": Municipal Non-Profit Enterprise "Third Cherkasy City Emergency Hospital" (cluster-level); Municipal Non-Profit Enterprise "Uman Central City Hospital" of Uman City Council (cluster-level); Municipal Non-Profit Enterprise "Uman Central District Hospital" of Palanka Village Council (cluster-level). Rehabilitation departments operate in 2 cluster-level healthcare facilities of the capable network, but contracts have not been concluded with the National Health Service of Ukraine on the medical care of the population under the medical guarantees program for the provision of medical services in the area of "Rehabilitation Care for Adults and Children in Inpatient Settings": Municipal Non-Profit Enterprise "Smila City Hospital" of Smila City Council (cluster-level); Municipal Non-Profit Enterprise "Zvenyhorodka Multidisciplinary Intensive Care Hospital" of Zvenyhorodka City Council (cluster-level). Major renovation of premises for the creation of a rehabilitation department is under way at 1 cluster-level healthcare facility of the capable network: Municipal Non-Profit Enterprise "Zolotonosha Multidisciplinary Hospital" of Zolotonosha City Council. Chernivtsi Oblast A total of 14 healthcare facilities operate in the oblast providing rehabilitation care to adults and children in inpatient settings. Of these, 6 cluster-level healthcare facilities provide inpatient rehabilitation care (100%). Chernihiv Oblast Rehabilitation departments have been created in all cluster-level and multi-profile supra-cluster hospitals in Chernihiv Oblast. | Rivne Oblast 957070,8 | Vinnytsia Oblast 37201,35 Rivne Oblast 3000,00 Khmelnytskyi Oblast 53200,0 Cherkasy Oblast 12120,7 Chernihiv Oblast 286560,0 | Vinnytsia Oblast 5083,44 Khmelnytskyi Oblast 15300,0 Cherkasy Oblast 1448,5 Chernihiv Oblast 769219,0 | Kharkiv Oblast The consequences of the russian federation's armed aggression and the destruction of medical infrastructure in communities have made it impossible to open inpatient rehabilitation departments at cluster-level facilities: the Municipal Non-Profit Enterprise of Izium City Council "Our Lady of Sand Central City Hospital" and the Municipal Non-Profit Enterprise "Kupiansk Territorial Medical Association" of Kupiansk City Council, Kharkiv Oblast. |
|  | 2) Conducting multidisciplinary training sessions from centers of excellence for all rehabilitation departments and centers of the capable network | 2025-2027 | at least 15 multidisciplinary training sessions ensured | Ongoing | Ministry of Health of Ukraine To respond promptly to the need to improve the quality of rehabilitation, since 2023 the Ministry of Health of Ukraine has initiated the development of clinical multidisciplinary rehabilitation centers of excellence. Their main goal is to upgrade the qualifications of rehabilitation specialists in the relevant professions and to train multidisciplinary rehabilitation teams (MDRTs) in the short and medium term. On 10 January 2024, cooperation memoranda were signed between the Ministry of Health of Ukraine and five centers-of-excellence facilities. On 8 April, a memorandum was signed between the Ministry of Health of Ukraine and the State Institution "Center for Mental Health and Rehabilitation of Veterans 'Lisova Poliana'." This facility directs its efforts toward the development of medical staff and rehabilitation specialists at healthcare facilities providing care to patients with psychological trauma, mild traumatic brain injury, as well as individuals who have survived torture and captivity. On 14 February 2025, a memorandum was signed with a seventh center of excellence, specializing in providing rehabilitation care to patients with spinal cord injuries — the Municipal Enterprise "Rivne Oblast Hospital for War Veterans" of Rivne Oblast Council (Klevan). Thus, as of December 2025, seven healthcare facilities have been engaged in the project: - Municipal Non-Profit Enterprise "Ivano-Frankivsk Oblast Clinical Hospital" of Ivano-Frankivsk Oblast Council, - Municipal Non-Profit Enterprise "City Clinical Hospital No. 4" of Dnipro City Council, - Municipal Non-Profit Enterprise "Vinnytsia Oblast Clinical Psychoneurological Hospital named after Academician O.I. Yushchenko" of Vinnytsia Oblast Council, - Municipal Non-Profit Enterprise "Ternopil Oblast Clinical Psychoneurological Hospital" of Ternopil Oblast Council, - Scientific Research Institute of Children's Diseases "Okhmatdyt," - State Institution "Center for Mental Health and Rehabilitation of Veterans 'Lisova Poliana' of the Ministry of Health of Ukraine," - Municipal Enterprise "Rivne Oblast Hospital for War Veterans" of Rivne Oblast Council. In 2025, training covered at least 41 facilities of the capable network (36 with WHO support, 5 with ENABEL support). Training formats offered by the centers of excellence include in-person training, internships, supervision, online training, conferences, trainer-training courses, expert assessments, and clinical professional 3-month training programs. Regulatory provisions for rehabilitation provided at the community level have been introduced, and measures have been taken to contract general healthcare facilities for outpatient rehabilitation, ensuring the provision of this type of rehabilitation care. The Ministry of Health, together with the National Health Service of Ukraine, is carrying out systematic work to form an extensive network for the provision of outpatient rehabilitation care for children on the basis of the capable network of healthcare facilities. This approach ensures accessibility of rehabilitation services for the child population, continuity of the rehabilitation process, and the possibility of receiving care as close as possible to the place of residence of the child and their family. As of December 2025, 531 healthcare facilities had concluded contracts with the National Health Service of Ukraine within the medical services package for "Rehabilitation Care for Adults and Children in Outpatient Settings." This number of providers indicates a well-formed and territorially balanced network of outpatient rehabilitation, covering various levels of medical care and ensuring timely access for children to rehabilitation services regardless of the region of residence. An important element in the development of the outpatient rehabilitation network is the introduction of a rehabilitation mono-service, provided by individual rehabilitation specialists in an outpatient setting according to the individual needs of the child. This format of care delivery allows for flexible responses to family requests, ensures the regularity of rehabilitation interventions, and optimizes the use of healthcare system resources. The rehabilitation mono-service is especially important for children who require long-term dynamic monitoring and correction of functional impairments without the need for an inpatient stage of rehabilitation. Resolutions of the Cabinet of Ministers of Ukraine No. 132 dated 7 February 2025, "On Amendments to the Procedures Approved by Resolutions of the Cabinet of Ministers of Ukraine No. 1268 dated 3 November 2021 and No. 1462 dated 16 December 2022," and No. 1438 dated 7 November 2025, "On Amendments to the Resolutions of the Cabinet of Ministers of Ukraine No. 1268 dated 3 November 2021 and No. 1462 dated 16 December 2022," have been adopted, regulating the mono-professional rehabilitation service. |  |  |  |  |
| 47. Improving the accessibility of mental health services | 1) Ensuring accessibility of mental health services at the primary and specialized (outpatient) levels of the medical field by scaling up mhGAP (Mental Health Gap Action Programme) training | 2025–2027 | an increase of at least 10 percent compared to the previous year in the number of medical staff who have completed mhGAP courses | Not started | Ministry of Defense of Ukraine Mandatory participation has been organized and ensured for all doctors and nursing staff providing primary-level medical care, as well as for psychologists and civil-military cooperation specialists, in an online course developed with the support of the World Health Organization, "Management of Common Mental Disorders at the Primary Level of Medical Care Using the mhGAP Guide," levels 1 and 2, on the "NHSU Academy" web platform (as of 30.12.2025, 406 doctors had completed the above-mentioned course; monitoring data is updated quarterly). State Border Guard Service Administration of Ukraine By Order of the State Border Guard Service Administration No. 13/14279-26-Vykh dated 19.02.2026, "On the Organization of Measures," registration of medical personnel of the State Border Guard Service bodies was organized for training on the National Health Service of Ukraine Academy platform. 64 individuals have been registered for the course "Management of Common Mental Disorders at the Primary Level of Medical Care Using the mhGAP Guide." Ministry of Internal Affairs 794 specialists from healthcare facilities of the Ministry of Internal Affairs system have participated in the Mental Health Gap Action Programme (mhGAP) materials, including specialists who are not directly specialized in mental health but who encounter patients with related needs in the course of their work. By Order of the State Border Guard Service Administration of Ukraine No. 13/14279-26-Vykh dated 19.02.2026, "On the Organization of Measures," registration of medical personnel of the State Border Guard Service bodies was organized for training on the National Health Service of Ukraine Academy platform. 64 individuals have been registered for the course "Management of Common Mental Disorders at the Primary Level of Medical Care Using the mhGAP Guide." In 2025, 45 individuals from the National Guard of Ukraine, including doctors, nursing staff, and psychologists, completed the mhGAP (Mental Health Gap Action Programme) online training course, which covered modern approaches to identifying, preventing, and providing assistance to individuals with mental disorders, as well as forming early-response skills. |  |  |  |  |
|  | 2) Creation of mental health centers in every cluster-level and children's supra-cluster healthcare facility within the framework of the national mental health and psychosocial support program | 2025-2027 | mental health centers created in 100 percent of cluster-level facilities |  | Vinnytsia Oblast In 2025, the number of Mental Health Centers that concluded an agreement with the National Health Service of Ukraine increased from 4 to 6: 2 supra-cluster facilities and 4 cluster-level facilities. Dnipropetrovsk Oblast Mental health centers have been created in 94 percent of cluster-level healthcare facilities — 15 out of 16. Donetsk Oblast Mental health centers have been created at the Municipal Non-Profit Enterprise "Oblast Clinical Psychiatric Hospital, Sloviansk," which has a contract with NHSU, and at the Municipal Non-Profit Enterprise "Mariupol City Hospital No. 1" of Mariupol City Council, which does not have a contract with NHSU. Zhytomyr Oblast Mental health centers have been created in 5 cluster-level (100%) healthcare facilities in the oblast and 1 children's supra-cluster (100%) healthcare facility. Zakarpattia Oblast In the oblast, under package 72, "Psychosocial and Psychiatric Care for Adults and Children Provided in Mental Health Centers and by Mobile Multidisciplinary Teams," 8 healthcare facilities have signed a contract with the National Health Service of Ukraine. 8 Mental Health Centers have been created in the oblast: 6 based at cluster-level hospitals and 2 at supra-cluster-level hospitals. Zaporizhzhia Oblast Within the framework of the National Mental Health and Psychosocial Support Program, mental health centers have been created at potentially cluster-level and supra-cluster-level healthcare facilities (in the government-controlled territory of the oblast), with contracts concluded with NHSU under the medical guarantees program for the service package "Psychosocial and Psychiatric Care for Adults and Children Organized by Mental Health Centers and Mobile Multidisciplinary Teams." As of 01.01.2026, 3 mental health centers have been created and operate at: Municipal Non-Profit Enterprise "Territorial Medical Association 'Healthy Family'" of Zaporizhzhia Oblast Council, Municipal Non-Profit Enterprise "City Hospital No. 4" of Zaporizhzhia City Council, Municipal Non-Profit Enterprise "Oblast Preschool Institution for Psychiatric Care and Rehabilitation" of Zaporizhzhia Oblast Council. Ivano-Frankivsk Oblast Mental health centers have been created and operate in 9 out of 10 cluster-level healthcare facilities. The question of opening a mental health center at the Municipal Non-Profit Enterprise "Central City Clinical Hospital" of Ivano-Frankivsk City Council is being worked on. Kyiv Oblast As of 1 January 2026, mental health centers, created in 2024, operate in 100% of cluster-level healthcare facilities in Kyiv Oblast. Kirovohrad Oblast Mental health centers have been created and are operating successfully in 4 cluster-level healthcare facilities in the oblast (Municipal Non-Profit Enterprise "Central City Hospital" of Kropyvnytskyi City Council, Municipal Non-Profit Enterprise "City Emergency Hospital" of Kropyvnytskyi City Council, Municipal Non-Profit Enterprise "Novoukrainka City Hospital" of Novoukrainka City Council, and Municipal Non-Profit Enterprise "Holovanivsk Hospital"), representing 80% of their total number. In addition, a mental health center has been created at a supra-cluster facility — Municipal Non-Profit Enterprise "Oblast Clinical Children's Hospital" of Kirovohrad Oblast Council. Luhansk Oblast In 2025, 5 healthcare facilities have "Mental Health" units in their structure, namely: Municipal Non-Profit Enterprise "Center for Mental Health" of Luhansk Oblast Council (Dnipro), Municipal Non-Profit Enterprise "Consultative-Diagnostic Center" of Sievierodonetsk City Council (Dnipro), Municipal Non-Profit Enterprise "Kreminna Multidisciplinary Hospital" of Kreminna City Council (Rivne), and Municipal Non-Profit Enterprise "Sievierodonetsk City Multidisciplinary Hospital" of Sievierodonetsk City Council. Also in 2025, the Municipal Non-Profit Enterprise "Rubizhne Central City Hospital" of Rubizhne City Council (Kharkiv) concluded a contract with NHSU under the medical guarantees program for the service package "Psychosocial and Psychiatric Care for Adults and Children Organized by Mental Health Centers and Mobile Multidisciplinary Teams." The institution has a "Mental Health Center" in its structure. A total of 6,172 individuals received services in 2025. Lviv Oblast Mental health centers have been opened in 7 out of 7 cluster-level healthcare facilities in Lviv Oblast. Contracts with NHSU under the package "Psychosocial and Psychiatric Care for Adults and Children Provided in Mental Health Centers and by Mobile Multidisciplinary Teams" are in place for 6 facilities (one facility was not contracted in 2025, as the facility's staff lacks a child psychiatrist). Mykolaiv Oblast 3 mental health centers operate in Mykolaiv Oblast. The centers ensure a comprehensive approach to mental health care, combining medical and psychosocial support for various patient categories. Odesa Oblast Mental health centers have been created in 7 out of 13 cluster-level facilities (54%) and in one children's supra-cluster healthcare facility. Poltava Oblast 8 Mental Health Centers have been created in 6 cluster-level facilities (75%). Rivne Oblast Mental health centers have been created in 86 percent of cluster-level healthcare facilities. Sumy Oblast As of 31.12.2025, mental health centers have been created in 3 out of 5 (60%) cluster-level healthcare facilities (Municipal Non-Profit Enterprise "Central City Clinical Hospital" of Sumy City Council, Municipal Non-Profit Enterprise of Konotop City Council "Konotop Central District Hospital named after Academician Mykhailo Davydov," Municipal Non-Profit Enterprise of Okhtyrka City Council "Okhtyrka Central District Hospital") and at a supra-cluster facility (Municipal Non-Profit Enterprise of Sumy Oblast Council "Sumy Oblast Clinical Hospital"). Ternopil Oblast 10 mental health centers have been created in the oblast, based at all cluster-level healthcare facilities and at a supra-cluster facility for providing medical care to children. Kharkiv Oblast During the reporting period, 9 cluster-level municipal healthcare facilities and 1 children's supra-cluster municipal healthcare facility have a contract with NHSU under the package "Psychosocial and Psychiatric Care for Adults and Children Organized by Mental Health Centers and Mobile Multidisciplinary Teams," representing 53.0% of the facilities in the capable network by clustering. Work to increase the number of mental health centers is ongoing. Khmelnytskyi Oblast In Khmelnytskyi Oblast, 6 healthcare facilities have concluded a contract with NHSU under the medical guarantees program for the package "Psychosocial and Psychiatric Care for Adults and Children Organized by Mental Health Centers and Mobile Multidisciplinary Teams." In 2025, mental health centers were also opened at Khmelnytskyi Oblast Hospital and the Municipal Non-Profit Enterprise "Khmelnytskyi Oblast Hospital for War Veterans"; the possibility of concluding a contract with NHSU is being explored. In total, 16,246 mental health services were provided to almost 4,000 people at healthcare facilities in the oblast last year. In 2026, work will continue on creating mental health centers based at all cluster-level and supra-cluster healthcare facilities in the oblast. Cherkasy Oblast As of the end of 2025, Mental Health Centers operated in 2 out of 6 cluster-level healthcare facilities in the oblast, namely: Municipal Non-Profit Enterprise "Smila City Hospital" of Smila City Council and Municipal Non-Profit Enterprise "Third Cherkasy City Emergency Hospital." Chernivtsi Oblast Mental health centers operate in all 6 cluster-level healthcare facilities in the oblast (100%). Mental health centers also operate in 2 outpatient/polyclinic facilities: Municipal Non-Profit Enterprise "City Polyclinic No. 1" and Municipal Non-Profit Enterprise "City Polyclinic No. 2." Chernihiv Oblast As of 01.01.2026, mental health centers have been created in 9 cluster-level healthcare facilities — 100%. Contracts with NHSU under package 72, "Psychosocial and Psychiatric Care for Adults and Children Provided in Mental Health Centers and by Mobile Multidisciplinary Teams," have been concluded at 7 facilities. | Zaporizhzhia Oblast 1304,79 | Khmelnytskyi Oblast 640,0 | Sumy Oblast 11561,6 Khmelnytskyi Oblast 9400,0 | Sumy Oblast Preparatory work is under way for creating mental health centers at other cluster-level and supra-cluster facilities. Problem issues: the difficult security situation in the front-line zone, and an insufficient number of specialists of the relevant profile. Kharkiv Oblast A significant reason for the slow opening of centers is the shortage of specialized personnel, which does not allow the specification requirements under the corresponding medical guarantees program package to be met. |
| Area "Digital Infrastructure, Administrative and Public (Electronic Public) Services" |  |  |  |  |  |  |  |  |  |
| 48. Development of high-speed internet access networks in all settlements | facilitating the organization and provision of broadband internet access in settlements for the stable provision of electronic communication services to the population | 2025—2027 | 95 percent of the population provided with broadband internet access at a fixed location | Ongoing | Ministry of Digital Transformation New Rules for the Provision and Receipt of Electronic Communication Services have been approved (Resolution of the Cabinet of Ministers of Ukraine No. 761 dated 25 June 2025), obliging providers to ensure data transmission speeds in accordance with established quality indicators. |  |  | 5000,010 | Targeted attacks on Ukraine's energy infrastructure, leading to prolonged power outages. Impact on the measure — Instability of internet access networks, inability to comply with requirements for continuity of service provision and network security. Resolution mechanism — Providers implementing directives of the National Center for Operational and Technical Management to increase network resilience. Service providers are obligated to take technical measures to guarantee the integrity and continuity of equipment operation using alternative power sources. |
| 49. Ensuring that local self-government bodies and oblast state (military) administrations publish public information in the form of open data on the Unified State Web Portal of Open Data (data.gov.ua) | 1) Publication of datasets from the sections "All Information Managers (According to Competence)," "Local Self-Government Bodies," "Local State Administrations," in accordance with the Recommendations for the Publication of Open Data Sets published by the Ministry of Digital Transformation on the Unified State Web Portal of Open Data | 2025—2027 | at least 10 datasets published by local state administrations and at least 50 datasets published by local self-government bodies | Ongoing | Vinnytsia Oblast As of 20.03.2026, 7 local state administrations (Vinnytsia Oblast, Vinnytsia, Haisyn, Zhmerynka, Mohyliv-Podilskyi, Tulchyn, and Khmilnyk district administrations) and 52 territorial communities of the oblast are registered on the Unified State Portal of Open Data. In total, 5,567 open data sets have been published. Volyn Oblast All datasets for which recommendations exist have been published. Zhytomyr Oblast 7 datasets of the oblast state (military) administration, as the sole manager of open data, have been published. 30 local self-government bodies are registered on the Unified State Web Portal of Open Data. Work is under way for managers to publish information in the form of open data on a "single window" basis. Zakarpattia Oblast 102 datasets have been published by local state administrations and 412 datasets by local self-government bodies. Zaporizhzhia Oblast Article 10-1 of the Law "On Access to Public Information" requires the publication of datasets, but allows for certain restrictions if access is limited based on the results of a three-part test or for the purpose of protecting national security, territorial integrity, and public safety. In view of the above, the publication of datasets on the Unified State Web Portal of Open Data has been suspended for the duration of the martial law legal regime. Ivano-Frankivsk Oblast In 2025, the Ivano-Frankivsk Oblast State Administration published 60 datasets on the Unified State Web Portal of Open Data. Publication of information in the form of open data on the Portal is carried out by: 22 city, settlement, and village councils of the oblast, and 5 district state administrations. Kyiv Oblast The oblast state administration and district state administrations have published at least 1 dataset each, and local self-government bodies have published 10–20 datasets per territorial community. Kirovohrad Oblast The oblast military administration ensures implementation of the openness and transparency policy. In 2025, the system for working with open data was organized: responsible persons were designated, the list of datasets and their update frequency was updated, and the procedure for publishing information was unified. Orders of the head of the oblast state administration No. 1505-r dated 1 October 2025 and No. 1676-r dated 8 December 2025 approved the results of a comprehensive information audit. Based on its results, an updated draft order on responsible persons and datasets subject to publication in the form of open data, managed by the Kirovohrad Oblast State Administration, was prepared. In 2025, the Kirovohrad Oblast State (Military) Administration published 3 datasets, and local self-government bodies in the oblast published 17 datasets, on the Unified State Web Portal of Open Data. Luhansk Oblast Datasets are not published due to a temporary restriction of access to them by the datasets portal administrator. Lviv Oblast The Lviv Oblast State Administration has published 254 datasets, and communities in Lviv Oblast have published 3,330 datasets. 37 communities have published 50 or more datasets from the sections "All Information Managers (According to Competence)," "Local Self-Government Bodies," and "Local State Administrations," in accordance with the Recommendations for the Publication of Open Data Sets published by the Ministry of Digital Transformation. Mykolaiv Oblast By letter No. 1/06-2-6620 dated 09.08.2022, the Ministry of Digital Transformation resumed the operation of the Unified State Web Portal of Open Data with a restriction on public access to datasets from managers in Kherson, Mykolaiv, Zaporizhzhia, Donetsk, Luhansk, and Kharkiv oblasts. Until the territory is completely liberated from the occupiers, the publication of open data on the Unified State Web Portal of Open Data by managers from the above-mentioned oblasts is not carried out. Odesa Oblast In 2025, 2 datasets from the "All Managers" section and 4 datasets from the "Local State Administrations" section were published on the Unified State Web Portal of Open Data. Poltava Oblast The Poltava Oblast Military Administration has published 9 mandatory datasets, and 8 datasets are under moderation. Out of 60 communities, 2 have published more than 50 datasets, and 40 communities are working on publishing datasets. Rivne Oblast By Order of the Head of the Rivne Oblast Military Administration No. 241 dated 2 May 2025, "On the Datasets of the Rivne Oblast State (Military) Administration Subject to Publication in the Form of Open Data," the List of Datasets of the Rivne Oblast Military/State Administration subject to publication in the form of open data on the Unified State Web Portal of Open Data was approved. The Rivne Oblast Military/State Administration has published 32 open datasets, of which: 18 comply with the updated Recommendations for the Publication of Open Data Sets, though 9 are still under moderation; 14 have their update frequency set to "No longer updated." Sumy Oblast Publication of public information in the form of open data on the Unified State Web Portal of Open Data (15 datasets) is ensured, managed by the Sumy Oblast State Administration — the oblast military administration, in accordance with the Recommendations for the Publication of Open Data Sets published by the Ministry of Digital Transformation on the Unified State Web Portal of Open Data. Ternopil Oblast An audit was conducted and 37 datasets were published, 11 of them from the "All Information Managers (According to Competence)" section. Compliance of the data structure with the requirements of Cabinet of Ministers Resolution No. 835 dated 21 October 2015 has been ensured. Kharkiv Oblast The Kharkiv Oblast State (Military) Administration has published 14 datasets on the Unified State Web Portal of Open Data, intended for publication by oblast state administrations under the sections "All Information Managers (According to Competence)" and "Local State Administrations." Khmelnytskyi Oblast 20 datasets have been published on the Unified State Web Portal of Open Data. Cherkasy Oblast The Cherkasy Oblast Military Administration has submitted 21 datasets, of which 7 have been published on the data.gov.ua open data portal. Local self-government bodies of Cherkasy Oblast have submitted 578 datasets, of which 331 have been published. Chernivtsi Oblast 685 datasets have been published by the oblast state administration (oblast military administration), district state administrations (district military administrations), and local self-government bodies of the oblast. Chernihiv Oblast Under the account "Chernihiv Oblast State Administration" on the Unified State Web Portal of Open Data, 21 datasets have been published. The resources within these datasets are updated in accordance with the frequency specified in the datasets' passports. Of 57 territorial communities, 36 are registered on the Unified State Web Portal of Open Data, where they have published a total of 354 datasets. Ministry of Digital Transformation According to information from the Unified State Web Portal of Open Data, 14 local self-government bodies have published 50 or more datasets that are mandatory for publication; 16 oblast military administrations have published more than 10 datasets. At the same time, Resolution of the Cabinet of Ministers of Ukraine No. 1151 dated 10 September 2025 amended the Regulation on Datasets Subject to Publication in the Form of Open Data, approved by Resolution of the Cabinet of Ministers of Ukraine dated 21 October 2015, in particular stipulating that the upload of the datasets specified in the list is carried out taking into account the recommendations published by the Ministry of Digital Transformation on the Unified State Web Portal of Open Data. |  |  |  | Donetsk Oblast In order to protect information resources during martial law, their publication has been restricted, as provided for by subparagraph 4 of paragraph 1 of Cabinet of Ministers Resolution No. 263 dated 12 March 2022, "Certain Issues of Ensuring the Functioning of Information and Communication Systems, Electronic Communication Systems, and Public Electronic Registers under Martial Law." Poltava Oblast Communities face a problem of insufficient staffing. An additional factor complicating the timely publication of datasets is the lengthy moderation period on the Unified State Web Portal of Open Data. Rivne Oblast Lengthy moderation period for datasets by the administrator of the Unified State Web Portal of Open Data. The essence of the problem lies in the significant time gap between the moment data is uploaded by the manager and its actual publication in open access. Datasets can remain in moderation status for a long time, which technically blocks users' access to information, even though the manager has formally fulfilled its obligation to upload the data. Until a dataset has passed moderation, it is not considered published, which creates risks of a negative assessment of the body's activity in terms of transparency. Ministry of Digital Transformation Staff turnover and shortages on the part of managers, and low priority given to the development of the open data sphere among managers. |
|  | 2) Facilitating the accession of Ukrainian cities to the International Open Data Charter | 2025—2027 | accession of at least 50 Ukrainian cities to the International Open Data Charter ensured |  | Vinnytsia Oblast Vinnytsia City Council joined the International Open Data Charter in 2017. A Memorandum of Cooperation was signed as part of the implementation of a pilot project on open data. A decision of the executive committee of the city council No. 1627 dated 20.07.2017, "On the Accession of Vinnytsia City Council and Its Executive Bodies to the International Open Data Charter," was adopted. The action plan for implementing the principles of the International Open Data Charter is carried out in accordance with Order of the City Mayor No. 181-R dated 18.10.2017, "On Measures for Implementing the Principles of the International Open Data Charter and Developing Open Data." Volyn Oblast - 1 city has joined the International Open Data Charter; - 52 communities (97% of communities in the oblast) are registered on the Portal; - 426 datasets have been published, including 232 in machine-readable format, with 219 kept up to date; - a website with video instructions and informational materials on publishing datasets has been created; - an information audit of open data has been conducted in 6 communities of the oblast. Zhytomyr Oblast Explanatory work was carried out on introducing an open data policy in communities in accordance with the principles of the International Open Data Charter, and on assisting local self-government bodies in registering on the Open Data Portal (30 local self-government bodies registered). Zakarpattia Oblast One city in Zakarpattia Oblast (Uzhhorod) has joined the International Open Data Charter. Zaporizhzhia Oblast The city of Zaporizhzhia, part of the Zaporizhzhia city territorial community, officially joined the International Open Data Charter in October 2020 (Order of the City Mayor No. 201r dated 02.10.2020). Ivano-Frankivsk Oblast The city of Ivano-Frankivsk has joined the International Open Data Charter. Kyiv Oblast Organizational and informational-advisory support is provided for the process of cities joining the International Open Data Charter. Kirovohrad Oblast In 2025, the city of Kropyvnytskyi joined the International Open Data Charter and committed to implementing its principles regarding the openness, accessibility, and machine-readability of data. This contributes to increasing the transparency of local self-government bodies' activities and developing an open data policy in the community. Luhansk Oblast Implementation has not begun. Lviv Oblast All 73 communities in Lviv Oblast have joined the International Open Data Charter. Poltava Oblast Currently, cities in the oblast have not joined the International Open Data Charter. Ternopil Oblast The oblast military administration has developed methodological recommendations on implementing the principles of the International Open Data Charter in the activities of the oblast military administration. Kharkiv Oblast By decision of Kharkiv City Council No. 348 dated 12.05.2021, the city of Kharkiv joined the International Open Data Charter. Khmelnytskyi Oblast Last year, a seminar for representatives of local self-government bodies on the principles of the International Open Data Charter was held in the oblast, with the support of the Ministry of Digital Transformation, with the aim of communities joining the charter. As of 01.01.2026, the city of Khmelnytskyi has joined the charter from Khmelnytskyi Oblast. Cherkasy Oblast The Cherkasy territorial community of Cherkasy district has joined the Open Data Charter. Gradual implementation of open data functionality is under way. Chernihiv Oblast There is no information on cities in Chernihiv Oblast joining the International Open Data Charter. Should a relevant request be received, the Chernihiv Oblast State Administration will ensure the necessary actions are taken within its authority. |  |  |  |  |
| 50. Increasing the level of digital literacy of the population, including through the creation of learning opportunities on the Unified State Web Portal of Digital Education "Diia. Osvita" | creation of educational materials on acquiring digital competencies on the Unified State Web Portal of Digital Education "Diia. Osvita" | 2025 | educational materials posted on the Unified State Web Portal of Digital Education "Diia. Osvita" | Completed | Ministry of Digital Transformation As of 2025, 37 educational products on the topic of digital literacy (digital skills and media literacy) have been posted on the Unified State Web Portal of Digital Education Diia.Osvita: educational series, guides, and "cyphrograms" for citizens, civil servants, teachers, medical professionals, and librarians. These include, in particular, educational series published in 2025: "ChatGPT: Your Personal Assistant at Work, in Study, and in Life" (https://osvita.diia.gov.ua/courses/chatgpt-your-personal-assistant-for-work-study-and-life), "Enterprise 360" (https://osvita.diia.gov.ua/courses/enterprise-360), "Digital Business" (https://osvita.diia.gov.ua/courses/digital-businesses), and "Technologies Shaping the Future" (https://osvita.diia.gov.ua/courses/technologies-shaping-the-future). In 2025, almost 55,000 users received certificates for completing educational series on digital literacy (digital skills and media literacy). In total, over the entire period, more than 615,000 users have received certificates on the topic of digital literacy. |  |  |  |  |
| 51. Facilitating electronic communications operators' access to construction, transport, and electric power facilities, and the lease of state and municipal property, for the purpose of placing technical equipment for electronic communications, and in the allocation of land plots for the deployment of electronic communication networks and/or their infrastructure, etc. | 1) Ensuring the allocation of land plots for the deployment of electronic communication networks and/or their infrastructure | 2027 | decisions adopted on providing electronic communications operators with land plots |  | Donetsk Oblast Implementation of the measure is planned for 2027. Kirovohrad Oblast In order to develop telecommunications infrastructure in the oblast, electronic communications operators deployed mobile communication networks in 2025, including the installation of 32 base stations. Local self-government bodies and local state administrations provided assistance to operators in resolving issues of access to infrastructure facilities and the allocation of land plots for placing technical equipment for electronic communications. Lviv Oblast Agreements have been signed for 6 land plots. Khmelnytskyi Oblast In 2025, no requests were received from mobile operators to the oblast military administration. Mobile operators have submitted requests to the Yarmolyntsi, Starokostiantyniv, and Horodok territorial communities. In 2026, work will continue on establishing communication regarding the allocation of land plots for the construction of mobile communication base stations. Chernivtsi Oblast Should requests be received from electronic communications operators regarding changes to the designated purpose of land and the allocation of land plots for the deployment of electronic communication networks and/or their infrastructure, they will be considered at meetings of the oblast commission on the exercise by the oblast state administration of its powers in the field of land relations. |  |  |  |  |
|  | 2) Introduction by passenger transport organizers of GPS monitoring systems for vehicle movement | 2025—2027 | online access for the population to information on vehicle movement ensured | Ongoing | Ministry for Communities, Territories and Infrastructure Development In order to create an effective, transparent, and technologically modern information and communication system that ensures the automated collection, transmission, storage, processing, and visualization of data on the location, movement, and condition of vehicles in near-real-time mode, using satellite navigation systems, communication tools, and software/hardware components, for the purpose of monitoring the execution of routes (trips), compliance with established transportation conditions, recording events and incidents, as well as providing analytics and management decisions regarding the operation of vehicles carrying out interregional and international passenger transport, a draft Resolution of the Cabinet of Ministers of Ukraine "On the Implementation of a Pilot Project for the Operation of a Vehicle GPS Monitoring System" has been developed. As of 1 May 2026, this draft act is at the stage of approval with central executive authorities and was published on the website for public discussion. |  |  |  |  |
| 52. Facilitating the introduction of digital documents in all areas of activity requiring verification of document authenticity or obtaining copies of identity documents, as well as integrating the remote qualified electronic signature (Diia.Signature) on official web resources for authorization and electronic signing of documents | development of unified procedures for integrating Diia services, including connecting information and communication systems to the Unified State Web Portal of Electronic Services regarding the use of services for verifying and obtaining copies of digital documents | 2027 | acts of the Cabinet of Ministers of Ukraine adopted | Not started | The deadline for implementing the measure has not yet arrived. |  |  |  |  |
| 53. Facilitating the development of a network of administrative service centers and ensuring the quality provision of services to applicants | 1) mproving legislation regarding the possibility of providing administrative services during registration actions in the State Ship Register of Ukraine and the Ship Book of Ukraine using an information and communication system based on an application submitted in electronic form, and amending the Procedure for Registering Ships in the State Ship Register of Ukraine and the Ship Book of Ukraine | 2025 | order of the Ministry for Communities, Territories and Infrastructure Development issued | Completed | Maritime Administration By Order of the Ministry for Communities, Territories and Infrastructure Development No. 1294 dated 22.08.2025, registered with the Ministry of Justice of Ukraine on 02.10.2025 under No. 1441/44847, amendments were made to the Procedure for Registering Ships in the State Ship Register of Ukraine and the Ship Book of Ukraine, providing, in particular, for the possibility of providing administrative services during registration actions in the State Ship Register of Ukraine and the Ship Book of Ukraine using an information and communication system based on an application submitted in electronic form. |  |  |  |  |
|  | 2) Formation of a functional network of administrative service centers, their territorial subdivisions, and remote (including mobile) administrator workstations to ensure the provision of all groups of administrative services | 2025—2027 | establishment of administrative service centers ensured in 85 percent of territorial communities | Ongoing | Ministry of Digital Transformation Under martial law and amid new challenges, the development of the network of administrative service centers continues. Administrative Service Centers (ASCs) have been established in 93% of communities. As of 1 January 2026, the established network of administrative service centers comprises 5,694 access points, namely: 1,373 ASCs, 163 territorial subdivisions, 3,592 remote administrator workstations, 51 mobile ASCs, and 515 village elders (starosty). Of these, 1,344 ASCs (including 90 in the "Diia.Center" format), 154 territorial subdivisions, 3,354 remote administrator workstations, 37 mobile ASCs, and 515 village elders providing services are operational, together forming 5,404 access points to administrative services. 290 ASC access points are not operating due to martial law. As a result of the russian federation's full-scale armed aggression against Ukraine, 86 service access points have been destroyed: 22 ASCs, 2 territorial subdivisions, 58 remote workstations, and 4 mobile centers; 66 points have been damaged (rendering them unusable): 24 ASCs, 3 territorial subdivisions, 38 remote workstations, and 1 mobile center; 153 points have been damaged (but remain usable): 62 ASCs, 6 territorial subdivisions, 84 remote workstations, and 1 mobile center, which currently require restoration. At the same time, the issue of state financial support for the sector remains relevant in order to complete the formation of an effective ASC network, ensure its sustainable development, and restore destroyed buildings and premises of the centers. In 2025, the Ministry of Digital Transformation formulated a public investment direction proposal, "Development and Transformation of the Network of Administrative Service Centers with a High Level of Digital Maturity, Accessibility, Inclusiveness, and Convenience for Applicants," for the Medium-Term Plan of Priority Public Investments of the State for 2026–2028; however, this direction has not yet been included among the main public investment directions, and no funds have been allocated. |  | 367 528,70 | 80 725,10 |  |
| Operational Goal 3. Social protection of war veterans and their families, internally displaced persons, and other vulnerable population groups |  |  |  |  |  |  |  |  |  |
| Напрям «Інтеграція внутрішньо переміщених осіб» Area: "Integration of Internally Displaced Persons" |  |  |  |  |  |  |  |  |  |
| 54. Creating an effective and transparent mechanism for recording, allocating and using state- and municipally-owned residential or other premises suitable for the temporary accommodation of internally displaced persons | Creating an information database on data regarding real-estate objects (including as a result of repairs, refitting, deterioration of technical condition, change of owner, etc.) | 2025 | the information database put into operation | Ongoing | Ministry for Communities, Territories and Infrastructure Development - Resolution of the Cabinet of Ministers of Ukraine No. 894 of 16 July 2025, "Certain Issues Concerning the Creation and Operation of the Information and Analytical System of Real Estate Objects for Providing Housing to Internally Displaced Persons, and Its Interaction with Other Information and Communication Systems" (hereinafter — Resolution No. 894), has been adopted. Pursuant to paragraph 2 of Resolution No. 894, the Ministry for Communities, Territories and Infrastructure Development is to: 1) take measures to create the Information and Analytical System of Real Estate Objects for Providing Housing to Internally Displaced Persons (hereinafter — the Information and Analytical System) and begin its operation no later than 1 October 2026; and 2) ensure electronic information exchange between the Information and Analytical System and the Unified State Electronic System in the Field of Construction no later than 1 September 2026. The Ministry for Communities, Territories and Infrastructure Development is taking measures, as provided for in paragraphs 2–5 of Resolution No. 894, to create the Information and Analytical System and begin its operation. In particular, cooperation continues with the Office of the United Nations High Commissioner for Refugees (hereinafter — UNHCR Ukraine) on developing the Information and Analytical System. The Ministry for Communities, Territories and Infrastructure Development informed the UNHCR Representation in Ukraine of the approval of a document containing technical requirements (TR) for creating the Information and Analytical System (letter dated 30.10.2025, No. 28315/37/10-25). By letters dated 12.11.2025, No. 34768/37/14-25, and a follow-up letter dated 26.03.2026, No. 4751/37/14-26, the Ministry for Communities, Territories and Infrastructure Development also appealed to the UNHCR Representation in Ukraine to expedite preparation of tender procedures for selecting a contractor to develop the software for the Information and Analytical System of Real Estate Objects for Providing Housing to Internally Displaced Persons, so as to put it into operation as soon as possible. - By letter dated 20.04.2026, UNHCR Ukraine informed the Ministry regarding the development of the information and analytical system, that approval of the tender results is currently at the stage of approval by UNHCR's Regional Bureau for Europe, expected during April or early May. In parallel with the tender process, UNHCR has supported the Ministry in documenting the ongoing real-estate inventory process provided for by Law No. 4080-IX. In particular, UNHCR has developed a module that will enable the transfer of collected inventory data into the new system once it is deployed. |  |  |  | No state-budget funds were allocated in 2025 or 2026 for measures to develop the Information and Analytical System of Real Estate Objects for Providing Housing to Internally Displaced Persons. It should be emphasized that, when drafting proposals for the 2026 state budget, the Ministry for Communities, Territories and Infrastructure Development requested funding for a programme that would provide for the development and implementation of a Unified Information and Analytical Housing System, whose creation is envisaged under the Law of Ukraine "On the Basic Principles of Housing Policy." The Information and Analytical System of Real Estate Objects for Providing Housing to Internally Displaced Persons is intended to become, in future, an integral part of the comprehensive Unified Information and Analytical Housing System, automating and optimizing the processes of collecting, managing, and publishing information on state and private facilities that could be used or repurposed to house internally displaced persons. These proposals were not taken into account in the Law of Ukraine "On the State Budget of Ukraine for 2026." |
| 55. Creating conditions for the phased resettlement of internally displaced persons living in temporary accommodation, taking into account regional human-resource needs and the particular needs of specific categories of persons (persons with disabilities, large families, the elderly) and the principle of family unity | 2) Creating a fund of social housing for war veterans and their families, internally displaced persons, large families, families with children, and other vulnerable population groups | 2027 | at least 800,000 square metres of social housing put into operation | Not started | The implementation deadline has not yet arrived. |  |  |  |  |
|  | 2) Creating a database of social housing for war veterans and their families, internally displaced persons, large families, families with children, and other vulnerable population groups, as well as for providers of supported-living services | 2027 | the corresponding database put into operation | Not started | The implementation deadline has not yet arrived. |  |  |  |  |
|  | 3) Improving the mechanism of social support for providing subsidies to internally displaced persons to pay the cost, or part of the cost, of renting (leasing) residential premises | 2026 | An act of the Cabinet of Ministers of Ukraine adopted | Ongoing | Ministry of Social Policy The housing-rental subsidy is provided in accordance with Resolution of the Cabinet of Ministers of Ukraine No. 1225 of 25.10.2024, "On Implementing a Pilot Project to Provide a Subsidy for Paying the Cost, or Part of the Cost, of Renting (Leasing) Residential Premises (Part of Residential Premises), and Compensation for Part of Personal Income Tax or the Single Tax and the Military Levy." The Ministry of Social Policy is currently drafting amendments to this resolution, aimed at improving the mechanism for implementing the pilot project and introducing compensation for housing-rental intermediary service fees. |  |  |  |  |
| 56. Developing and implementing local programmes for the adaptation and integration of internally displaced persons into the social and economic environment of their place of residence | Developing and implementing local programmes for the adaptation and integration of internally displaced persons into the social and economic environment of their place of residence | 2025 | programmes for the adaptation and integration of internally displaced persons operating in all regions and territorial communities. |  | Vinnytsia Oblast In the oblast, local programmes provide social support to various categories of citizens, including internally displaced persons, in the form of material cash assistance and social support in the form of food packages. For the social protection, integration and adaptation of IDPs in the oblast's host communities, 81 local IDP support programmes have been approved. In 63 programmes, IDP social-protection issues are addressed within targeted social-protection programmes for the population, of which 9 include separate provisions for IDP support. In 14 communities, local IDP social-protection programmes have been approved. In 4 communities, programmes supporting IDPs' housing rights have been approved. By Order of the Head of the Oblast Military Administration No. 1062 of 04 August 2023, the Oblast Targeted Programme for Supporting Internally Displaced Persons for the period 2023–2027 was approved. Dnipropetrovsk Oblast The Comprehensive Programme for Supporting Internally Displaced Persons in Dnipropetrovsk Oblast for 2026–2028 has been approved. Donetsk Oblast In 2025, the Regional Programme for Supporting and Integrating Internally Displaced Persons for 2024–2025 was in force, approved by Order No. 372/5-24 of the Head of the Oblast State Administration, Head of the Oblast Military Administration, of 10.06.2024. With the assistance of the Oblast State Administration, in 2025 local IDP support programmes were developed and approved in 5 district state administrations/district military administrations and 46 territorial communities of the oblast. Zhytomyr Oblast By Order of the Zhytomyr Oblast Military Administration No. 1264 of 17.11.2025, "On the Comprehensive Programme for Social Support of Internally Displaced Persons for 2026–2027," funding of UAH 10.0 million has been planned for the programme's measures. The Programme includes measures on: informing IDPs; organizing the provision of social services; realizing IDPs' housing and property rights; setting up sites for temporary IDP accommodation; forming a housing fund for temporary IDP accommodation in the oblast's territorial communities; organizing free meals; organizing free provision of sanitary/hygiene and durable-use items; organizing employment and vocational training; and paying financial support to internally displaced persons toward repaying part of the principal on mortgage loans. A similar programme was in force in 2023–2025. Similar programmes also exist in the oblast's territorial communities. Zakarpattia Oblast The following have been developed and are in force in the oblast: 1) the Comprehensive Programme for Supporting Internally Displaced Persons in Zakarpattia Oblast for 2023–2025, approved by Order No. 785 of the Head of the Oblast State Administration – Head of the Oblast Military Administration of 04.09.2023 (as amended), which includes measures for realizing IDPs' housing and property rights, IDP employment, IDP social-protection measures, information activities, and the provision of educational, medical, psychological and cultural services; the Comprehensive Programme has been extended to 2026–2028 pursuant to Order No. 819 of 03.12.2025; 2) the Programme for Setting Up Temporary Accommodation Sites for Internally Displaced Persons, Servicemembers of the Armed Forces of Ukraine, and Their Family Members Who Are Internally Displaced, in Zakarpattia Oblast for 2024–2025, approved by Order No. 1010 of the Head of the Oblast State Administration – Head of the Oblast Military Administration of 20.11.2023 (as amended); 3) the Programme for Compensating Part of the Interest Rate on Mortgage Loans Obtained under the "yeOselia" State Programme in Zakarpattia Oblast for 2023–2027, approved by Order No. 420 of 03.05.2023; 4) the Programme for Improving the Housing Conditions of Residents of Zakarpattia Oblast and Servicemembers of the Armed Forces of Ukraine and Their Family Members through the Preferential Lending Programme "Vlasnyi Dim" ("Own Home") for 2021–2025, approved by Oblast Council Decision No. 1835 of 01.10.2020; and 5) the Regional Programme for Sustained Psychosocial Support of the Population Affected by Russian Aggression, "Ty Yak?" ("How Are You?"), for 2023–2025, approved by Order No. 570 of 12.06.2023. 67 programmes including IDP support measures have been developed and are in force in 41 territorial communities of the oblast. Zaporizhzhia Oblast The oblast has in force the Comprehensive Programme for Supporting Internally Displaced Persons in Zaporizhzhia Oblast for the period 2025–2026 (approved by Order No. 1003 of the Head of the Oblast State Administration, Head of the Oblast Military Administration, of 24.11.2024, as amended), whose measures are aimed, among other things, at adapting and integrating internally displaced persons into the social and economic environment of their place of residence. In addition, territorial communities located in the government-controlled territory of the oblast (including relocated ones) continuously develop and implement local programmes aimed at meeting IDP needs in various areas. UAH 6,175.84 thousand from the oblast budget and UAH 184,032.1 thousand from local budgets of territorial communities were allocated to implement the above-mentioned measures in 2025. Ivano-Frankivsk Oblast In 2025, 18 targeted IDP support programmes were in force in the oblast: 1 at the oblast level and 17 in territorial communities, along with 30 programmes containing separate IDP support measures. Kyiv Oblast To adapt and integrate internally displaced persons into the social and economic environment of their place of residence, during 2025 measures were implemented under the Kyiv Oblast Targeted Programme "Support for Internally Displaced Persons for 2023–2025," approved by Kyiv Oblast Council Decision No. 553-18-VIII of 09 June 2023 (as amended). The Kyiv Oblast Targeted Programme "Integration of Internally Displaced Persons" for 2026–2027 was approved by Kyiv Oblast Council Decision No. 1469-34-VIII of 23.10.2025. Kirovohrad Oblast During 2025, the Regional Programme for Supporting and Integrating IDPs of Kirovohrad Oblast until 2025 (hereinafter — the Regional Programme) was in force, approved by Order No. 779-r of the Head of the Oblast Military Administration of 17 July 2023. Local IDP programmes have been developed in 48 of 49 communities. Under the Regional Programme, in 2025 one-time material assistance totalling UAH 10 million was provided to specific categories of the IDP population, namely large families, persons with Group I and II disabilities, and persons aged 80 and over. Since the start of 2026, a Regional Programme for Supporting and Integrating Internally Displaced Persons for 2026–2028 has been developed and approved by Order No. 435-r of the Head of the Oblast Military Administration of 09 March 2026, and local self-government bodies have been recommended to approve corresponding local programmes and allocate funds for the programme's implementation in local budgets for the period 2026–2028. Luhansk Oblast The Oblast Comprehensive Targeted Programme for Supporting Internally Displaced Persons until 2025 has been implemented. Lviv Oblast In 2025, the oblast implemented the oblast targeted programme "Comprehensive Programme for Supporting Internally Displaced Persons for the Period of Martial Law in Ukraine," under which partial cash compensation was provided to IDP families in Lviv Oblast to reimburse preferential loans for participants in the "Housing for IDPs" programme. Mykolaiv Oblast By Order No. 166-r of the Head of the Mykolaiv Oblast Military Administration of 28.04.2023, the Comprehensive Programme for Implementing Regional Policy on Internal Displacement until 2025 in Mykolaiv Oblast was approved, providing for measures to further consolidate the forces and capabilities of all branches of government and local self-government, aimed at: reducing the impact of negative consequences of internal displacement caused by armed aggression against Ukraine on Ukrainian citizens; introducing mechanisms for responding to challenges arising from displacement; realizing the rights of internally displaced persons, ensuring access to administrative, social, educational, medical, cultural and other services, and creating conditions for developing the potential and strengthening the capacity of internally displaced persons in host territorial communities. The Programme also includes a separate section on ensuring IDP employment, and a measure to assess potential challenges and conflicts in order to strengthen social cohesion. IDP support, adaptation and integration programmes have also been adopted in 52 territorial communities of the oblast. Odesa Oblast In 2025, to adapt and integrate internally displaced persons into the social and economic environment of their place of residence, corresponding local programmes are being implemented in 32 territorial communities of Odesa Oblast, and corresponding measures are included in the socio-economic development programmes of the relevant communities. Their implementation ensures measures aimed at adapting and integrating internally displaced persons, carried out by executive authorities in cooperation with local self-government bodies, taking into account IDPs' current needs and territorial development characteristics. These measures cover the provision of social services, assistance with housing, access to education and medical services, and employment support. UAH 24,354.793 thousand was allocated in 2025 for implementing local IDP adaptation and integration programmes. Poltava Oblast The oblast has in force the Oblast Comprehensive Programme for Supporting Internally Displaced Persons for 2025–2027. In 2025, local (targeted or comprehensive) IDP support programmes were in force in 32 communities. In 27 communities, IDP support measures are implemented within general social-protection programmes. Rivne Oblast In 2025, under the Comprehensive Programme for Supporting Internally Displaced Persons in Rivne Oblast for the period 2023–2025 (Order No. 307 of the Head of the Oblast State Administration – Head of the Oblast Military Administration of 04.07.2023, as amended), UAH 100 million was allocated from the oblast budget to ensure proper conditions for residents of residential-care institutions from among internally displaced persons. To create conditions and opportunities for housing, proper living conditions, methodological assistance, and outreach on IDPs' rights and opportunities, the oblast has in force the Programme for Providing Housing to Internally Displaced Persons in Rivne Oblast for 2025–2027 (Order No. 222 of the Head of the Oblast State Administration – Head of the Oblast Military Administration of 23.04.2025, as amended). 64 local IDP support programmes are being implemented in the oblast's territorial communities (Varash District — 6, Dubno District — 18, Rivne District — 30, Sarny District — 10), providing for material assistance, meals for children, improved living conditions, and support for IDP adaptation. Sumy Oblast The Oblast Comprehensive Programme for Supporting Internally Displaced Persons for 2025–2026 was approved by Order No. 754-OD of the Head of the Sumy Oblast State Administration – Head of the Oblast Military Administration of 20.12.2024, addressing conditions for the proper integration of displaced persons at their new place of residence in Ukraine. Corresponding programmes have been adopted at the local level. The programmes provide for conducting IDP needs assessments, providing informational and social services according to individual needs to support adaptation to new living conditions, organizing and carrying out cultural-integration and adaptation measures, and providing material and humanitarian assistance at the local level. Ternopil Oblast By Order No. 321/01.02-01 of the Head of the Oblast Military Administration of 16.06.2023, an operational action plan was approved for implementing, in 2023–2025, the Strategy of State Policy on Internal Displacement until 2025, providing for: assessing IDP needs; psychosocial support; engagement in the cultural life of territorial communities and access to cultural services; ensuring access to educational services and physical activity/sport; carrying out vocational training/retraining measures and supporting employment and self-employment; forming housing funds for temporary accommodation; and providing accessible housing that accounts for needs, capacities and vulnerability criteria. The oblast has also approved a comprehensive programme for social support of specific categories of citizens for 2025–2027, aimed at creating favourable social and living conditions and providing social support to specific categories of the oblast's residents; UAH 32.2 million has been allocated for implementing this programme's measures in 2025. The programme provides for monthly assistance to families of fallen (deceased) Defenders of Ukraine. Since the start of 2025, UAH 531,000 in monthly assistance has been paid to families of fallen (deceased) Defenders of Ukraine from among IDPs. Targeted IDP support programmes have been established in 9 territorial communities of the oblast, and comprehensive programmes including IDP support are in force in 46 communities. Kharkiv Oblast The Kharkiv Oblast Military Administration has developed a Comprehensive Programme for Supporting Internally Displaced Persons in Kharkiv Oblast for the period 2023–2027 (hereinafter — the Comprehensive Programme), approved by Oblast Council Decision No. 673-VIII of 05.10.2023. The Comprehensive Programme's measures provide for: ensuring proper living conditions at IDP temporary-accommodation sites; providing financial support to IDPs registered for housing; addressing IDP employment and self-employment; and covering internally displaced persons with social, medical and educational services and their participation in cultural events, among other things. According to the latest data, 17 local IDP support programmes were in force in the oblast. Kherson Oblast The oblast has in force a Comprehensive Programme for Supporting Internally Displaced Persons in the Territory of Kherson Oblast for the Period of Martial Law in Ukraine. Similar IDP support programmes have been approved by all territorial communities of the oblast. Khmelnytskyi Oblast Last year, the oblast had in force the Oblast Comprehensive Programme for Supporting Internally Displaced Persons in Khmelnytskyi Oblast for 2024–2025 (Order of the Oblast Military Administration No. 305/2023-n of 21.11.2023) and local IDP support programmes in 47 territorial communities of the oblast. A new regional IDP support programme will be approved in 2026. Cherkasy Oblast By Decision No. 33-12/VIII of Cherkasy Oblast Council of 28.11.2025, the Oblast Comprehensive Programme for Supporting Internally Displaced Persons for the period 2026–2028 was approved. The programme's aim is to ensure the realization of IDPs' rights and the fulfilment of their needs, improve their living conditions, promote their further integration, and ensure full access to administrative, social, cultural and other services. IDP support programmes are in force in all districts and territorial communities of the oblast. UAH 5.1 million was used to implement the oblast programme in 2025. A total of UAH 640 million from local budgets of Cherkasy Oblast was used to fund IDP support measures in 2022–2025. Chernivtsi Oblast To ensure proper conditions for realizing the socio-economic and personal rights and freedoms of forcibly displaced persons, Order No. 1340-r of the Oblast State Administration (Oblast Military Administration) of 05 December 2024 approved the "Comprehensive Programme for Supporting and Integrating Internally Displaced Persons and Other War-Affected Persons for 2025." IDP adaptation and integration programmes have been approved by 32 territorial communities (61.5%). Chernihiv Oblast Chernihiv Oblast has in force the Oblast Programme for Supporting Internally Displaced Persons in Chernihiv Oblast for 2025–2026. 27 local programmes aimed at ensuring IDPs' rights and freedoms were in force in 25 territorial communities of the oblast. | Donetsk Oblast 7021,58 Zakarpattia Oblast A total of UAH 58.17 million was allocated from the oblast budget and UAH 45.70 million from the budgets of territorial communities to finance measures supporting internally displaced persons (IDPs). Funding provided through oblast budget programmes included: 1.UAH 641.8 thousand; 2.UAH 8.51 million; 3.UAH 640.1 thousand; 4. UAH 1.45 million; 5.Additional funding provided within the framework of oblast budget pro Luhansk Oblast 7935,998 Sumy Oblast 81910,2 | Donetsk Oblast 732720,7 Zhytomyr Oblast 10000,0 Zaporizhzhia Oblast 190207,9 Ivano-Frankivsk Oblast 5000,0 1791,7 17855,3 Kyiv Oblast 21457,7 Luhansk Oblast 76628,284 Lviv Oblast 672,7 Mykolaiv Oblast 215831,3 Odesa Oblast 10570,085 Rivne Oblast 121392,5 Sumy Oblast 13440 Khmelnytskyi Oblast 99100,0 Chernivtsi Oblast 13877,5 | Donetsk Oblast 38885,2 Ivano-Frankivsk Oblast 19,0 Luhansk Oblast 15317,7 Sumy Oblast 20693,3 Chernihiv Oblast 43393,2 | Luhansk Oblast In 2025, 47 measures under the programme were implemented, while 17 remained unimplemented. This is because implementation of certain measures is planned for after the de-occupation of the oblast's settlements, and for some measures there are no investors or funding available. Odesa Oblast In implementing these measures, certain problem issues exist, including limited local-budget financial resources, uneven capacity levels among territorial communities for developing and implementing comprehensive programmes, growing IDP needs for social and housing services, and limited employment opportunities for IDPs in certain communities. In addition, coordination between executive authorities, local self-government bodies, and other service providers needs further strengthening, along with broader IDP access to vocational-training and retraining programmes. |
| Area: "Veterans and Servicemembers" |  |  |  |  |  |  |  |  |  |
| 57. Creating conditions at the local and regional level for effective readaptation and socio-economic reintegration of war veterans | 1) Ensuring the provision of professional adaptation services to war veterans and their family members | 2025-2027 | professional adaptation services provided to no fewer than 5,000 war veterans and their family members annually | Ongoing on a continuous basis. | Ministry of Veterans Affairs Professional adaptation services were received by 1,334 individuals. Ministry of Economy. In 2025, the State Employment Service ensured the provision of professional adaptation services to war veterans, including combat participants. In order to increase their competitiveness on the labour market, 890 individuals received vouchers for training, and 1,046 individuals underwent professional training in various areas of training and retraining, which contributed to the acquisition of new professional competencies and improved prospects for further employment. | Ministry of Veterans Affairs 16819,7 | - | - | - |
|  | 2) Ensuring the operation of specialists supporting war veterans and demobilized persons in territorial communities | 2025-2027 | At least 11,000 people employed as specialists supporting war veterans and demobilized persons | Ongoing on a continuous basis. | Ministry of Veterans Affairs 2,323 people have been employed as specialists supporting war veterans and demobilized persons. | 498 073,7 |  |  |  |
|  | 3) Ensuring the participation of the national team of Ukraine in international sporting competitions, including the "Invictus Games" and the "Warrior Games” | 2025-2027 | participation of the national team of Ukraine in the corresponding events ensured | Completed | Ministry of Veterans Affairs Participation of war veterans in 3 international sporting competitions was ensured, namely: the international sporting competition "Invictus Games"; the international sporting competition "Strong Spirit's Games"; and the international sporting competition "ABU DHABI WORLD PROFESSIONAL JIU-JITSU CHAMPIONSHIP." | 11 467,8 |  |  |  |
| 58. Ensuring the accessibility of psychological assistance and rehabilitation for persons being discharged or discharged from military service from among war veterans, persons a#ected by hostilities, and persons for whom the fact of deprivation of personal liberty as a result of armed aggression against Ukraine has been established | 1)Ensuring the provision of quality psychological assistance services to war veterans and their family members, as well as to persons for whom the fact of deprivation of personal liberty as a result of the Russian Federation's armed aggression against Ukraine has been established | 2025-2027 | psychological assistance services provided to at least 23,000 war veterans and their family members annually. | Ongoing on a continuous basis | Ministry of Veterans Affairs Psychological assistance services were provided to 5,978 people. | 18 911,2 | - | - | - |
|  | 2) Ensuring the operation and population of the Register of Providers of Psychological Assistance Services for Veterans and Their Family Members | 2027 | 27 psychological-assistance service providers included in the register. Status: Not implemented | Not started | The implementation deadline has not yet arrived. |  |  |  |  |
|  | 3) Conducting training, retraining, and professional development for psychologists/specialists providing psychological assistance to war veterans and their family members | 2025-2027 | проведено навчання, перепідготовку та підвищення кваліфікації не менш як 200 фахівців | Ongoing on a continuous basis | Ministry of Veterans Affairs In 2025, online training was held at the "Borodianka" Scientific-Educational Expert Centre, attended by 249 psychologists, for professional development of specialists included in the Register of Providers of Psychological Assistance Services for Veterans and Their Family Members. | - | - | - | - |
|  | 4) Developing an online course on ensuring the accessibility of psychological assistance for DSNS personnel being discharged or discharged from service, from among war veterans, persons affected by hostilities, and persons for whom the factof deprivation of personal liberty as a result of armed aggression against Ukraine has been established | 2025 | an online course created, and training provided for at least 300 DSNS specialists | Completed | Ministry of Internal Affairs (MIA). DSNS psychologists have developed and implemented online courses aimed at ensuring the accessibility of psychological assistance for DSNS personnel being discharged or already discharged from service, including war veterans, persons a#ected by hostilities, and persons for whom the fact of deprivation of personal liberty as a result of armed aggression against Ukraine has been established. The online courses are informational/educational and practically oriented in nature, aimed at supporting psychological health, easing adaptation to civilian life, and raising awareness of opportunities to receive professional psychological assistance. Links to the online courses are freely available on DSNS's o'cial page and its YouTube social media channel. |  |  |  |  |
|  | 5) Expanding population access to rehabilitation assistance in healthcare at the territorial-community level | 2025-2027 | outpatient rehabilitation assistance provided at 100 percent of general healthcare institutions. | Completed | Ministry of Health of Ukraine Regulatory frameworks for community-level rehabilitation have been introduced, and measures have been taken to contract general healthcare institutions for outpatient rehabilitation, ensuring the provision of this type of rehabilitation assistance. The Ministry of Health, together with the National Health Service of Ukraine, is carrying out systematic work to build an extensive network for providing rehabilitation assistance to children in outpatient settings, based on a capable network of healthcare institutions. This approach ensures the accessibility of rehabilitation services for the child population, continuity of the rehabilitation process, and the ability to receive assistance as close as possible to the child's and their family's place of residence. As of December 2025, 531 healthcare institutions had concluded agreements with the National Health Service of Ukraine within the medical-services package for "Rehabilitation Assistance for Adults and Children in Outpatient Settings." This number of providers indicates a well-established and territorially balanced outpatient rehabilitation network, covering various levels of medical care and ensuring timely access to rehabilitation services for children regardless of their region of residence. An important element in developing the outpatient rehabilitation network is the introduction of a rehabilitation mono-service, provided by individual rehabilitation specialists in outpatient settings according to a child's individual needs. This format of assistance allows flexible responses to family requests, ensures regularity of rehabilitation interventions, and optimizes the use of healthcare-system resources. The rehabilitation mono-service is particularly important for children requiring long-term dynamic monitoring and correction of functional impairments without the need for an inpatient rehabilitation stage. Resolutions of the Cabinet of Ministers of Ukraine No. 132 of 7 February 2025, "On Amending the Procedures Approved by Resolutions of the Cabinet of Ministers of Ukraine No. 1268 of3 November 2021 and No. 1462 of 16 December 2022," and No. 1438 of 7 November 2025, "On Amending Resolutions of the Cabinet of Ministers of Ukraine No. 1268 of 3 November 2021 and No. 1462 of 16 December 2022," have been adopted, regulating the mono-professional rehabilitation service. | - | - | - | - |
| Strategic Goal: "Increasing the Level of Regional Competitiveness" |  |  |  |  |  |  |  |  |  |
| Operational Goal 1. Infrastructure resilient to security, social and economic challenges |  |  |  |  |  |  |  |  |  |
| Напрям «Транспортна інфраструктура» Area: "Transport Infrastructure" |  |  |  |  |  |  |  |  |  |
| 59. Developing public-transport and cycling infrastructure in territorial communities | Developing comprehensive spatial development plans for the territories of territorial communities that take public-transport infrastructure into account | 2025-2027 | draft comprehensive plans developed in at least 50 territorial communities. |  | Vinnytsia Oblast In accordance with current state building regulations, a comprehensive spatial development plan for the territories of territorial communities (hereinafter — CSDP) contains a thematic textual and graphical section, "Transport Mobility and Infrastructure," reflecting the road network and internal/external transport facilities and structures. This section is included in the approved CSDP of Vinnytsia city territorial community. Decisions to develop a CSDP have been adopted in 19 territorial communities of the oblast. Dnipropetrovsk Oblast 16 territorial communities have adopted decisions to develop comprehensive spatial development plans for the territories of territorial communities. Zakarpattia Oblast Currently, no draft comprehensive plans exist in the oblast's territorial communities. Zaporizhzhia Oblast As of now, 4 territorial communities of Zaporizhzhia District (Vilniansk city, Kushuhum settlement, and Mykhailo-Lukashove and Shyrokivka rural territorial communities) have adopted decisions to develop comprehensive spatial development plans for their territories, taking public-transport infrastructure into account, among other things (hereinafter — the Comprehensive Plan). In response to requests from Kushuhum settlement and Vilniansk city territorial communities, the Oblast State Administration provided information on identifying state interests to be taken into account when developing the Comprehensive Plans (letters dated 15.05.2025 No. 06054/08-27 and 05.09.2025 No. 12062/08-19, respectively); a corresponding request from Shyrokivka rural territorial community is currently being processed. Ivano-Frankivsk Oblast. Development of the comprehensive spatial development plan for the territory of Ivano-Frankivsk city territorial community has begun, with completion planned for 2027. Kyiv Oblast Comprehensive spatial development plans are being developed for 8territorial communities (Boguslav, Obukhiv, Dymer, Kotsyubynske, Kalyta, Hatne, Pirnove, and Tashan territorial communities). Kirovohrad Oblast. As of 1 January 2026, 20 decisions to develop comprehensive spatial development plans for the territories of territorial communities have been adopted in Kirovohrad Oblast Luhansk Oblast Implementation of this measure with respect to cycling-infrastructure development is not currently under way owing to the temporary occupation of most of the oblast's territory. Implementation will begin without delay once the territories are de-occupied, priority stabilization measures are carried out, demining is completed, and proper security conditions are created for the resumption of state authority and business-entity operations. Mykolaiv Oblast As of 31.12.2025, comprehensive spatial development plans for the territories of territorial communities have not been developed in the oblast; local self- government bodies are working on developing such plans (legislation provides for extending the deadline for developing comprehensive spatial development plans for territorial communities until 2028). Poltava Oblast 35 communities have begun work on developing a CSDP: in 4 communities, a developer has been selected and development is under way; in 5 communities, working groups have been established to approve the terms of reference; in 26 communities, a decision to develop a plan has been adopted. Rivne Oblast The oblast is developing comprehensive spatial development plans for the territories of territorial communities (CSDPs), which take public-transport infrastructure into account. Development of CSDPs in Shpaniv and Varash territorial communities is at the final stage. A further 20 territorial communities of the oblast have adopted decisions to develop CSDPs and are carrying out organizational measures to prepare baseline data and select developers of urban-planning documentation. Sumy Oblast. Development of comprehensive spatial development plans for the territories of territorial communities takes public-transport infrastructure into account. 7 territorial communities of the oblast have begun developing comprehensive spatial development plans. Ternopil Oblast As of January 2026, 12 communities of the oblast (Baikivtsi, Berezhany, Bilobozhnytsia, Bilche-Zolote, Borshchiv, Ivane-Pusteme, Velyka Berezovytsia, Zalishchyky, Kopychyntsi, Tovste, Pidvolochysk, and Chortkiv communities) have adopted decisions to develop comprehensive spatial development plans. All communities are at the decision-adopted stage; only Zalishchyky community has formulated terms of reference for a comprehensive spatial development plan, and Baikivtsi community has begun collecting information for developing one. Kharkiv Oblast Comprehensive spatial development plans for the territories of three territorial communities — Rohan, Pisochyn, and Solonytsivka — have been developed.Kherson Oblast. Local territorial communities in the oblast's de-occupied territories have developed comprehensive territorial recovery programmes providing for the development of public-transport and cycling infrastructure. Khmelnytskyi Oblast As of 01.01.2026, 2 comprehensive spatial development plans taking public-transport infrastructure into account have been developed: Medzhybizh territorial community — its comprehensive spatial development plan was approved in 2024; Sataniv territorial community — a draft comprehensive spatial development plan has been developed, with approval planned for 2026. Cherkasy Oblast. In 2025, in Shpola (Zvenyhorodka District), Korsun-Shevchenkivskyi, Ruska Poliana, and Bilozirka (Cherkasy District) territorial communities, measures for developing comprehensive spatial development plans were carried out at various preparation stages, including forming baseline data, developing terms of reference, concluding contracts, and preparing design documentation. Chernihiv Oblast 1 comprehensive plan has been developed. | Dnipropetrovsk Oblast 2009,8 Poltava Oblast 2611,9 Rivne Oblast 1936,1 Khmelnytskyi Oblast 2094,5 | Dnipropetrovsk Oblast 250,00 Kyiv Oblast 21000,0 Poltava Oblast 6254,0 Rivne Oblast 13134,8 Khmelnytskyi Oblast 865,6 Chernihiv Oblast 5547,8 | Chernihiv Oblast 8000,0 | Vinnytsia Oblast Limited local-budget funds for developing urban-planning documentation. Dnipropetrovsk Oblast In 2023, the remaining UAH 1,466.050 of state subvention funds were returned to the state budget. Resolution of the Cabinet of Ministers of Ukraine No. 853 of 28.07.2021 has ceased to apply. Donetsk Oblast Currently, all settlements of Donetsk Oblast are located less than 100 kilometres from the administrative boundary between temporarily occupied territory and other Ukrainian territory where hostilities are taking place, and from the line of contact. Given the unfavourable living conditions that have arisen, developing urban- planning documentation is impossible or impractical. Kyiv Oblast Owing to limited funding capacity of territorial-community budgets and the Kyiv Oblast budget for developing comprehensive spatial development plans, as of 01.01.2026 only 12% of the oblast's territorial communities had begun developing such documents. This issue can only be resolved through state-budget subventions and international technical assistance funding. Luhansk Oblast. Pursuant to Order No. 376 of the Ministry for Development ofCommunities and Territories of Ukraine of 28.02.2025, most of Luhansk Oblast is classified as temporarily occupied territory, and the rest as an area of active hostilities. Implementation of this measure is therefore possible only after the oblast's territories are de-occupied, active hostilities cease, and security and stabilization measures are carried out. Poltava Oblast The long timeframes and high cost of developing a CSDP require co- financing from the state budget and other sources. |
| 60. Restoring and developing the export-logistics system | Creating conditions for implementing the "Maritime Single Window" information system, with its subsequent integration with the information systems of fiscal and regulatory authorities | 2027 | conditions created for implementing the "Maritime Single Window" information system. | Not started | The implementation deadline has not yet arrived. |  |  |  |  |
| Area: "Comfortable Communities" |  |  |  |  |  |  |  |  |  |
| 61. Implementing modern urban and territorial planning practices that take into account the principles of inclusiveness | Updating building regulations for territorial planning and development to incorporate principles of inclusiveness | December 2025 | the state building regulations "Inclusiveness of Buildings and Structures: Basic Provisions" updated | Completed | Ministry for Communities, Territories and Infrastructure Development Amendment No. 3 to DBN B.2.2-40:2018, "Inclusiveness of Buildings and Structures. Basic Provisions," was approved by Order of the Ministry for Communities, Territories and Infrastructure DevelopmentNo. 1617 of 20.11.2025. The amendments took effect on 1 April 2026 and are aimed at strengthening barrier-free-accessibility requirements, including clarified requirements for entrance areas, movement paths, parking spaces, and sanitary/hygiene facilities. |  |  |  |  |
| 62. Implementing and updating the "yeVidnovlennia" ("eRecovery") electronic public service | Developing and submitting to the Cabinet of Ministers of Ukraine a draft resolution amending certain resolutions of the Cabinet of Ministers of Ukraine regarding the restoration of certain categories of real-estate objects damaged as a result of hostilities, terrorist acts, or sabotage caused by the Russian Federation's armed aggression against Ukraine, and the provision of compensation for damaged property | 2025 | a resolution of the Cabinet of Ministers of Ukraine adopted | Completed | Ministry for Communities, Territories and Infrastructure Development The "yeVidnovlennia" ("eRecovery") electronic public service is improved as needed; regulatory acts governing compensation for damaged/destroyed real property areimproved through amendments. In particular, in 2025 the Ministry for Communities, Territories and Infrastructure Development prepared the following government resolutions: No. 296 of 14 March 2025, "On Amending Certain Resolutions of the Cabinet of Ministers of Ukraine Regarding the Restoration of Certain Categories of Real-Estate Objects Damaged as a Result of Hostilities, Terrorist Acts, or Sabotage Caused by the Russian Federation's Armed Aggression, and the Provision of Compensation for Such Objects"; No. 359 of 31 March 2025, "On Amending the Procedure for Providing Compensation for Destroyed Real-Estate Objects"; No. 802 of 7 July 2025, "On Amending the Procedure for Providing Compensation for the Restoration of Certain Categories of Real-Estate Objects Damaged as a Result of Hostilities, Terrorist Acts, or Sabotage Caused by the Russian Federation's Armed Aggression, Using the 'yeVidnovlennia' Electronic Public Service"; No. 815 of 7 July 2025, "Certain Issues Concerning the Remote Inspection of Destroyed Certain Categories of Real-Estate Objects Located in Areas of Possible Hostilities for Which No Date for the Cessation of Possible Hostilities Has Been Determined, in Areas of Active Hostilities, and in Areas of Active Hostilities Where State Electronic Information Resources Operate, for Which No Date for the End of Hostilities Has Been Determined"; No. 864 of 15 July 2025, "Certain Issues Concerning the Implementation of the 'Housing Repair for the Restoration of People's Rights and Opportunities (HOPE)' Project"; No. 1525 of 26 November 2025, "On Amending the Procedure for Providing Compensation for the Restoration of Certain Categories of Real-Estate Objects Damaged as a Result of Hostilities, Terrorist Acts, or Sabotage Caused by the Russian Federation's Armed Aggression, Using the 'yeVidnovlennia' Electronic Public Service"; No. 1646 of 12 December 2025, "On Amending Annex 2 to the Procedure for Providing Compensation for the Restoration of Certain Categories of Real-Estate Objects Damaged as a Result of Hostilities, Terrorist Acts, or Sabotage Caused by the Russian Federation's Armed Aggression, Using the 'yeVidnovlennia' Electronic Public Service"; and No. 1645 of 15 December 2025, "On Amending Annex 3 to the Procedure for Providing Compensation for Destroyed Real-Estate Objects." |  |  |  |  |
| 63. Modernizing, adapting and decarbonizing centralized district-heating systems | Reviewing and approving heat-supply schemes for settlements with a population exceeding 20,000, and/or regional heat-supply-system modernization programmes submitted by local self-government bodie | 2025—2027 | at least five heat-supply schemes processed | Completed | Ministry for Communities, Territories and Infrastructure Development The Ministry for Communities, Territories and Infrastructure Development’Commission for Reviewing Heat-Supply Schemes of Settlements with a Population Exceeding 20,000 and/or Regional Heat-Supply-System Modernization Programmes has, since 01 January 2025, approved 9 settlement heat-supply schemes, namely for: Lviv, Cherkasy, Kovel (Rivne Oblast), Dnipro, Zaporizhzhia, Ternopil, Varash (Rivne Oblast), Kryvyi Rih (Dnipropetrovsk Oblast), and Chernihiv. |  |  |  |  |
| 64. Implementing projects to increase the energy efficiency of state- and municipally-owned residential buildings | 1) Ensuring independent monitoring of energy certificates | 2025—2027 | at least 30 independent energy-certificate monitoring conclusions prepared | Completed | State Agency on Energy Efficiency and Energy Saving of Ukraine (Derzhenerhoefektyvnosti) Independent monitoring was carried out for 77 residential-building energy certificates, with corresponding independent monitoring conclusions prepared (letter dated 15.01.2026, No. 5-1.2/2.3/07-26). |  |  |  |  |
|  | 2) Ensuring implementation of the "EnerhoDIM" Support Programme for the Energy Modernization of Multi-Apartment Buildings | 2025-2027 | at least 235 projects implemented | Completed | Ministry for Communities, Territories and Infrastructure Development By letter dated 30.12.2025, No. 01/18/689/25, the State Institution "Energy Effciency Fund" informed the Ministry for Communities, Territories and Infrastructure Development that, as of 26 December 2025, 593 projects had been implemented under the "EnerhoDIM" programme, with construction works fully completed. |  |  |  |  |
|  | 3) Ensuring implementation of the "VidnovyDIM" ("RestoreHOME") programme | 2025-2027 | at least 150 projects implemented | Completed | Ministry for Communities, Territories and Infrastructure Development By letter dated 30.12.2025, No. 01/18/689/25, the State Institution "Energy Efficiency Fund" informed the Ministry for Communities, Territories and Infrastructure Development that, as of 26 December 2025, 757 completed projects had been implemented under the "VidnovyDIM" programme. |  |  |  |  |
|  | 4) Ensuring implementation of the "GreenDIM" programme to increase the share of renewable energy in domestic electricity and heat production systems | 2025-2026 | at least 81 projects implemented | Completed | Ministry for Communities, Territories and Infrastructure Development By letter dated 30.12.2025, No. 01/18/689/25, the State Institution "Energy Efficiency Fund" informed the Ministry for Communities, Territories and Infrastructure Development that, as of 26 December 2025, 155 completed projects had been implemented under the "GreenDIM" programme. |  |  |  |  |
| 65. Developing energy-service instruments for the modernization of housing and communal services facilities | oncluding energy-service agreements at housing and communal services facilities | 2026 | at least three energy-service contracts concluded | Not started | The implementation deadline has not yet arrived. |  |  |  |  |
| 66. Ensuring the accessibility of quality centralized water-supply and wastewater services for various groups of citizens, taking into account the latest technologiesand the needs of territorial communities | Implementing energy-modernization measures at state- or municipally-owned water- supply and wastewater enterprises | 2025—2027 | at least five energy-modernization projects at water-supply and wastewater enterprises implemented |  | Ministry for Communities, Territories and Infrastructure Development The State Targeted Economic Programme for the Energy Modernization of State- and Municipally-Owned Water-Supply and Wastewater Enterprises for the Period until 2030 (hereinafter — "Enerhovoda") is aimed at addressing critical-infrastructure problems. Its development and implementation are integrated into the national strategic-planning system, in particular through the Action Plan for 2025–2027 for implementing the State Strategy for Regional Development for 2021–2027, approved by Order of the Cabinet of Ministers of Ukraine No. 1047-r of 25 September 2025 (hereinafter — Order No. 1047-r). This programme, approved by Order of the Cabinet of Ministers No. 1133-r of 15 November 2024, was adopted owing to the need to reduce the energy intensity of water- supply services — critically important given the shortage of energy resources and wartime challenges. It is one of the key mechanisms for implementing the tasks of the above-mentioned Action Plan, aimed at strengthening territorial-community capacity and modernizing life-support systems in line with European energy-e'ciency standards. The programme's main focus, within regional strategy implementation, is the sector's technological renewal through replacing outdated equipment, introducing automated management systems, and developing enterprises' own generation based on renewable energy sources. This approach helps ensure the sustainable operation of water-supply enterprises, reduce their financial dependence on budget subsidies, and increase the level of territorial communities' energy security, fully consistent with the priorities set out in Order No. 1047-r. Actual funding of the "Enerhovoda" programme in 2025 was provided from local budgets in the amount of UAH 655.2 million. This significantly exceeds the volumes planned under the programme (UAH 107.8 million) and is due to the need for urgent restoration of systems after destruction, ensuring service provision to consumers, and developing project documentation for future works. At the same time, UAH 2,447.6 million was financed from other sources (the contractor's own funds, grants, loans, etc.), also substantially exceeding the planned amount (UAH 66.3 million). This increase is driven by the need for energy resilience and reduced energy consumption by sector enterprises amid ongoing power-supply disruptions. |  |  |  |  |
| 67. Introducing new approaches to housing provision, drawing on best practices and the experience of EU member states | 1) Supporting the draft Law of Ukraine "On the Basic Principles of Housing Policy" (registration No. 12377 of 6 July 2025) in the Verkhovna Rada of Ukraine | 2025 | Law of Ukraine adopted | Completed | Ministry for Communities, Territories and Infrastructure Development The Law of Ukraine "On the Basic Principles of Housing Policy" was adopted by the Verkhovna Rada of Ukraine on 13 January 2026. |  |  |  |  |
|  | 2) Entry into force of amendments to the Law of Ukraine "On the Social Housing Fund" (or a new version of this Law) | 2026 | Law of Ukraine adopted | Started | Ministry for Communities, Territories and Infrastructure Development The first draft of the Law of Ukraine "On Social Housing" (a new version of the Law of Ukraine "On the Social Housing Fund") is being developed jointly with representatives and experts of international and civil-society organisations. Working meetings are being held to develop the provisions of the relevant draft law; in particular, on 1 April 2026 the Ministry, with support from the Delegation of the European Union to Ukraine and the European Investment Bank, held a working meeting devoted to discussing the conceptual foundations of the future Law of Ukraine "On Social Housing". On 6 May 2026, a working meeting was held with the participation of local self-government bodies and associations, Members of Parliament of Ukraine, representatives of central executive authorities, and international and national organisations, devoted to discussing the conceptual foundations for developing municipal social housing in Ukraine. |  |  |  |  |
|  | 3) Developing and submitting a draft State Housing Strategy to the Cabinet of Ministers of Ukraine | 2026 | Cabinet of Ministers act adopted | Started | Ministry for Communities, Territories and Infrastructure Development To ensure preparation of the State Housing Policy Strategy, by order of the Ministry No. 924 of 29 May 2025, "On Certain Issues of the Interagency Working Group on Developing the State Housing Policy Strategy", an Interagency Working Group on Developing the State Housing Policy Strategy was established, consisting of a Steering Committee and a Technical Working Group. On 17 March 2026, a meeting of the Interagency Working Group's Steering Committee was held, chaired by Deputy Prime Minister for Reconstruction — Minister for Communities and Territories Development of Ukraine Oleksii Kuleba, on presenting the strategic goals and key approaches of the future State Housing Policy Strategy. On 7 May 2026, the Ministry, with support from the World Bank and with the participation of representatives of state authorities and international partners, held a practical workshop, "National Housing Policy Strategy: Aligning Approaches and Developing Joint Solutions". The purpose of the event was to align the positions of key state authorities and international partners on the content of the draft State Housing Policy Strategy. |  |  |  |  |
|  | 4) Implementing the public investment project "Creating a Social Housing Fund" with support from the European Investment Bank | 2027 | construction (reconstruction) ensured | Started | Ministry for Communities, Territories and Infrastructure Development The investment project "Providing Housing for Residents of the Bakhmut City Territorial Community (with IDP Status) in Safe Regions of Ukraine" has been entered into the DREAM ecosystem, aimed at providing housing and accompanying social services. The project concept envisages dividing a quarter of part of the territory of the settlement of Hoshcha (approximately 6 hectares) into small-scale districts, constructing steel-frame housing, and creating landmarks and sites that existed in Bakhmut (Rose Alley, and an Embankment — an image of the Bakhmutka River rendered in luminescent material). In addition, Cabinet of Ministers Resolution No. 796 of 2 July 2025, "On Implementing a Pilot Project for Creating a Municipal (Social) Rental Housing Fund and Providing It for Rent", has been adopted, defining the mechanism for implementing the pilot project on creating a municipal (social) rental housing fund and providing it for rent. Measures are currently being taken to review applications from local self-government bodies wishing to participate in the pilot project, as well as to secure the Ministry of Finance's approval of the volume and terms of borrowing by local self-government bodies, in accordance with the procedure set out in Cabinet of Ministers Resolution No. 110 of 16 February 2011. |  |  |  |  |
|  | 5) Implementing the pilot project on creating a municipal (social) rental housing fund and providing it for rent | 2027 | report on the results of pilot project implementation submitted to the Cabinet of Ministers of Ukraine | Started | Ministry for Communities, Territories and Infrastructure Development Cabinet of Ministers Resolution No. 796 of 2 July 2025, "On Implementing a Pilot Project for Creating a Municipal (Social) Rental Housing Fund and Providing It for Rent", has been adopted. Measures are being taken to review applications from local self-government bodies wishing to participate in the pilot project on creating a municipal (social) rental housing fund. As part of the project's first stage, a pilot phase is planned for implementation with the European Investment Bank, with total blended financing of EUR 100 million, comprising EUR 50 million in grant financing from the European Commission and EUR 50 million in credit resources. The pilot phase is aimed at launching construction of the first municipal (social) rental housing facilities, as well as establishing the organisational, legal and financial mechanisms for implementing the project with a view to its subsequent scaling up. To accelerate implementation of the project's pilot phase, measures are being taken to secure the Ministry of Finance's approval of the volume and terms of borrowing by local self-government bodies, in accordance with the procedure set out in Cabinet of Ministers Resolution No. 110 of 16 February 2011, following the signing of the Financial and Grant Agreements between Ukraine and the European Investment Bank. |  |  |  |  |
|  | 6) Monitoring the implementation of local programmes concerning the social housing fund and the housing fund for temporary accommodation of citizens, including internally displaced persons | 2025—2027 | replenishment of the social housing fund and the housing fund for temporary accommodation of citizens by at least 20 percent secured | Started | Ministry for Communities, Territories and Infrastructure Development According to information provided by oblast military state administrations, the number of properties (apartments, housing units) classified under the social housing fund is 912, and the number of properties (apartments, housing units) classified under the housing fund for temporary accommodation is 3,383. |  |  |  |  |
| Area “Energy Infrastructure” |  |  |  |  |  |  |  |  |  |
| 68. Development of distributed electricity generation in territorial communities | facilitating the implementation of projects to install cogeneration units to provide electric and thermal energy | 2025—2026 | cogeneration units installed to provide electric and thermal energy with a total thermal capacity of 100 MW | Ongoing | Ministry of Energy The Ministry of Energy of Ukraine continuously conducts operational monitoring of the commissioning of gas-piston, gas-turbine, and cogeneration units based on information from regional military administrations, distribution system operators, and gas distribution network operators. Currently, Ukraine has equipment with a total capacity of 2,365 MW, of which 1,386 MW has already been commissioned. Vinnytsia oblast Within the framework of the Distributed Generation Development Strategy, in 2025 the oblast built more than 80 MW of new generating capacity, of which: the capacity of industrial solar power plants commissioned in 2025 was 11.4 MW; private household solar installations amounted to 11.75 MW connected to electricity and gas networks; and 15 cogeneration units with a capacity of over 60 MW. Volyn oblast In 2025–2026, 11 cogeneration units were installed and commissioned. Dnipropetrovsk oblast 8.604 MW. Donetsk oblast At the beginning of 2025, "Kramatorskteploenergo" LLC completed the commissioning of 3 cogeneration units (model JENBACHER JMC 420 GS-N.L) with a total capacity of 4.5 MW. All expenditures for the corresponding works were financed from the company's own funds and from the budget of the Kramatorsk municipal territorial community (MTC) in 2024. Zhytomyr oblast As of 01.01.2026, 18 cogeneration units with a total capacity of 29.27 MW were commissioned in the oblast. Zakarpattia oblast. A phased build-up of distributed generation is being ensured, along with the connection of new generating units to the networks and the implementation of technical solutions to improve the reliability of the power system's operation. The total installed generating capacity in the oblast as of 01.03.2026 was 653.266 MW, of which: 587.5 MW — renewable energy sources, including: 453.0 MW — solar power plants (258.7 MW — commercial producers, 195.164 MW — private households); 42.1 MW — hydroelectric power plants (mini-HPPs); 80.8 MW — wind power plants; 11.6 MW — biogas; 65.7 MW — cogeneration units. Zaporizhzhia oblast During 2025, 9 cogeneration units were installed at heat-supply facilities of the Zaporizhzhia city territorial community, with a total electric capacity of 9.85 MW and thermal capacity of 11.123 MW. In addition, the installation of an additional 50 cogeneration units with a total electric capacity of 106 MW is planned at heat- and water-supply facilities of the Zaporizhzhia and Vilniansk city territorial communities, as well as at healthcare facilities of the Zaporizhzhia city territorial community. Ivano-Frankivsk oblast In 2025, cogeneration gas units with a total thermal capacity of 89.1 MW were installed in the oblast. Kyiv oblast In 2025, 37 cogeneration units were installed to provide electric and thermal energy with a total capacity of 77.1 MW (including one gas turbine unit with a capacity of 20 MW and 3 gas-piston units). Kirovohrad oblast In 2025, 5 cogeneration units with a capacity of 2.22 MW were commissioned. Currently, 11 units with a total capacity of 44.71 MW are in operation. Luhansk oblast Implementation has not begun. Lviv oblast 9 cogeneration units were installed by municipal enterprises: 8.102 MW of thermal capacity; 6.42 MW of electric capacity. 23 cogeneration units were installed by private enterprises with a total electric capacity of 43.046 MW, and 1 gas turbine unit was installed by a state enterprise with an electric capacity of 16 MW. Mykolaiv oblast In total, the oblast has installed: cogeneration units — 21 units / 28.15 MW; commissioned — 16 units / 19.675 MW. Equipment — donor funds. Construction and installation works — funds of the business entities. Odesa oblast Within the framework of a USAID project, in May 2024 the municipal enterprise "TM Yuzhteplokomunenergo" (Pivdenne) received a gas-piston cogeneration unit with a capacity of 0.6 MW. The unit has now been commissioned. Also, within the framework of projects involving other cities. Poltava oblast In 2025, private economic entities commissioned 5 cogeneration units (total capacity 6.1 MW); municipal thermal energy enterprises commissioned 2 units (total capacity 1.25 MW). Rivne oblast Heat-supply enterprises in the oblast implemented 9 projects to install cogeneration units with a total thermal capacity of 28.0 MW and electric capacity of 28.2 MW. Sumy oblast 25 cogeneration units with a capacity of 101.2 MW have been installed and are operating. Ternopil oblast 23 cogeneration units are connected to the network in the oblast, of which: 5 units (10.2 MW) generate electricity for sale, feeding around 220 MW per day into the network; 18 units (18.374 MW) generate electricity for own needs. Kharkiv oblast In order to effectively develop distributed generation in the region, a comprehensive assessment of the current state of generating capacities was carried out, an analysis of electricity consumption volumes by consumer category was conducted, potential distributed generation projects to be implemented were identified, and the Energy Resilience Passport of Kharkiv Oblast was developed and approved by joint order of the Ministry of Energy and the Ministry for Communities, Territories and Infrastructure Development of 31.11.2024 No. 496/1502. Amendments were made to the Energy Resilience Passport of Kharkiv Oblast regarding the implementation of distributed generation projects, which were sent to the Ministry of Energy of Ukraine in July 2025. Work is continuously carried out in the oblast to create a decentralized energy and heat supply system in the city of Kharkiv and settlements of Kharkiv oblast (installation of modular boiler houses, cogeneration units, gas-piston and gas-turbine units, generators, etc.). In the event of a threat or emergence of emergency situations, enterprises are provided with cogeneration units at 77.8% (144 units — 205.2 MW): 95 units with a total electric capacity of 79.4 MW have been installed (of which 8 units with a capacity of 11 MW were destroyed as a result of the shelling of Kharkiv by the Russian Federation on 25.12.2024); of these, 57 units with an electric capacity of 64.7 MW were installed in 2025. In addition, distributed generation facilities are being implemented by other economic entities in the oblast (Gas Transmission System Operator of Ukraine, businesses). Economic entities have installed: 3 gas turbine units with a total capacity of 21.6 MW (GTSOU, damaged as a result of shelling on 15.11.2025); 5 gas-piston units with a total capacity of 2.8 MW; 7 cogeneration units with a total electric capacity of 9.3 MW, installed both to cover the own needs of enterprises/organizations/institutions and to supply electricity to Ukraine's Unified Energy System, of which 4 units with an electric capacity of 3.5 MW were installed in 2025. Work also continues on implementing renewable energy facilities. In Kharkiv oblast the following have been installed: 41 industrial solar power plants (SPPs) and SPPs under self-generation agreements with a total capacity of 28.5 MW, and 1,202 SPPs of private individuals with a total capacity of 30.1 MW; electricity production since the beginning of the year amounted to 19.9 thousand MWh and 27.2 thousand MWh respectively; 3 bioenergy units (biomass, biogas) with a total capacity of 11.2 MW, with electricity production over 11 months of 2025 amounting to over 21.1 thousand MWh. Within the framework of implementing Cabinet of Ministers of Ukraine Resolution No. 510-r of 7 June 2024 "On certain measures to stabilize the operation of the unified energy system of Ukraine," in order to ensure energy independence, Kharkiv oblast continues work on installing solar power plants and energy storage units at budget-sector facilities. Similar work is carried out by municipal enterprises. Funding sources are local programmes, donor assistance, and credit funds. Thus, to meet own needs, 84 SPPs (3.1 MW) were installed, of which 24 SPPs (total capacity 1.0 MW) were commissioned during 2025. Khmelnytskyi oblast. The regional military administration, together with local self-government bodies, continuously takes measures to ensure that heat, water supply, and sewerage enterprises develop plans for reserving sources of thermal and electric energy and for modernizing boiler houses. By the end of the year, 52 cogeneration units with a total capacity of 40.113 MW had been installed at municipal thermal energy facilities (43 units in operation). Cherkasy oblast In 2025, enterprises of various forms of ownership installed and commissioned 43 cogeneration and gas-piston units with a total capacity of 65.42 MW. Chernivtsi oblast Six cogeneration units, each with a capacity of 1.5 MW, were installed at facilities of the Chernivtsi municipal enterprise "Chernivtsiteplokomunenergo." Chernihiv oblast To provide additional thermal and electric energy generation, 24 generating units with a total electric capacity of 46.3 MW were installed in Chernihiv oblast. | Zhytomyr oblast 64600,00 | Zhytomyr oblast 118000,0 Zaporizhzhia oblast 53114,2 Kyiv oblast 98098,0 Mykolaiv oblast 161026,43 Odesa oblast 2 227 000,00 Ternopil oblast 7000,0 Chernivtsi oblast 70000,0 | Zhytomyr oblast 1200000,0 Zaporizhzhia oblast 337565 Kyiv oblast 357500,0 | Donetsk oblast As a result of enemy shelling in June 2025, the aforementioned cogeneration units sustained significant damage. Measures are currently being taken to relocate them to a safe location outside the oblast to carry out the corresponding restoration works with the support of the Ministry of Energy of Ukraine; the necessary funding is expected. Odesa oblast Due to the absence and delay of additional equipment, some cogeneration units, instead of being commissioned in 2025, will be commissioned during 2026. |
| 69. Development of energy clusters and biogas production based on wastewater and sludge treatment facilities | facilitating the implementation of projects to install biogas/biomethane production units | 2025—2026 | biogas/biomethane production units installed with a total capacity of 15 MW |  | Vinnytsia oblast Within the framework of the Distributed Generation Development Strategy, in 2025 the oblast built more than 80 MW of new generating capacity, of which: the capacity of industrial solar power plants commissioned in 2025 was 11.4 MW; private household solar installations amounted to 11.75 MW connected to electricity and gas networks; and 15 cogeneration units with a capacity of over 60 MW. Zhytomyr oblast There are currently no biogas/biomethane production units based on wastewater and sludge treatment facilities in the oblast. Zaporizhzhia oblast As of 01.01.2026, one biogas plant is operating in the government-controlled territory of the oblast, installed by "Biohaz Ukraina" LLC at the solid municipal waste landfill of the Zaporizhzhia city territorial community. There is currently no need for additional biogas/biomethane production units. Ivano-Frankivsk oblast Biogas plants continue to operate in the oblast. Currently, bioenergy plants with a total capacity of 1.2 MW have been installed. Kyiv oblast Implementation has not begun. Luhansk oblast Implementation has not begun. Lviv oblast Implementation has begun on a project to build a biogas station with combined electric and thermal energy production at the treatment facilities of the Lviv municipal enterprise "Lvivvodokanal." Mykolaiv oblast The project of the regional municipal enterprise "Mykolaivobltheploenergo" envisages the construction of two biomass-based energy-generating complexes (agricultural raw material feedstock), each with a capacity of 5 MW. The project is scheduled to begin in 2026. The funding requirement is EUR 24 million. Ternopil oblast There are no projects for installing biogas/biomethane production units. Kharkiv oblast In Kharkiv oblast, 2 biogas units with a total capacity of 4.2 MW are operating, producing almost 19.0 thousand MWh of electricity in 2025. Territorial communities in the region are considering the possibility of implementing measures to develop energy clusters and biogas production based on wastewater and sludge treatment facilities; in particular, an analysis of technical possibilities and consultations with partners are underway. Khmelnytskyi oblast The regional military administration, together with local self-government bodies, continuously takes measures to develop projects for implementing alternative energy sources, including the installation of biogas/biomethane production units. By the end of the year, 3 biogas plants and 3 biomass plants with a total capacity of 57.57 MW were operating in the oblast and supplying electricity to the grid. Cherkasy oblast There are no biogas/biomethane production units with a total capacity of 15 MW in the oblast. Chernivtsi oblast A private investor has installed 1 biogas-fuelled unit with a capacity of 1 MW in the oblast. Chernihiv oblast To provide additional thermal and electric energy generation, 24 generating units with a total electric capacity of 46.3 MW were installed in Chernihiv oblast. |  |  |  | Donetsk oblast Ongoing hostilities in the oblast's territory, the destruction of industrial infrastructure due to enemy shelling, the unsatisfactory security situation, and the region's investment unattractiveness effectively make it impossible to implement these projects at present. Kyiv oblast Due to the difficult financial condition of investors, the implementation of projects involving the installation of biogas/biomethane production units has been temporarily suspended. |
| 70. Development and implementation of municipal and regional energy plans | monitoring the status of development of local energy plans | 2025—2027 | approval of local energy plans ensured in 100% of Ukraine's regions | Started | State Agency on Energy Efficiency and Energy Saving Based on the monitoring conducted, information was received from 17 regional military administrations regarding the approval of 65 local energy plans: 1 regional and 64 municipal. |  |  |  |  |
| 71. Implementation of energy management systems in public authorities, local self-government bodies, and municipal enterprises, and energy monitoring systems for public and residential buildings | monitoring the state of implementation and ensuring the functioning of energy management systems in public authorities and local self-government bodies in accordance with Cabinet of Ministers of Ukraine Resolution No. 1460 of 23 December 2021 "On the introduction of energy management systems" | 2025—2027 | functioning of energy management systems ensured in 100% of public authorities and no fewer than 70% of local self-government bodies | Completed | State Agency on Energy Efficiency and Energy Saving Information was received from 51 public authorities regarding 12,033 buildings, of which 8,456 buildings (70.3% of the total) have approved orders on the implementation of energy management systems; information was received from 19 regional military administrations regarding 18,268 buildings, of which 12,273 buildings (67.2% of the total) have decided to implement energy management systems. |  |  |  |  |
| Area "Civil Protection and Public Safety" |  |  |  |  |  |  |  |  |  |
| 73. Facilitating the expansion of the civil protection fund of protective structures, taking into account the principles of inclusiveness and barrier-free access | monitoring the condition of the civil protection fund of protective structures and providing methodological assistance to public authorities and balance-holders on the creation and maintenance of protective structure fund facilities (civil protection shelters, anti-radiation shelters, dual-purpose structures) | 2025—2027 | the number of protective structures in the relevant territory increased by no fewer than 30% | Ongoing | Ministry of Internal Affairs The State Emergency Service (SES) continues systematic work to monitor the readiness of civil protection fund facilities, which is one of the key elements of ensuring public safety under martial law. As of 15.01.2026, the total number of civil protection fund facilities in Ukraine stands at 68,529. Of these, 7,595 facilities are located in temporarily occupied territories or in active combat zones, meaning their actual state of readiness cannot currently be established. Due to the expansion of combat zones and temporary occupation, an additional 4,193 facilities lost the possibility of full inspection and operation during the year. In territory controlled by the Government of Ukraine, 60,934 fund facilities are registered, of which, based on inspections conducted, 53,224 facilities (87%) are in a state of readiness for their intended use. At the same time, 5,705 facilities (10%) have been identified as unsuitable for sheltering the population and requiring response measures, and 2,005 facilities (3%) lack unobstructed access. During the year, the fund increased by 3,455 facilities, representing 5% of the total number of fund facilities. In accordance with the Plan for comprehensive inspections of civil protection fund facilities for 2025, approved by SES Order No. 1272 of 28.11.2024, comprehensive inspections of the state's civil protection fund facilities were carried out. Over the course of 2025, the SES, together with the National Police, local executive authorities, and local self-government bodies, conducted comprehensive inspections of 62,822 facilities (5,233 shelters, 14,054 anti-radiation shelters, 93 dual-purpose structures, 43,442 other civil protection fund facilities of the state). By the end of the year, comprehensive inspections had been carried out on 100% of the planned number of facilities. In addition, 23,421 control inspections and 6,157 unscheduled inspections were carried out since the beginning of the year, based on decisions of the relevant commissions on technogenic-ecological safety and emergency situations. In territory controlled by the Government of Ukraine, central executive authorities, local military administrations, and local self-government bodies achieved an increase in the civil protection fund of 3,455 facilities. |  |  |  |  |
| 73. Facilitating the development of warning and public alert systems regarding the threat or occurrence of emergency situations | 1) Carrying out technical modernization of territorial automated centralized warning systems regarding the threat or occurrence of emergency situations in the regions | 2025—2027 | modernization of 100% of automated centralized warning systems ensured |  | Vinnytsia Oblast In November 2025, the stage of preparing design-and-estimate documentation for the engineering project "Creation (new construction) of the Regional Automated Centralized Warning System of Vinnytsia Oblast. Adjustment" was completed. In accordance with Cabinet of Ministers Resolution No. 119 of 02.02.2024, the information design was finalized and approval was obtained from the Ministry of Digital Transformation of Ukraine. A contract has been concluded for the implementation of TASCO in the oblast. Procurement and installation of equipment has begun. Dnipropetrovsk Oblast The system is operating in trial mode. Zhytomyr Oblast Design-and-estimate documentation for the regional automated centralized warning systems of Zhytomyr Oblast has been developed. The design-and-estimate documentation has been revised. The increase amounts to 30%. Zakarpattia Oblast There is 1 effective public warning system in operation. Zaporizhzhia Oblast In 2025, a number of measures were implemented aimed at the creation, modernization, and improvement of the regional and local automated centralized warning systems (TASCO and MASCO, respectively), namely the following was developed: - design-and-estimate documentation for the reconstruction of Zaporizhzhia Oblast's TASCO. Ivano-Frankivsk Oblast In 2025, the regional automated centralized warning system was put into trial operation. Kyiv Oblast For the reconstruction (modernization) of the regional automated centralized public warning system of Kyiv Oblast, part of the necessary equipment has been procured. Kirovohrad Oblast Business entities in the oblast carried out the installation and conversion of facility-level warning stations within local warning systems. A district-based warning system has been introduced. Luhansk Oblast Implementation has not begun. Lviv Oblast The oblast's regional automated centralized warning system was put into industrial operation by order of the head of the Lviv Oblast Military Administration No. 1224/0/5-24VA dated 19.11.2024; it is in working condition and performing its designated function. Mykolaiv Oblast During 2025, the Civil Protection Department of the Mykolaiv Oblast Military Administration undertook a number of measures for the technical modernization of TASCO, namely: a works contract No. 17/25 dated 13.03.2025 was concluded for the "New construction of the regional automated centralized warning system of Mykolaiv Oblast." Installation works are being carried out in accordance with the design. Completed at 20%. Odesa Oblast Design-and-estimate documentation was produced for "Re-equipment and reconstruction (technical modernization) of the regional automated centralized public warning system of Odesa Oblast." Based on the results of the scientific-technical expert review and the review of the cost estimate, the project received positive conclusions. To determine a contractor, 9 requests were sent, of which 2 commercial proposals for project implementation were received. 2) 90 technical specifications were created and agreed, and design-and-estimate documentation for the technical modernization of MASCO was produced in 20 territorial communities. In the Izmail city territorial community, construction of MASCO has been completed, with 19 base stations installed. Trial operation of the warning system in the Izmail territorial community is ongoing until 31.12.2026. Poltava Oblast Since 2020, a newly built regional automated centralized warning system has been in trial operation. Rivne Oblast A design for the regional automated centralized warning system (TASCO) has been developed in the oblast. Sumy Oblast A TASCO modernization design has been developed. Ternopil Oblast The modernization of the "OZON" TASCO has been completed in the oblast, with 4 additional PMU-01 modems installed; the total number of channels for transmitting signals to end devices is now 12. This modernization has increased the speed of the warning system and the delivery of warning signals to the oblast's population. Kharkiv Oblast Revisions to the design-and-estimate documentation for the reconstruction of the regional automated centralized warning system of Kharkiv Oblast have been completed, and a positive expert report was obtained under registration number ЕХ01:9811-9201-8270-8123. Khmelnytskyi Oblast In 2025, the regional automated centralized warning system was modernized and put into trial operation. Cherkasy Oblast In accordance with the action plan for implementing the Concept for the Development and Technical Modernization of the Centralized Warning System for Threats or Emergencies, approved by Cabinet of Ministers Order No. 448-r dated 11.07.2018, the Cherkasy Oblast Military Administration prepared in 2024 the technical specification for the reconstruction (technical modernization) of Cherkasy Oblast's TASCO, which was agreed with the State Emergency Service of Ukraine, the Ministry of Digital Transformation of Ukraine, and the State Service for Special Communications and Information Protection of Ukraine. Procurement of design-and-estimate documentation development services for the modernization of Cherkasy Oblast's TASCO was carried out. As a result of the procurement, a contract worth UAH 1,064 thousand was concluded and design-and-estimate documentation for the TASCO modernization was produced. Based on the design documentation's baseline data, a tender for the modernization of Cherkasy Oblast's TASCO was held for UAH 123,658.6 thousand. Chernivtsi Oblast In 2025, design-and-estimate documentation was produced for the project "Reconstruction of Chernivtsi Oblast's TASCO." Chernihiv Oblast Design-and-estimate documentation was developed for the "Technical Modernization of the Regional Automated Centralized Warning System of Chernihiv Oblast." | Rivne Oblast 897,0 Kharkiv Oblast 64,0 | Vinnytsia Oblast 12804,479 Dnipropetrovsk Oblast 10621,226 Zaporizhzhia Oblast 729,0 Ivano-Frankivsk Oblast 4521,9 Kyiv Oblast 22834,8 Lviv Oblast 48,4 Mykolaiv Oblast 14900,0 Odesa Oblast 799,6 Sumy Oblast 799,6 Khmelnytskyi Oblast 16216,0 Chernivtsi Oblast 300,0 |  | Donetsk Oblast As of 01.01.2026, more than 70% of the oblast's territory is temporarily occupied. The front line is changing dynamically. Given the situation in Donetsk Oblast caused by the Russian Federation's military aggression, the regional automated centralized warning system (TASCO) is non-functional and does not provide reception/transmission of signals and information from the national automated centralized warning system to local automated centralized warning systems (MASCO). No technical modernization of TASCO or MASCO has been carried out. |
|  | 2) Creation of New Local Automated Centralized Warning Systems (MASCO) in Districts and Territorial Communities | 2025—2027 | 1,595 new MASCO systems created, excluding temporarily occupied communities and districts |  | Vinnytsia Oblast New MASCO systems have been created in the Vinnytsia and Yakushyntsi territorial communities of the oblast. Contracts for the development of design-and-estimate documentation for the implementation of MASCO have been concluded in the Raihorod, Khmilnyk, Horodkivka, Pishchanka, Samhorodok, Zhmerynka, Yampil, Kalynivka, Illintsi, Luka-Meleshkivska, Pohrebyshche, Tyvriv, Bershad, and Kryzhopil territorial communities. As of 1 January 2026, the Oblast Military Administration and the Main Directorate of the State Emergency Service in Vinnytsia Oblast had reviewed and approved 56 technical specifications for the new construction of MASCO. Volyn Oblast 2 new local automated centralized warning systems have been created. Dnipropetrovsk Oblast 28 new local automated centralized warning systems have been created. Zhytomyr Oblast Design-and-estimate documentation has been developed for the creation of local automated warning systems in the Zhytomyr, Korosten, and Korostyshiv territorial communities. Technical specifications, with subsequent development of design-and-estimate documentation, have been developed in 56 communities. The increase amounts to 0.1%. Zaporizhzhia Oblast In 2025, a number of measures were carried out for the creation, modernization, and improvement of TASCO and MASCO, namely, the following was developed: design-and-estimate documentation for the new construction of MASCO in 11 territorial communities. The Novomykolaivka settlement territorial community is currently building phase 1. Ivano-Frankivsk Oblast 1 new local automated centralized warning system has been created and put into trial operation. Kyiv Oblast Local automated centralized warning systems have been created in 3 territorial communities of Kyiv Oblast. Luhansk Oblast Implementation has not begun. Lviv Oblast 80 MASCO systems have been created in Lviv Oblast — 7 at the district level and 73 in territorial communities of the oblast. Design-and-estimate documentation for MASCO has been developed in 7 districts and 64 territorial communities. MASCO has been put into industrial operation in 7 districts and 52 territorial communities. Modernization of MASCO in districts and territorial communities is to be completed within the timeframe set by the Action Plan for implementing the Concept for the Development and Technical Modernization of the Centralized Warning System for Threats or Emergencies, approved by Cabinet of Ministers Order No. 488-r dated 11 July 2018 (deadline: December 2026). Mykolaiv Oblast 56 design specifications for MASCO have been developed and agreed. 20 designs for new MASCO systems have been developed. 8 design-development contracts have been concluded. Odesa Oblast Active implementation of new local automated centralized warning systems is underway. Poltava Oblast A new local automated centralized warning system has been created in the Horishni Plavni community; design documentation has been developed in 36 communities. Rivne Oblast 17 new local automated centralized warning systems have been created in the oblast's territorial communities. Sumy Oblast In 2025, 20 technical specifications for the construction of local automated centralized warning systems (MASCO) were agreed; 9 MASCO development designs were prepared by the oblast's territorial communities. Ternopil Oblast New local automated centralized warning systems have been created in the following territorial communities of the oblast: Baikivtsi, Velyka Berezovytsia, Velykyi Hai, Zbarazh, Zolotyi Potik, Ivanivka, Kopychyntsi, Ternopil, Khorostkiv, and Chortkiv. In 2025, the Main Directorate of the State Emergency Service of Ukraine in Ternopil Oblast agreed 31 technical specifications for the creation of local automated centralized warning systems. Kharkiv Oblast 1 new local automated centralized warning system (MASCO) has been created in the city of Kharkiv; design-and-estimate documentation for MASCO has been developed in 49 territorial communities of the oblast, of which 39 have received positive expert reports. Khmelnytskyi Oblast Last year the oblast carried out the following measures: - 3 territorial communities modernized MASCO; - 3 territorial communities are in the process of implementing MASCO; - 5 territorial communities concluded agreements for the development of design-and-estimate documentation for MASCO; - 11 territorial communities developed designs. Work in this area will continue in 2026. Cherkasy Oblast At present, all 66 territorial communities of the oblast have developed and agreed technical specifications for the creation of MASCO. Design-and-estimate documentation for the creation of MASCO has been produced by the following territorial communities: Bereznyaky, Bilozirya, Budyshcha, Mykhailivka, Moshny, Ruska Poliana, Stepankivka, Stepanky (Cherkasy district); Babanka, Bashtechky, Zhashkiv, Ladyzhynka, Mankivka, Uman, Palanka (Uman district); Drabiv, Zolotonosha, Irkliiv (Zolotonosha district); Zvenyhorodka, Matusiv, Mokra Kalyhirka, Shpola (Zvenyhorodka district). Implementation of MASCO in these communities will proceed according to the communities' financial capacity. The remaining communities are working to identify developers and commission working designs for MASCO. In total, UAH 1,569.6 thousand was used in 2025. Chernihiv Oblast MASCO has been created in 6 territorial communities of Chernihiv Oblast, with 181 end-point warning devices installed (648 loudspeakers/electric sirens) in 49 settlements. In addition, 109 end-point warning devices (311 loudspeakers/electric sirens) have been installed in 27 territorial communities, covering 80 settlements. | Rivne Oblast 9220,0 | Volyn Oblast 5958,0 Dnipropetrovsk Oblast 25393,4 Zhytomyr Oblast 198,0 (обласний бюджет) Zaporizhzhia Oblast 3000,0 Kyiv Oblast 4254,3 Lviv Oblast 25431,97 Mykolaiv Oblast 1936,884 Poltava Oblast 30865,0 Kharkiv Oblast 9302,498 Khmelnytskyi Oblast 5106,5 | Ivano-Frankivsk Oblast 1344,8 Khmelnytskyi Oblast 1733,0 | Vinnytsia Oblast The cost of MASCO modernization and creation works. Most territorial communities are unable to allocate significant financial resources. Poltava Oblast Insufficient funding of measures from community and district military administration budgets under martial law. |
| 74. Promoting the Establishment of Safety Centers in Territorial Communities Integrated structures with unified communication in accordance with legislation, taking into account the principle of territorial accessibility for protecting the population and territories from fires and emergencies, ensuring public order, and public health (with fire-rescue units, police stations, and emergency medical brigades). | 1) Providing methodological assistance to local self-government bodies on establishing and operating local and volunteer fire-rescue units, including within safety centers, in territorial communities. | 2025–2027 | fire-rescue units of local and volunteer fire protection established in at least 70% of territorial communities. | Started | Ministry of Internal Affairs In 2025, territorial bodies of the State Emergency Service provided methodological assistance to local self-government bodies on establishing local and volunteer fire protection units in territorial communities: 3,910 working meetings, 967 joint meetings, 232 seminars, and 422 round-table sessions were held; the establishment of fire-rescue units was raised at 949 sessions of technogenic-ecological safety and emergency commissions of local self-government bodies (28 regional and 921 local sessions); the topic was covered 7,002 times in the media. To ensure fire safety and prompt emergency response, 111 local and volunteer fire-rescue units were established in 2025. |  |  |  |  |
|  | 2) Transferring to local self-government bodies equipment and real estate on the State Emergency Service's balance sheet that is unused and not planned for use, for the needs of volunteer and local fire-protection units, including within safety centers. | 2025–2027 | equipment and real estate transferred to local self-government bodies | Started | Ministry of Internal Affairs During 2025, State Emergency Service units transferred 122 units of various-purpose equipment from state to communal ownership to support local fire-protection units. Also, to ensure the proper functioning of local fire-protection units, 16 real-estate properties under the State Emergency Service's management were transferred from state to communal ownership to local self-government bodies during 2025. |  |  |  |  |
|  | 3) Ensuring the establishment of police stations. | 2025-2027 | police stations established in 100% of safety centers. | Ongoing | Ministry of Internal Affairs To increase police presence in communities, build partnership relations with the population, and create proper working conditions for police officers, police stations are being set up and launched. As of 01.01.2026, more than 1,500 police stations are operating nationwide, of which 28 are based at safety centers. During 2025, 155 police stations began operating, of which 5 were based at newly established safety centers in Kharkiv (2), Zaporizhzhia, Zakarpattia, and Mykolaiv (1 each) oblasts. At the same time, due to Russia's armed aggression against Ukraine, 104 police stations ceased operating, of which 15 were destroyed, 16 were damaged, and 73 are located in temporarily occupied territory. | Funding: within the limits of expenditures provided under the State Budget of Ukraine, budget program 1007020 "Ensuring the activities of bodies, institutions, and establishments of the National Police of Ukraine." |  |  |  |
|  | 4) Ensuring the establishment of emergency (ambulance) medical brigades. | 2025-2027 | emergency medical brigades established at 100% of safety centers. | Ongoing on a continuous basis | MOH Emergency medical brigade duty has been ensured at safety centers according to regional needs. By letter of the Ministry of Health No. 25/39752/2-25 dated 23.12.2025, a request was sent to the Health Departments of oblast military administrations regarding implementation of the Strategy; responses were received on organizing emergency medical brigade duty in territorial communities of oblasts where safety centers have been established. | - | - | - | - |
| 75. Supporting the Creation (Restoration) of Safe Conditions in Territorial Communities through the "Community Police Officer" Project | Implementation via a network of police stations in territorial communities and appointment of community police officers. | 2027 | community police officers appointed in 100% of territorial communities that joined the project | Ongoing on a continuous basis | Ministry of Internal Affairs To introduce new forms and methods into police work, build partnership-based engagement with the population, provide quality police services, and ensure police presence in the country's territorial communities, the National Police continues implementing the "Community Police Officer" project. It is currently being implemented in almost 1,100 territorial communities across 23 regions, covering 83% of the total (excluding communities in temporarily occupied territories), specifically: Volyn Oblast — 47 of 54 communities; Vinnytsia — 63 of 63; Dnipropetrovsk — 69 of 86; Donetsk — 8 of 46; Zhytomyr — 37 of 66; Zakarpattia — 55 of 63; Zaporizhzhia — 20 of 67; Ivano-Frankivsk — 49 of 62; Kyiv — 68 of 69; Kirovohrad — 49 of 49; Lviv — 50 of 73; Mykolaiv — 38 of 52; Odesa — 76 of 91; Poltava — 43 of 60; Rivne — 64 of 64; Sumy — 46 of 51; Ternopil — 51 of 55; Kharkiv — 51 of 56; Kherson — 13 of 49; Khmelnytskyi — 46 of 60; Cherkasy — 43 of 66; Chernihiv — 44 of 57; Chernivtsi — 52 of 52. During 2025, 108 new territorial communities joined the project. The staffing establishment for community police officers is nearly 2,500 positions: Vinnytsia — 298; Volyn — 78; Dnipropetrovsk — 140; Donetsk — 22; Zhytomyr — 98; Zakarpattia — 80; Zaporizhzhia — 41; Ivano-Frankivsk — 77; Kyiv — 247; Kirovohrad — 102; Lviv — 111; Mykolaiv — 79; Odesa — 107; Poltava — 64; Rivne — 195; Sumy — 76; Ternopil — 103; Kharkiv — 144; Kherson — 19; Khmelnytskyi — 110; Chernivtsi — 116; Chernihiv — 119; Cherkasy — 71. Currently 85% of community police officer positions are filled. | Funding: within the limits of expenditures under the State Budget of Ukraine, budget program 1007020 "Ensuring the activities of bodies, institutions, and establishments of the National Police of Ukraine." |  |  |  |
| Operational Goal 2: A Strong, Capable, and Competitive Regional Economy |  |  |  |  |  |  |  |  |  |
| Area “ New Jobs, Investment, and Business Development" |  |  |  |  |  |  |  |  |  |
| 76. Stimulating Entrepreneurial Activity in the Regions by Encouraging Working-Age IDPs, War Veterans and Their Family Members, and Unemployed Persons to Seek Employment and Start Their Own Businesses | 1) Development and implementation of vocational training programs based on labor-market demand. | 2026 | Labour market-oriented vocational training programmes have been implemented. | Not started | the deadline for the measure has not yet arrived. |  |  |  |  |
|  | 2) Providing financial support for veterans', family members', and IDP veterans' business projects. | 2025-2027 | financial support provided for at least 50 projects | здійснюється постійно | Ministry of Veterans Affairs Support has been provided to veterans and their family members for the implementation of 434 entrepreneurship projects selected as winners of the "VARTO" competitive grant programs over 2024–2025. | 357558,4 |  | 7000 |  |
|  | 3) Updating and implementing employment-assistance programs targeting vulnerable population groups. | 2025—2027 | a 3% annual increase in the employment of working-age vulnerable persons who had been unemployed and returned to the labor market |  | Ministry of Economy In implementation of the Law of Ukraine "On Employment of the Population," the Ministry of Economy runs the following employment-assistance programs: - Compensation to employers for labor costs for employing IDPs during martial law. In 2025, 7,070 decisions were made granting such compensation for 15,860 individuals; UAH 364,871.7 thousand was disbursed. - Compensation for labor costs for employing registered unemployed persons from among IDPs. In 2025, 1,397 decisions were made for 1,397 individuals; UAH 76,653.2 thousand was disbursed. - Compensation to employers for actual costs equal to the unified social contribution. In 2025, 2,298 decisions were made for 2,298 individuals; UAH 37,916.20 thousand was disbursed. - Compensation to employers of 50% of actual labor costs. In 2025, 1,475 decisions were made for 1,475 individuals; UAH 17,263.60 thousand was disbursed. - Compensation to employers of 50% of the minimum wage. In 2025, 2,812 decisions were made for 2,812 individuals; UAH 43,050.30 thousand was disbursed. - Compensation to small businesses for actual costs equal to the unified social contribution for mandatory state social insurance. In 2025, 11,797 decisions were made for 11,797 individuals; UAH 166,824.70 thousand was disbursed. In 2025, 35,600 persons were employed under the above programs, 13.6% more than in 2024. - Compensation of actual costs for adapting workplaces/business premises/independent professional activity premises for persons with disabilities. During 2025, compensation was provided to employers for adapting such workplaces for 2,400 employed persons with Group I or II disabilities, 27.9% more than in 2024. - Socially useful works. In 2025, 115,600 referrals were issued for participation in socially useful works, including 22,300 referrals for IDPs, 661 for combat participants, 6,600 for persons with disabilities, 1,500 for persons over 60, and 537 for people aged 60–70 involved in such works in front-line areas. The works are carried out in 34 [sic] oblasts: Vinnytsia, Volyn, Dnipropetrovsk, Donetsk, Zhytomyr, Zaporizhzhia, Ivano-Frankivsk, Kyiv, Kirovohrad, Lviv, Mykolaiv, Odesa, Poltava, Rivne, Sumy, Ternopil, Kharkiv, Kherson, Chernihiv, and Cherkasy. The Ministry of Economy pursues a systematic and consistent policy of adapting state employment policy to the challenges of martial law and the needs of economic recovery. Changes introduced in 2025 to Cabinet of Ministers Resolutions No. 893 of 22.08.2023 ("Certain issues regarding compensation of actual costs for adapting workplaces/business premises/independent professional activity premises for persons with disabilities"), No. 753 of 13.07.2011 ("On approving the procedure for engaging working-age persons in socially useful works under martial law"), and No. 331 of 20.03.2022 ("On approving the procedure for providing employers with compensation for labor costs for employing IDPs as a result of hostilities during martial law in Ukraine") are aimed at comprehensively addressing key labor-market tasks: strengthening inclusiveness and support for vulnerable population groups; sustaining regional livelihoods; and stimulating and supporting employers. |  |  |  |  |
|  | 4) Development of grant programs supporting entrepreneurial initiative among vulnerable population groups. | 2025—2027 | financial support provided to at least 1,000 vulnerable persons for organizing and expanding their own businesses under grant programs | Ongoing | Ministry of Economy 2,824 positive decisions have been made on granting the combat-veteran (UBD) grant, of which 308 concern IDPs (as of 23.03.2026). |  |  | Funding: UAH 1.3 billion (as of 23.03.2026), financed from the budget of the Mandatory State Social Insurance Fund against Unemployment. |  |
|  | 5) Introduction and implementation of state and regional business-support programs. | 2025—2027 | financial support provided to at least 500 business entities to develop their own businesses. | Ongoing | Ministry of Economy To promote employment and processing-industry development, the Government introduced a grant program for processing-industry enterprises (Cabinet of Ministers Resolution No. 739 of 24.06.2022, as amended). The grant amount per recipient does not exceed UAH 8 million, and for business entities restoring fixed production assets destroyed or damaged by Russian armed aggression, it does not exceed UAH 16 million, and in any case may not exceed the amount of damage incurred. In 2025, 450 grants totaling UAH 2,293.3 million were actually disbursed. | 2293300,0 |  |  |  |
|  | 6) Implementation of programs for the safety and resilience of critical infrastructure and programs to increase the resilience of territorial communities to crisis situations caused by the interruption or deterioration of services essential to their functioning or vital functions | 2025-2027 | relevant programs implemented |  | Vinnytsia Oblast Territorial communities have developed action plans for emergency and off-schedule situations at housing and utility facilities to ensure a stable autumn-winter period, modeling scenarios of energy-carrier shortages and the corresponding actions of authorities and services in the subordinate territories. Donetsk Oblast By order of the head of the oblast state (military) administration No. 1/5-25 of 01.01.2025, the Program for the Economic and Social Development of Donetsk Oblast for 2025 was approved, providing for measures including: support for security and defense forces stationed in the oblast in procuring materiel, works, and services related to martial-law measures; procurement of structures and means to protect the oblast's critical infrastructure from missile, artillery, and other shelling; and subventions/subsidies from the oblast budget to community budgets to sustain critical infrastructure, ensure a stable heating season, and carry out priority defense-preparation and emergency-prevention/response measures under martial law. Zhytomyr Oblast 66 programs for critical infrastructure safety/resilience and community resilience to crisis situations caused by interrupted or degraded essential services have been developed in territorial communities, of which 64 have been approved. Zaporizhzhia Oblast In line with the President's "Resilience Plan," the oblast state (military) administration approved by order No. 107-DSK of 11.03.2026 a Comprehensive Resilience Plan for Zaporizhzhia Oblast for 2026, based on four key areas: critical infrastructure protection, distributed generation development, backup/alternative power supply, and decentralization of heat generation. Local self-government bodies have also implemented relevant measures under local programs, including critical infrastructure safety/resilience, community resilience, and protection from technogenic and natural emergencies. In 2025, UAH 1,125.6 thousand from local budgets was allocated for community-resilience measures. Ivano-Frankivsk Oblast Local programs for critical infrastructure safety/resilience and community resilience are in effect. Relevant programs have been approved by the councils of Kuty, Bilshivtsi, Solotvyn settlement councils, and Rozhniv, Pasichna village councils; a "Plan for the safety and resilience of critical infrastructure facilities sustaining the population's livelihoods" was approved by Voinyliv settlement council; and a "Plan of measures to ensure the safety and resilience of critical infrastructure" was approved by the executive committee of Perehinske settlement council and by order of Vytvytsia village council. Given the overall situation in Ukraine, all territorial communities of the oblast are conducting systematic work on critical infrastructure safety and resilience and have established stable procedures for responding to crisis situations caused by interrupted or degraded essential services. Kyiv Oblast To ensure critical infrastructure safety/resilience and community resilience, measures are being implemented under the Kyiv Oblast Comprehensive Program for Ensuring the Safety of the Population and Territory from Emergencies for 2024–2027, approved by Kyiv Oblast Council decision No. 772-22-VIII of 7 December 2023 (as amended). Kirovohrad Oblast In February 2026, the oblast military administration approved a Comprehensive Resilience Plan for Kirovohrad Oblast for 2026, including measures to ensure the stable operation of fuel-and-energy sector critical infrastructure and life-support systems under martial law and related security challenges. Luhansk Oblast Implementation has not begun. Lviv Oblast In 2025, the oblast targeted "Program for the Resilience and Safety of Lviv Region Communities" was developed and approved by order of the head of the oblast military administration No. 1912/0/5-25VA of 31.12.2025; UAH 65 million from the oblast budget is allocated for its implementation in 2026. Mykolaiv Oblast 1) In fulfillment of Cabinet of Ministers Resolution No. 566 of 06.06.2023, to improve water-supply resilience for the Mykolaiv city territorial community, a water intake from the Southern Bug River and a main water pipeline have been built, along with new treatment facilities (filtration station); for wastewater management in the Nova Odesa city territorial community, a full biological and mechanical wastewater treatment station has been built. 2) In fulfillment of Cabinet of Ministers Order No. 567-r of 11.06.2025, to improve heat-supply resilience for the Mykolaiv city territorial community, 18 block-modular boiler houses have been built. 3) In fulfillment of Cabinet of Ministers Order No. 1135-r of 18.10.2025, to improve electricity-distribution resilience for the Mykolaiv city territorial community, construction of Level II engineering-protection structures has begun at facilities of the distribution system operator JSC "Mykolaivoblenergo." Poltava Oblast Communal enterprises have worked out an action algorithm for designated life-support system facilities to prevent emergencies during the 2025/2026 heating period. Rivne Oblast To ensure critical infrastructure safety/resilience and reduce community vulnerability to natural, technogenic, military, and social emergencies, relevant programs have been developed and are in effect in the district military administration and 31 local self-government bodies. Sumy Oblast In 2025, the oblast's territorial communities implemented 25 local programs on critical infrastructure safety and resilience. Ternopil Oblast A program for protecting the population and territories of Ternopil Oblast from emergencies for 2023–2027 has been developed and is in effect, approved by order of the head of the oblast military administration No. 853/01.02-01 of 6 December 2022, under which UAH 2,598.2 thousand was allocated from the oblast budget in 2025. Kharkiv Oblast In all territorial communities of the oblast (except those in temporarily occupied territory), lists of facilities ensuring vital functions have been approved. Plans for the safety and resilience of critical infrastructure sustaining territorial communities have been approved in 38 communities. Work continues on developing and approving local programs to increase community resilience to crisis situations caused by interrupted or degraded essential services. In 28 communities the programs are approved and being implemented; in 11, draft programs are under agreement; in the remaining communities, drafting continues. Development of a regional program on critical infrastructure safety and resilience is also underway. Khmelnytskyi Oblast An oblast interagency crisis-response plan has been developed and approved; work is underway on local programs for critical infrastructure safety/resilience and community resilience. Work is ongoing with district military administrations and territorial communities to develop plans for critical infrastructure safety and resilience. By the end of 2025, resilience plans had been developed in 5 territorial communities (Sataniv, Slavuta, Novodunaivtsi, Myroliubne, Poninka), with other communities taking steps toward developing such plans. Work continues on compiling threat cards to form the oblast's overall community safety and resilience plan. Cherkasy Oblast In 2025, the Regional Plan for the Protection and Ensuring of Safety and Resilience of Critical Infrastructure of Cherkasy Oblast was in effect, approved by order of the Cherkasy Oblast Military Administration No. 35 of 29.01.2024. Chernivtsi Oblast Airspace protection has been provided above designated critical infrastructure facilities against airstrike debris; cyber-protection of critical information infrastructure facilities has been carried out; generators of various capacities have been procured and installed; and the material-technical base for emergency-restoration works has been replenished. Territorial communities have taken measures to approve, in the established manner, plans for critical infrastructure safety and resilience, factoring in actions to strengthen protection against physical and cyber threats. The oblast state (military) administration developed and approved a Comprehensive Program for Critical Infrastructure Safety and Resilience for 2023–2025. A Comprehensive Resilience Plan for Chernivtsi Oblast for 2026 has been developed/ Chernihiv Oblast Chernihiv Oblast has in effect a Program to Increase the Resilience of Chernihiv Oblast's Territorial Communities to Crisis Situations Caused by Interruption or Deterioration of Essential Services or Vital Functions, for 2025–2027. | Mykolaiv Oblast - 8 000 000,0 - 1 114 163,037 - 270 166,20 | Zaporizhzhia Oblast 1125,6 Kyiv Oblast 170469,8 Ternopil Oblast 2598,2 Chernivtsi Oblast 67042,99 | Chernivtsi Oblast 45455,0 |  |
|  | 7) Training the population to ensure protection in the event of crisis-response mode or return to normal functioning. | 2025-2027 | relevant programs implemented. | Ongoing | Vinnytsia Oblast Training of leadership and specialists in civil protection in the oblast is carried out in accordance with Cabinet of Ministers Resolution No. 819 of 23.10.2013 and planning documents. In 2025, training was planned for 2,020 people; 2,035 were actually trained (820 under state order, 1,215 under contract). Practical training was provided through command-staff exercises, staff drills, and training-methodological gatherings, along with participation of district units and territorial communities. For public training, 4 model programs, 50 methodological materials, 48 reference outlines, and 4 manuals were developed; 32 memos and 12 posters on emergency actions were prepared. 360 consultation points operate in the oblast, conducting public information and outreach work. Donetsk Oblast During 2025, 49 residents of Donetsk Oblast completed basic military training at the National Resistance Population Training Center of Dnipropetrovsk Oblast in Dnipro. The total number of people covered by training and activities of the "Center for Unity and National Resistance" platform in Donetsk Oblast was 13,300; over 9,500 people completed first-aid and mine-safety training; over 3,600 participated in national-patriotic education and civic-education events; other participants were engaged in media-literacy, psychological-support, and civil-safety activities. Zhytomyr Oblast Training of the population of the Korosten city territorial community was conducted under the community's General Population Training Program for protection in crisis-response and normal-functioning-recovery modes, on the topic "Methods of ensuring population protection." Zaporizhzhia Oblast During 2025, the Civil Protection and Life-Safety Training-Methodological Center of Zaporizhzhia Oblast conducted 92 training activities for population preparedness under martial law, involving 2,117 people. 6,070 memos, 2,430 guides, and 3,500 booklets on population actions in emergencies under martial law were distributed. Ivano-Frankivsk Oblast In 2025, 1,428 people were trained at the Civil Protection and Life-Safety Training-Methodological Center of Ivano-Frankivsk Oblast (plan: 1,270), of whom 651 were under state order and 777 under contract (plan: 619). Kyiv Oblast Under the staffing plan of the Civil Protection and Life-Safety Training-Methodological Center of Kyiv Oblast for training leadership and specialists involved in civil-protection organization and implementation for 2025, 1,930 people were trained, of whom 800 under state order and 1,130 under contract. Kirovohrad Oblast During 2025, 4 staff exercises were conducted with the management bodies and forces of the civil-protection territorial subsystem of Kirovohrad Oblast's unified state civil-protection system. Luhansk Oblast Implementation has not begun. Lviv Oblast Organizational-methodological guidelines for training the population of Lviv Oblast for emergency response for 2025–2026 have been developed and approved by order of the head of the oblast military administration No. 1470/0/5-24VA of 25.12.2024. A staffing plan for the Civil Protection and Life-Safety Training-Methodological Center of Lviv Oblast for 2025 was approved by order No. 9/0/5-25VA of 06.01.2025; plan fulfillment is 99%. The organizational-methodological guidelines were sent to healthcare institutions for use in their work. Health-department and healthcare-institution specialists regularly train various age groups on crisis-response actions, disease prevention, and life-safety basics (accounting for inclusivity requirements). This information is published on the Lviv Oblast Health Department's website and social-media pages, as well as those of healthcare institutions. Mykolaiv Oblast In 2025, population training was conducted under the organizational-methodological guidelines for training the population of Mykolaiv Oblast for emergency response for 2025, approved by order of the head of the Mykolaiv Oblast Military Administration No. 1-d of 03.01.2025. Poltava Oblast The oblast military administration's official web portal hosts the population evacuation procedure and the guide "Population actions during hazardous events and emergencies." Informational materials on this topic are regularly published in central, oblast, and district periodicals, on social media (Facebook, Twitter/X), through news agencies, and on official websites. Rivne Oblast A network of 273 civil-protection consultation points has been established in the oblast (order of the head of the oblast state/military administration No. 92 of 19.02.2025, "On organizing the work of civil-protection consultation points"). These points provide information and training to the population on civil protection from emergencies and other anticipated or occurring hazardous events. Sumy Oblast By order of the head of the Sumy Oblast State (Military) Administration No. 677-OD of 26.11.2024, a staffing plan for the Civil Protection and Life-Safety Training-Methodological Center of Sumy Oblast for 2025 was approved. 777 people were trained under state order, and 1,273 under contract. Ternopil Oblast During the reporting period, functional training was conducted for leadership and specialists involved in civil-protection organization and implementation among local executive authorities, local self-government bodies, enterprises, institutions, and organizations. 1,492 people completed functional training, of whom 540 under state order and 952 under contract. Khmelnytskyi Oblast 489 consultation points operate in the oblast to provide civil-protection information to the population at their place of residence, where training, information, and preparedness activities are conducted. Last year, over 2,400 people were trained at these points. Cherkasy Oblast In 2025, 211 sessions were conducted (in preschool institutions; general secondary schools; vocational institutions; higher-education institutions; with employees of enterprises, institutions, and organizations; with the local population; and during operational response to citizen reports of suspected explosive devices), reaching 2,964 people, with 1,702 units of printed informational materials distributed. Chernivtsi Oblast 75 informational events on the algorithm of actions under martial law were held; 550 informational materials on civil protection, life safety, and fire/technogenic safety were distributed. | Lviv Oblast 16293,12 | Mykolaiv Oblast 55,1 |  | . |
| 77. Improving Population Access to Labor Markets by Increasing Labor Mobility and Local-Needs Adaptation | 1) Conducting an active information campaign on local labor-market opportunities and the advantages of legal employment among vulnerable population groups directly in territorial communities. | 2025-2027 | population informed of local labor-market opportunities and the advantages of legal employment | Ongoig | Ministry of Economy The State Labor Service established an Interagency Working Group on coordinating joint actions to reduce undeclared labor and prevent occupational injuries and diseases. The Working Group developed and approved a National Plan of joint measures to reduce undeclared labor and occupational injuries for 2025. Quarterly reports on the National Plan's implementation are heard, with decisions made on any needed updates. Throughout 2025, the National Plan was implemented; 4 sessions of the Interagency Working Group were held. Draft Strategies for reducing undeclared labor (including in the informal economy), occupational injuries, and occupational diseases for 2026–2030, and for combating human trafficking for labor exploitation and forced labor for 2026–2030, have been prepared. To reduce undeclared labor, since the start of 2025, 100,007 informational visits to employers were conducted. 565 media announcements and 26,007 online publications were placed; 3,479 mass events (seminars, webinars, meetings, round tables) were held; 70,896 electronic mailings were sent to employers. As a result, employment contracts were concluded with 232,572 individuals. Since the start of 2025, during 267 compliance-monitoring activities on employment-relationship documentation, 350 workers were found working without an employment contract at 154 employers, and 174 workers were found with contracts substituted by other types of agreements at 37 employers. In addition, 519 workers were found who had signed employment contracts but were allowed to work without notifying the tax authorities, at 116 employers. As a result of compliance activities, 238 orders to remedy violations were issued; 201 administrative-offense protocols were filed with courts under Article 41, Part 3 of the Code of Ukraine on Administrative Offenses; materials from 27 compliance activities were referred to law-enforcement bodies due to indications of crimes under Articles 172 and 173 of the Criminal Code of Ukraine. 21 business entities remedied identified violations following the orders. As a result, 70 workers had employment contracts concluded. The "Come Into the Light!" information campaign runs annually at the end of summer, aimed at encouraging a shift from shadow, undeclared labor to legal, transparent labor relations, by informing workers and employers of their mutual rights and obligations, explaining the benefits of declared labor, and highlighting the risks of undeclared labor, especially under martial law. The campaign targets workers, unemployed persons, youth, and employers (particularly small and medium businesses), social partners, and society at large. Communications are conducted through social media (Facebook, Instagram), public-service announcements and informational materials in national and regional media (TV, radio, online, print), outdoor advertising (billboards and citylights), individual informational visits to employers, and partnerships with state bodies, local self-government bodies, and workers'/employers' organizations. A unified visual style and set of informational materials (posts, infographics, video and audio spots, billboard/citylight designs) was created for the campaign. In 2025, the "Come Into the Light!" campaign ran from 1 August to 1 October. Employers' and trade-union organizations, the State Tax Service, the Pension Fund, the Association of Ukrainian Cities, local authorities and self-government bodies, and civil-society organizations were involved. Given letters from the National Council of Ukraine on Television and Radio Broadcasting recognizing the campaign materials as social advertising, broadcasts were secured on national and regional TV channels, in public places, and in transport. The video was shown hourly on 30 Intercity+ trains and on monitors at railway stations of Ukrzaliznytsia, on "Pershyi," "Suspilne Krym," "Suspilne Kultura," and "Suspilne Sport" channels, as well as local and regional Suspilne channels (63 broadcasts on each), in public transport, and on shopping-mall and street-media screens. Overall, the video was shown over 520,000 times and the audio spot over 21,000 times. Within the campaign in 2025, 13,845 informational visits to employers were conducted, 213 billboards placed, 183 media announcements published, 9,301 online/social-media posts made, 445 informational events held, and 2,980 informational letters on employment-documentation rules sent. The campaign reached 12 million people (with at least one contact with the materials). As a result, employment contracts were concluded with 10,096 workers. To ensure effective enforcement of labor legislation regarding proper documentation of employment relationships, the State Labor Service conducted a quantitative cross-sectional study in July 2025 to assess the scale and structure of undeclared labor in Ukraine under martial law. The study found that approximately 23.4% of employed persons — nearly one in four, or roughly 2.68 million people — work without a documented employment relationship. Significant levels of undeclared labor were recorded in temporary accommodation and food services, security services, motor-vehicle repair, and trade. | Funding: within allocated budget appropriations. In 2025, UAH 688.5 million was spent under the budget program "Management and administration in the field of industrial safety, occupational health and safety, and labor-law compliance oversight." | - | - | - |
|  | 2) Providing information and advisory support to relocated businesses. | 2025-2027 | information and advisory support provided to 100% of relocated enterprises that request such services. | Ongoing | Ministry of Economy The State Labor Service launched a pilot advisory-support project for relocated enterprises in March 2022; from May 2022, advisory support was extended to all business entities. During 2025, 4,760 enterprises were informed about the project and the possibility of using the State Labor Service's services; 2,859 have already used such support, including 299 relocated enterprises that needed advisory assistance. Work to ensure informational support for relocated enterprises continues. State Emergency Service: Territorial units of the State Emergency Service conduct relevant work among business entities (including representatives of relocated businesses) regarding the administrative service of registering declarations of compliance of a business entity's material and technical base with fire-safety legislative requirements, through administrative-service centers. | Funding: within allocated budget appropriations; UAH 688.5 million was spent in 2025 under the same budget program noted above. | - | - | - |
| 78.Increasing the Investment Attractiveness of Territories, Supporting Investment Attraction, and Promoting Regional Investment Opportunities | 1) Creating oblast databases of energy-efficiency and alternative-energy investment projects. | 2025 | oblast investment-project databases created | Ongoing | Cabinet of Ministers Oblast state administrations provide, twice yearly as part of monitoring alternative-fuel use, information to the State Energy Efficiency Agency on planned potential energy-production projects: heat pumps; biomass/biogas; cogeneration; and secondary energy resources. |  |  |  |  |
|  | 2) Creating regional decarbonization and energy-efficiency offices. | 2025- 2027 | regional decarbonization and energy-efficiency offices created | Ongoing | Cabinet of Ministers In 2025, the State Energy Efficiency Agency provided organizational and advisory support to Ukraine's regions on investment attraction and promoting regional investment opportunities, resulting in the creation of 1 regional decarbonization and energy-efficiency office in Odesa. As of 31 December 2025, such offices operate in eight regions of Ukraine. |  |  |  |  |
|  | 3) Selecting energy-efficiency and decarbonization projects. | 2025- 2027 | at least 30 projects selected | Ongoing | Cabinet of Ministers In 2025, a commission established by the State Energy Efficiency Agency, under paragraph 6 of Annex 1 to the Procedure for Using Funds of the State Decarbonization and Energy-Efficiency Transformation Fund (approved by Cabinet of Ministers Resolution No. 761 of 21 June 2024), selected 56 energy-efficiency and decarbonization projects for state support. |  |  |  |  |
|  | 4) Holding international events in Ukraine and abroad (B2B, G2B, trade fairs, forums, business conferences) to promote regional investment potential. | 2025—2027 | at least 40 events held | Completed | Ministry of Economy representatives took part in the following events: - 02.03–07.03.2025 — preparatory event for the Ukraine Recovery Conference (URC 2025), Milan, Italy (Ministry of Economy funded). - 05.03–09.03.2025 — Conference on Investing in a More Sustainable and Secure Europe, Luxembourg, and consultations on preparing URC 2025, Paris, France (Ministry of Economy funded). - 07.03–08.03.2025 — Third UIF Steering Board Meeting, Brussels, Belgium (Ministry of Economy funded). - 07.03–15.03.2025 — Conference "Reform Priorities for an Inclusive Economic Recovery in Ukraine," London, UK (Ministry of Economy funded). - 17.03–19.03.2025 — Working Group on Responsible Business Conduct, Investment Committee, and Inclusive Platform on Due-Diligence Policy Cooperation (Ministry of Economy funded). - 31.03–02.04.2025 — OECD Investment Committee meeting, Paris, France (online). - 07.04–13.04.2025 — Round table "Forging the EU-Ukraine Future: A Defining Moment for Economic Recovery and Integration" and the EU-Ukraine Business Summit "EU support and accession driving Ukraine's economic recovery," Brussels, Belgium (Ministry of Economy funded). - 18.05–22.05.2025 — preparatory activities for URC 2025, Rome, Italy (Ministry of Economy funded). - 20.06.2025 — Network of National Contact Points meeting, Paris, France (online). - 06.07–14.07.2025 — Ukraine Recovery Conference (URC 2025), Rome, Italy (partly funded by the Ministry of Economy and the host). - 27.10–30.10.2025 — Working Group on Responsible Business Conduct, Investment Committee, and Inclusive Platform on Due-Diligence Policy Cooperation (Ministry of Economy funded). - 30.10.2025 — OECD Network of National Contact Points meeting, Paris, France (Ministry of Economy funded). - 07.11.2025 — OECD Investment Committee meeting, Paris, France (online). - 11.11–16.11.2025 — "ReBuild Ukraine Construction & Energy" conference, Warsaw, Poland (partly funded by the Ministry of Economy and the host). - 30.11–05.12.2025 — as part of the President's visit and participation in a business forum, Dublin, Ireland (Ministry of Economy funded). - 13.12–18.12.2025 — Ukrainian-German Business Forum, Berlin, Germany (Ministry of Economy funded). - 16.10.2025 — organized and held the conference "Responsible Business Conduct for Ukraine's Recovery: A Path to Sustainable Investment and European Integration," Kyiv. | 1472,1 |  |  |  |
| 79. Updating Regional Smart-Specialization Directions | Implementing the smart-specialization approach in Ukraine's regions in line with EU methodology. | 2025—2027 | smart-specialization priorities defined in regional development strategies | Ongoing | Ministry of Economy In implementing smart specialization within regional development in Ukraine, the following has been ensured: - Approval of Methodological Recommendations on applying smart specialization at the regional level (Ministry of Economy Order No. 14563 of 10.06.2024), developed based on the European Commission's Framework Approaches to smart specialization for EU enlargement and neighborhood countries. - Establishment of a Coordination Center for the implementation of smart specialization, a temporary consultative-advisory body under the Ministry of Economy. Its regulations and composition were approved by Ministry of Economy Order No. 25080 of 01.11.2024 (as amended). - Creation of regional teams (expert groups) tasked with organizing and managing the process of defining regional smart-specialization priorities. In 7 regions, with support from Joint Research Centre experts, the "entrepreneurial discovery" process has begun, which will result in defined smart-specialization priorities to be reflected in annexes to the regional development strategies. |  |  |  |  |
| 80. Development and implementation of mechanisms for supporting regional development projects aimed at developing priority types of economic activity identified on the basis of smart specialization and the need to transition to a climate-neutral economy | Incorporation of dedicated objectives and measures for science, technology and innovation development into regional development strategies and territorial community development strategies | 2025—2027 | Relevant strategies contain tasks and measures on scientific and technological development | Ongoing | Vinnytsia Oblast The oblast has in effect the Strategy for Balanced Regional Development of Vinnytsia Oblast for the period up to 2027, which, in accordance with the requirements of current legislation, has been updated and approved by Decision No. 1124 of the 66th session of the 8th convocation of the Vinnytsia Oblast Council of 25 April 2025 (hereinafter — the Strategy). The updated Strategy contains directions and measures related to the scientific and technological development of the region. In particular, Strategic Goal I, "A Competitive Region Based on Innovative and Sustainable Development," contains Operational Goal 1.4, "Innovative Development of the Region," whose main tasks are: 1.4.1. Supporting the deployment of renewable energy as a component of energy independence; 1.4.2. Developing industrial, innovation, and technology parks, supporting the development of technical infrastructure, attracting investment, and providing investor support. Donetsk Oblast The Strategy for the Development of Donetsk Oblast for the period up to 2027 (approved by Order No. 147/5-20 of the Head of the Oblast State Administration, Head of the Oblast Military Administration, dated 17.02.2020, as amended) defines Operational Goal 3.2, "Creating conditions for post-war recovery using scientific and innovative solutions." The Action Plan for the implementation of the Strategy for the Development of Donetsk Oblast for the period up to 2027 in 2025–2027 (approved by Order No. 913/5-25 of the Head of the Oblast State Administration, Head of the Oblast Military Administration, dated 30.12.2025) provides for the development of the Program for Innovative Development of Donetsk Oblast for 2028–2030. Zhytomyr Oblast Assisting farmers in mastering innovative methods of organic agricultural production, including through the development of the craft sector. Zakarpattia Oblast In the updated Strategy for the Development of Zakarpattia Oblast for the period up to 2027 dated 19.12.2024 No. 1216 — Strategic Goal 2, "Increasing the Competitiveness of the Region," and Operational Goal 2.1.4, "Knowledge transfer, support for innovative research, and technology transfer based on 'education–science–production' chains, support for start-ups," the performance indicators of which are: - Number of industrial enterprises implementing innovations — 19; - Number of new business entities in the region's high-tech economic sectors — 9. Zaporizhzhia Oblast In accordance with paragraph 12 of the Procedure for the Development, Approval, Monitoring, and Evaluation of Implementation of Regional Development Strategies and Action Plans for Their Implementation (Resolution No. 816 of the Cabinet of Ministers of Ukraine of 04.08.2023, as amended by Resolution No. 81 of the Cabinet of Ministers of Ukraine of 28.01.2026), for draft regional strategies of regions in which, at the time development began, more than 30% of territorial communities belong to areas of hostilities and/or areas temporarily occupied by the Russian Federation (in accordance with the order of the Ministry for Development of Communities and Territories), the provisions on taking smart specialization priorities into account may not be applied. Given the above, work on implementing the smart specialization approach in the oblast has been suspended. Ivano-Frankivsk Oblast The updated Strategy for the Development of Ivano-Frankivsk Oblast for 2021–2027, approved by Decision No. 1393-46/2026 of the Oblast Council of 20.02.2026, contains the task "Promoting the scientific and technological development of designated priority economic activities through the organization of cooperation with educational and scientific institutions." |  |  |  |  |
|  |  |  |  |  | Kyiv Oblast Regional development projects aimed at developing priority types of economic activity identified on the basis of smart specialization are provided for in the Action Plan for the implementation of the Strategy for the Development of Kyiv Oblast for 2021–2027 in 2025–2027, approved by Decision No. 1531-35-VIII of the Kyiv Oblast Council of 4 December 2025, as well as in the development of new oblast targeted programs. |  |  |  | Kyiv Oblast Limited investment capacity of budgets at all levels and of scientific and business entities is hindering the implementation of regional development projects aimed at developing priority types of economic activity identified on the basis of smart specialization. |
|  |  |  |  |  | Kirovohrad Oblast Strategy-2027 contains tasks and measures on scientific and technological development. In particular, within Strategic Goal 1, "A Competitive, Innovation-Oriented Economy Developing on the Basis of Smart Specialization," Operational Goal 1.3, "Development of existing and creation of new high-tech industries taking into account smart specialization principles," contains the following tasks: - development of priority types of economic activity, including those identified on the basis of smart specialization; - stimulating the development of innovation potential and intellectual services infrastructure, intensifying cooperation between the oblast's enterprises and scientific institutions and higher education institutions, in particular regarding the generation of new scientific and innovative developments and their introduction into production. Luhansk Oblast On the basis of paragraph 12 of the Procedure for the Development of Regional Development Strategies and Action Plans for Their Implementation, as well as Monitoring of the Implementation of Such Strategies and Action Plans, approved by Resolution No. 816 of the Cabinet of Ministers of Ukraine of 04.08.2023 (as amended by Resolution No. 81 of the Cabinet of Ministers of Ukraine of 28.01.2026), the principles of smart specialization were not applied in the development of the draft Strategy in its new edition. Lviv Oblast The Strategy for the Development of Lviv Oblast for the period 2021–2027, approved by Decision No. 664 of the Oblast Council of 03.02.2026, contains a task on promoting scientific and technological development. In particular, this concerns Task 2.1.4, "Promoting scientific and technological development," under Operational Goal 2.1, "Development of the region's smart specialization." Poltava Oblast The regional development strategy and community development strategies contain tasks and measures on scientific and technological development. |  |  |  | Kirovohrad Oblast Decline in the level of innovation and investment activity of the oblast's business entities; insufficient own sources of financing for enterprises; absence of state innovation support instruments. |
|  |  |  |  |  | Rivne Oblast The tasks and measures of the Strategy for the Development of Rivne Oblast for the period up to 2027 are aimed at developing priority smart specialization sectors. At LLC "Kronospan Rivne," within the framework of an investment project to build a wood-processing plant in the village of Horodok with a capacity of 1,400 thousand m³ per year (a line for producing OSB (oriented strand board) with a capacity of 600 thousand m³ per year has been commissioned), 17 jobs were created. At LLC "ODEK Ukraine," the investment project "Increasing plywood production, 4x8 ft." is in its final stage of implementation, increasing capacity from 116 thousand m³ per year to 136 thousand m³ per year, creating 30 jobs. Sumy Oblast The updated Strategy for the Regional Development of Sumy Oblast for 2021–2027, approved by Decision of the Sumy Oblast Council of 30.04.2025, provides for the implementation of smart specialization at the regional level within the framework of Operational Goal 1.1, "A Competitive Industrial and Agricultural Complex of the Region," under Strategic Goal 1, "Increasing the Level of Competitiveness and Security of the Region" (Task 1.1.2, "Supporting the implementation of economic projects for the restoration and development of energy facilities involving the oblast's machine-building enterprises to ensure energy security and independence on the basis of smart specialization"; 1.1.3, "Production of innovative products by the region's light industry enterprises"; and 1.1.4, "Creating conditions for the production, storage, and deep processing of agricultural products, including on the basis of smart specialization"). The Strategy provides for the introduction of the latest production technologies and the manufacture of high-value-added products, taking into account the region's machine-building technological and production capacities and the latest technological developments of scientific institutions, in particular within the framework of the activities of the public union "Sumy Machine-Building Cluster of Power Equipment," which includes enterprises from the energy, machine-building, chemical, and oil-and-gas engineering sectors, as well as Sumy State University. Ternopil Oblast Tasks and measures on the oblast's scientific and technological development, aimed at developing priority types of its economic activity, including creating conditions for the integration of science, education, and the oblast's smart sectors, have been included in the updated Strategy for the Development of Ternopil Oblast for 2021–2027. Kharkiv Oblast The Strategy for the Development of Kharkiv Oblast for 2021–2027 (in its new edition), approved by Decision No. 1150-VIII of the Oblast Council of 24 April 2025 (hereinafter — the Strategy), contains goals, tasks, and measures aimed at ensuring the region's scientific and technological development: Strategic Goal 4. Ensuring an investment-attractive climate in the region and creating innovation and investment infrastructure. Operational Goal 4.1. Supporting innovation and entrepreneurship development through the development of investment and innovation infrastructure. Tasks: - creating and developing innovation hubs: science and industrial parks, technology parks, business incubators, and accelerators to support start-ups and innovative enterprises; - stimulating cooperation between the production sector, education, and science to generate and implement innovations; - promoting the attraction of investment resources, funds from international organizations, EU programs, and global financial institutions for the implementation of economic restructuring projects. Operational Goal 4.2. Communication support and promotion of the region's investment offering. Tasks: - promoting economic platforms in the region to increase the competitiveness of small and medium-sized enterprises in the oblast; introducing and supporting information-analytical online services for investors and entrepreneurs; developing and promoting the brand of Kharkiv Oblast, organizing information campaigns to promote the region on the world stage. Operational Goal 4.3. Increasing investment security and restoring war losses. Task: programming the reconstruction and modernization of the region's infrastructure on the "Build Back Better" principle, defining recovery priorities and mechanisms for restoring damaged infrastructure in de-occupied districts. Kherson Oblast The process of updating the regional strategy is ongoing. Khmelnytskyi Oblast Within the framework of Operational Goal 1.4, "Growth of Innovation Potential and Smart Specialization of the Region," of the regional strategy, a set of scientific and technological development measures is provided for, aimed at supporting applied research, innovative start-ups, and the introduction of modern technologies in smart specialization sectors. Cherkasy Oblast The updated Strategy for the Development of Cherkasy Oblast for the period 2021–2027 defines tasks and measures on scientific and technological development, in particular within the framework of the region's smart specialization directions. Thus, smart specialization direction S.1, "Innovative agrotechnologies, production and processing of agricultural products, high quality of food products," provides for operational goals and tasks on cooperation between the region's science and business in the development of technologies for producing, processing, and promoting agricultural products, improving the quality and safety of food products, and developing climate-oriented agriculture. Smart specialization direction S.2, "Development of the IT sector and information and communication technologies," provides for engaging the scientific sector and business in the development of IT technologies, in particular through cooperation with the public union "Cherkasy IT Cluster," which includes IT companies of Cherkasy Oblast. The cluster actively cooperates with higher education institutions, training and employing students. In addition, within the framework of Strategic Goal 1, "Strengthening the Economic Capacity of the Region," tasks are provided for modernizing the industrial complex by reducing the energy intensity of production, increasing production efficiency through the introduction of innovations, creating a machine-building cluster, and developing a network of industrial parks. Tasks and measures on scientific and technological development are detailed in the Action Plan for 2025–2027 for the implementation of the Strategy for the Development of Cherkasy Oblast for the period 2021–2027 (approved by Decision No. 35-6/VIII of the Cherkasy Oblast Council of 13.03.2026). In particular, within the framework of the region's smart specialization directions, the Action Plan includes the following implementation tools: introduction of technologies for processing animal-origin waste to produce biogas; introduction of new cultivation technologies adapted to climate change in the region (in cooperation with Uman National University); development and innovative upgrading of irrigation systems for use in the oblast's agricultural sector; conducting seminars for the oblast's communities on nature-based technologies for preserving and restoring soil fertility; introducing innovations into food production; an intelligent platform for the ultrasonic extraction of plant raw materials for personalized nutritional support and the production of functional beverages to improve the quality of life of people with post-traumatic stress disorders (based at Cherkasy State Technological University); an energy-efficient modular technological platform for producing adaptive functional food products (for wounded servicemembers) under martial law and post-war reconstruction conditions (based at Cherkasy State Technological University); establishment of the Cherkasy State Technological University Shared Scientific Equipment Center "Analytics & Prototypes" (A&P Center); and holding the ITFUSION BUSINESS FORUM. In addition, within the framework of Strategic Goal 1, "Strengthening the Economic Capacity of the Region," the Action Plan includes the following projects and measures: installation of energy-saving and energy-generating equipment at enterprises; promotion of regional business innovations; conducting a regional analysis of the production potential of machine-building enterprises in the region; creating and developing a network of industrial and eco-industrial parks, forming regional processing clusters with their participation, and supporting the participation of the oblast's industrial parks in the GEIPP-II Ukraine project (UNIDO). As of 1 January 2026, 49 territorial communities in Cherkasy Oblast had their own approved development strategies. In accordance with Part 2 of Article 11-1 of the Law of Ukraine "On the Principles of State Regional Policy," draft territorial community development strategies are developed taking into account the priorities defined by the relevant regional development strategies. The Cherkasy Oblast Military Administration is currently carrying out consultative and methodological work with the oblast's territorial communities to bring their own development strategies into line with the updated Strategy for the Development of Cherkasy Oblast for the period 2021–2027. Chernivtsi Oblast The Strategy for the Development of Chernivtsi Oblast for the period up to 2027 defines, on the basis of smart specialization, Strategic Goal 1, "SMART Increasing the Competitiveness of the Region through the Innovative Development of Agriculture, Processing Industry, and Tourism." Achievement of this strategic goal is envisaged through the implementation of the following operational goals: - Stimulating the innovative development of agriculture. - Increasing the competitiveness of products from leading industrial sectors. - Increasing the economic resilience of business entities. - Developing tourism and recreation. - Forming a modern system for training personnel for the needs of the regional economy, including taking into account the needs of relocated businesses. The Action Plan for the implementation, in 2025–2027, of the Strategy for the Development of Chernivtsi Oblast for the period up to 2027, under Strategic Goal 1, "SMART Increasing the Competitiveness of the Region through the Innovative Development of Agriculture, Processing Industry, and Tourism," includes 24 regional development projects and measures with a total value of UAH 2,672,515.0 thousand. Chernihiv Oblast The Sustainable Development Strategy of Chernihiv Oblast for the period up to 2027 contains the main tasks and pathways for developing the oblast's smart specialization sectors and scientific and technological development, set out under Operational Goal 3.3, "Accelerated innovative development of the region's priority smart specialization sectors," of Strategic Goal 3, "Restoring business and building a new economy for the region." |  |  | Rivne Oblast 1.802,900.0 (enterprise funds) 2.128,300.0 (enterprise funds) |  |
| Area: Tourism |  |  |  |  |  |  |  |  |  |
| 81. Creating conditions for developing the recreational and tourism potential of territories, taking into account natural and security constraints | preparation of proposals for amendments to legislation on resorts to create conditions for the development of the recreational and tourism potential of territories, taking into account natural and security constraints | 2026 | Cabinet of Ministers of Ukraine act has been adopted | Ongoing | State Agency for Tourism Development of Ukraine The draft Law of Ukraine "On Amendments to Certain Legislative Acts of Ukraine Regarding Ensuring the Environmental Safety of Water Use" has been finalized and sent to central executive authorities for approval. Submission to the Cabinet of Ministers is planned for 2026. |  |  |  | Comments were received from the Ministry of Health on the draft law concerning mechanisms for monitoring compliance with water-use safety standards. After the comments are addressed, the new version of the law will be sent to the Ministry of Justice for approval. The Law of Ukraine "On the Declaration of the Natural Territories of the Kuyalnyk Estuary of Odesa Oblast as a Resort of National Significance" of 5 December 2018 No. 2637-VIII (hereinafter — the Law) provides that the Cabinet of Ministers of Ukraine must, within six months of this Law entering into force, approve the regime of the district and sanitary protection zones of the Kuyalnyk resort in Odesa Oblast. At the same time, it has been established that the draft Resolution of the Cabinet of Ministers of Ukraine "On Approving the Regime of the District and Sanitary Protection Zones of the Kuyalnyk Resort of Odesa Oblast" was not developed and submitted to the Cabinet of Ministers for approval. Work is currently underway on developing a draft resolution for approval with the Odesa Oblast Military Administration and interested central executive authorities. |
| 82. Promoting the proper arrangement of tourist routes and tourist attractions, their digitalization, and the creation of comfortable and safe conditions for tourists (visitors) | development of recommendations for the proper arrangement of tourist routes and tourist attractions | 2026 | recommendations developed and published on the official website of SATD | Ongoing | SATD A meeting was held with the technical committee for standardization "Tourism and Tourism Services." |  |  |  |  |
| 83.Promoting the formation of local tourism brands and the popularization of the tourism potential of regions and territorial communities, including through the use of digital technologies | 1) study and analysis of local tourism brands in the regions of Ukraine | 2025 | at least 50 local tourism brands in the regions of Ukraine analyzed | Ongoing | SATD An analysis of local tourism brands in the regions of Ukraine has been conducted. Consultations are planned for 2026–2027. |  |  |  |  |
|  | 2) holding consultations (presentations) on theoretical and practical steps for creating/developing local tourism brands in territorial communities | 2025—2027 | at least 20 consultations held for local self-government bodies | Ongoing | SATD An analysis of local tourism brands in the regions of Ukraine has been conducted. Consultations are planned for 2026–2027. |  |  |  |  |
| 84. Intensifying work on nominating sites of unique value that could potentially belong to the UNESCO World Heritage List | ensuring the review and updating of the list of Ukrainian cultural and natural heritage sites included in the UNESCO World Heritage Tentative List | 2025—2027 | at least five nomination dossiers submitted for inclusion in the UNESCO World Heritage Tentative List and the UNESCO World Heritage List | Ongoing | Ministry of Culture and Strategic Communications of Ukraine Work is currently underway to complete the application for including the site "Cultural Landscape of Chernihiv" in the UNESCO World Heritage Tentative List. In addition, the nomination dossier for the cultural heritage site "Sofiyivka Park. A Romantic Park — An Echo of Antiquity" (hereinafter — the ND) was reviewed on 16 July 2025 at a meeting of the Scientific and Methodological Council on Cultural Heritage Protection of the Ministry of Culture and was recommended, after finalization, for submission for review to the Ukrainian National Committee of ICOMOS, with subsequent transmission to the Secretariat of the UNESCO World Heritage Committee. On 30.12.2025, a revised ND was received from the National Dendrological Park "Sofiyivka" of the National Academy of Sciences of Ukraine, which is planned to be sent for submission to the UNESCO World Heritage Centre. On 18.09.2025, a Memorandum was signed between the Ministry of Culture and Strategic Communications of Ukraine, the Ministry of Culture of the Republic of Moldova, and the Ministry of Culture of Romania on cooperation in preparing and promoting a joint nomination dossier for inclusion in the UNESCO World Heritage List of the transnational serial site "Cultural Complex of Precucuteni-Ariușd-Cucuteni-Trypillia." Work is currently underway to prepare the relevant nomination dossier. Ministry of Economy Research is being conducted on the location and value of the gypsum karst caves of Western Ukraine for the purpose of including them in the UNESCO World Heritage Tentative List. |  |  |  |  |
| Стратегічна ціль «Розбудова ефективного багаторівневого врядування» |  |  |  |  |  |  |  |  |  |
| Оперативна ціль 1. Розвиток інституційної спроможності органів публічної влади з урахуванням кращих практик ЄС |  |  |  |  |  |  |  |  |  |
| Напрям «Інструменти планування та підзвітності у регіональній політиці» |  |  |  |  |  |  |  |  |  |
| 85. Updating strategic planning documents and the implementation of regional policy taking into account priorities for the recovery and development of regions and territories affected by the armed aggression of the Russian Federation, in particular regarding the restoration (preservation) of balanced (sustainable) ecosystem development and adaptation to climate change | ensuring that the tasks and measures of regional development strategies are brought into line with the provisions of the updated State Strategy for Regional Development for 2021–2027, taking into account smart specialization principles | 2025 | amendments made to 100% of regional development strategies |  | Vinnytsia Oblast To ensure the implementation of state regional development policy under the conditions of the Russian Federation's full-scale invasion, and to form appropriate preconditions for post-war recovery — which requires the mobilization of significant resources as well as their effective allocation and management — Decision No. 1124 of the 66th session of the 8th convocation of the Vinnytsia Oblast Council of 25 April 2025 introduced amendments to the Strategy for Balanced Regional Development of Vinnytsia Oblast for the period up to 2027, approved by Decision No. 921 of the 42nd session of the 7th convocation of the Oblast Council of 21 February 2020. Dnipropetrovsk Oblast The Strategy for the Development of Dnipropetrovsk Oblast for the period up to 2027 has been updated in accordance with the provisions of the updated State Strategy for Regional Development for 2021–2027, taking into account smart specialization principles (Decision No. 502-25/VIII of the Dnipropetrovsk Oblast Council of 07.05.2025, "On Amending Decision No. 624-24/VII of the Oblast Council of 7 August 2020 'On the Regional Development Strategy of Dnipropetrovsk Oblast for the Period up to 2027'"), and an Action Plan for its implementation has also been approved. Donetsk Oblast By Order No. 309/5-25 of the Head of the Oblast State Administration, Head of the Oblast Military Administration, dated 01.05.2025, "On Amending Order No. 147/5-20 of the Head of the Oblast State Administration, Head of the Oblast Military-Civil Administration, of 17 February 2020," the updated Strategy was approved. By Order No. 913/5-25 of the Head of the Oblast State Administration, Head of the Oblast Military Administration, dated 30.12.2025, the Action Plan for the implementation of the Strategy for the Development of Donetsk Oblast for the period up to 2027 in 2025–2027 was approved. Zhytomyr Oblast The Strategy for the Development of Zhytomyr Oblast for the period up to 2027, approved by Decision No. 1722 of the Zhytomyr Oblast Council of 18.12.2019 (as amended on 24.12.2020 No. 16 and on 10.04.2025 No. 889). Zakarpattia Oblast The Strategy for the Development of Zakarpattia Oblast for the period up to 2027 was approved by Decision of the Oblast Council session of 19.12.2024 No. 1216. The Action Plan for the implementation, in 2026–2027, of the Strategy for the Development of Zakarpattia Oblast for the period up to 2027 was approved by Decision of the Oblast Council session of 19.03.2026 No. 1553. Zaporizhzhia Oblast The Regional Development Strategy of Zaporizhzhia Oblast for the period up to 2027 was approved by Decision No. 134 of the Oblast Council of 12.12.2019 (hereinafter — the Strategy). The Strategy's strategic goals, operational goals, and tasks were aimed at the region's long-term socio-economic growth and improving the quality of life of its residents. Since the start of the Russian Federation's full-scale invasion, 87% of the territory of Zaporizhzhia Oblast has been and currently remains under temporary occupation or in an area of active hostilities — 54 out of 67 territorial communities (in accordance with the order of the Ministry for Communities, Territories and Infrastructure Development). The remainder of the oblast's territory (13 communities) is located in a zone of possible hostilities and is classified as the "orange zone" — territory within 25–70 km of the zone of active hostilities (high risk), under constant threat of Russian attacks. Given the occupation of most of the region's territory, ongoing destruction from shelling, and maximum proximity to the front line, the region's medium-term development forecast is subject to heightened uncertainty regarding the development of events related to the full-scale war. Consequently, these circumstances have objectively made it impossible to carry out work on updating the Strategy. Ivano-Frankivsk Oblast Appropriate organizational and practical work has been carried out to update and revise the oblast's Development Strategy for 2021–2027. Order No. 530 of the Oblast State Administration of 02.12.2024 established a working group to carry out the relevant tasks. The updated Strategy was approved by Decision No. 1393-46/2026 of the Oblast Council of 20.02.2026. Kyiv Oblast The updated Strategy for the Development of Kyiv Oblast for 2021–2027, approved in its new edition by Decision No. 1259-31-VIII of the Kyiv Oblast Council of 6 March 2025. This Strategy complies with the main provisions of the updated State Strategy for Regional Development for 2021–2027, taking into account smart specialization principles. Kirovohrad Oblast In accordance with the requirements of Resolution No. 940 of the Cabinet of Ministers of Ukraine of 13 August 2024, "On Amending the State Strategy for Regional Development for 2021–2027," Decision No. 540 of the Kirovohrad Oblast Council of 4 July 2025 introduced amendments to the Strategy for the Development of Kirovohrad Oblast for 2021–2027. Luhansk Oblast In 2025, work began on developing a draft new edition of the Strategy for the Development of Luhansk Oblast for 2021–2027 (hereinafter — the Strategy). Four meetings of the working group on developing the draft Strategy for the Development of Luhansk Oblast and its implementation action plans were held. An opinion was received from the Ministry for Communities, Territories and Infrastructure Development dated 18.03.2026 confirming that the draft Strategy complies with the established requirements for its preparation, as well as with the strategic goals and priorities defined by the State Strategy for Regional Development of Ukraine. A draft order of the Head of the Oblast State Administration — Head of the Oblast Military Administration on approving the draft Strategy is being prepared. On the basis of paragraph 12 of the Procedure for the Development of Regional Development Strategies and Action Plans for Their Implementation, as well as Monitoring of the Implementation of Such Strategies and Action Plans, approved by Resolution No. 816 of the Cabinet of Ministers of Ukraine of 04.08.2023, the principles of smart specialization were not applied in the development of the draft Strategy in its new edition. Lviv Oblast Work has been carried out to update the Strategy for the Development of Lviv Oblast for the period 2021–2027, approved by Decision No. 948 of the Lviv Oblast Council of 24.12.2019, and to bring its tasks and measures into line with the provisions of the updated State Strategy for Regional Development, taking into account smart specialization principles. The updated Strategy was approved at the Oblast Council session on 03.02.2026 (Decision No. 664). Mykolaiv Oblast The updated Strategy for the Development of Mykolaiv Oblast for the period up to and including 2027 contains tasks on scientific and technological development aimed at accelerating the introduction of new technologies, improving production efficiency, product quality, and the competitiveness of the economy. These tasks are: 2.4.1. Developing business support infrastructure; 4.2.1. Promoting the development of highly qualified personnel potential in smart specialization sectors. The development of the Action Plan for the implementation of the Development Strategy will be carried out under the updated Procedure (as amended by Resolution No. 81 of the Cabinet of Ministers of Ukraine of 28.01.2026 and in accordance with the recommendations of the Ministry for Communities, Territories and Infrastructure Development). Odesa Oblast By Decision No. 768-VIII of the Odesa Oblast Council of 06.06.2025, the Strategy for the Recovery and Development of Odesa Oblast for the period 2021–2027 was updated, and by Decision No. 769-VIII of 06.06.2025, the Action Plan for the implementation, in 2025–2027, of the Strategy for the Recovery and Development of Odesa Oblast for the period 2025–2027 was approved. Poltava Oblast Amendments to the Regional Development Strategy of Poltava Oblast for 2021–2027 were introduced by Decision No. 889 of the Oblast Council session of 24 December 2024, bringing it into line with the provisions of the updated State Strategy for Regional Development for 2021–2027. Rivne Oblast In 2025, the Strategy for the Development of Rivne Oblast up to 2027 was updated and approved (Order No. 122 of the Head of the Oblast State Administration — Head of the Oblast Military Administration of 28.02.2025; Decision No. 1069 of the Oblast Council of 28.03.2025). The draft Strategy received a positive opinion from the Ministry for Communities, Territories and Infrastructure Development confirming compliance with the requirements for preparing strategic documents, as well as with the strategic goals and priorities defined by the State Strategy for Regional Development of Ukraine (letter dated 20.02.2025 No. 3987/35/10-25). Sumy Oblast By Decision of the Sumy Oblast Council of 30.04.2025, amendments were made to the Regional Development Strategy of Sumy Oblast for 2021–2027, taking into account smart specialization principles. Ternopil Oblast In order to bring the tasks and measures of the regional development strategy into line with the provisions of the updated State Strategy for Regional Development for 2021–2027, the oblast has developed an updated Strategy for the Development of Ternopil Oblast for 2021–2027, approved by Order No. 222/01.02-01 of the Head of the Oblast Military Administration of 4 April 2025. Kharkiv Oblast In fulfillment of paragraph 3 of Resolution No. 940 of the Cabinet of Ministers of Ukraine of 13.08.2024, Kharkiv Oblast approved, by Decision No. 1150-VIII of the Oblast Council of 24 April 2025, the Strategy for the Development of Kharkiv Oblast for 2021–2027 (in its new edition). Kherson Oblast Within the framework of cooperation with the international technical assistance project "Polaris Programme: Supporting Multi-Level Governance in Ukraine," work continues on updating the Strategy for the Development of Kherson Oblast for the period 2021–2027. Data collection has been completed for describing the main trends and socio-economic development problems of the region and identifying potential smart specialization directions. Khmelnytskyi Oblast The Regional Development Strategy of Khmelnytskyi Oblast for 2021–2027 was updated in 2025. During the update of the Strategy, consistency between strategic and operational goals, tasks, and measures with state regional policy priorities was ensured, along with the integration of approaches oriented toward innovative development, structural economic transformation, and increased regional competitiveness. Cherkasy Oblast In order to bring it into line with the provisions of the updated State Strategy for Regional Development for 2021–2027, amendments were made to the Strategy for the Development of Cherkasy Oblast for the period 2021–2027. The updated Strategy was approved by Decision No. 35-5/VIII of the Cherkasy Oblast Council of 13.03.2026. The updated Strategy defines two smart specialization directions for the region: 1. Innovative agrotechnologies, production and processing of agricultural products, high quality of food products. 2. Development of the IT sector and information and communication technologies. Chernivtsi Oblast The Strategy for the Development of Chernivtsi Oblast for the period up to 2027 has been updated and brought into line with the provisions of the updated State Strategy for Regional Development for 2021–2027, taking into account smart specialization principles. By Decision No. 5-20/25 of the 20th session of the 8th-convocation Oblast Council of 11.09.2025, the Strategy for the Development of Chernivtsi Oblast for the period up to 2027 (in its updated edition) was approved. By Decision No. 1-22/26 of the 22nd session of the 8th-convocation Oblast Council of 29.01.2026, the Action Plan for the implementation, in 2025–2027, of the Strategy for the Development of Chernivtsi Oblast for the period up to 2027 was approved. Chernihiv Oblast By Decision No. 3-22/VIII of the 22nd session of the 8th-convocation Chernihiv Oblast Council of 14.03.2025, amendments were made to the Sustainable Development Strategy of Chernihiv Oblast for the period up to 2027. The opinion of the Ministry for Communities, Territories and Infrastructure Development confirming that the draft regional development strategies, their implementation action plans, and amendments thereto comply with the established requirements for their preparation and with the strategic goals and priorities defined by the State Strategy for Regional Development of Ukraine was issued on 03.03.2025, No. 5050/35/10-25. |  |  |  |  |
| 86. Ensuring the alignment of sectoral strategies with the goals and priorities of state regional policy | ensuring the alignment of draft acts of the Cabinet of Ministers of Ukraine with the strategic goals and priorities of the State Strategy for Regional Development of Ukraine | 2025—2027 | at least 80 draft acts of the Cabinet of Ministers of Ukraine reviewed and corresponding opinions provided on them | Ongoing | Ministry for Communities, Territories and Infrastructure Development Resolution No. 361 of the Cabinet of Ministers of Ukraine of 26 March 2026, "On Approving the Procedure for the Development, Monitoring, and Evaluation of the Results of Implementation of Strategies that Form the Basis for Developing Public Investment Proposals," has been adopted. |  |  |  |  |
| 87. Introducing local statistics, creating tools for the collection, storage, and processing of local statistical data, including gender-disaggregated data | development of mechanisms for collecting, aggregating, and analyzing statistical data at the level of communities and regions | 2025—2027 | a local statistics collection system has been introduced and is used for strategic planning, monitoring, and evaluation of the implementation of state regional policy | Ongoing | Ministry for Communities, Territories and Infrastructure Development Amendments to Resolution No. 305 of the Cabinet of Ministers of Ukraine of 15 March 2024 are being prepared with a view to restoring the monitoring and evaluation of state regional policy. Minrozvytku, in cooperation with the State Statistics Service (Derzhstat), is working on developing a municipal statistics system to take into account the needs of assessing the capacity and development of territorial communities. |  |  |  |  |
| 88.З Introducing a unified geoinformation system for monitoring and evaluating the development of regions and territorial communities as a component of the Unified Digital Integrated Information-Analytical Management System for the Reconstruction of Real Estate, Construction, and Infrastructure (DREAM) | 1) development and approval of the Operating Regulations for the unified geoinformation system for monitoring and evaluating the development of regions and territorial communities | 2025—2026 | an order of Ministry for Communities, Territories and Infrastructure Development has been issued and registered with the Ministry of Justice | Ongoing | Ministry for Communities, Territories and Infrastructure Development The draft order of Ministry for Development of Communities and Territories has completed the development stage and, upon completion of the approval procedure, will be submitted to the Ministry of Justice. |  |  |  |  |
|  | 2) ensuring the development of regional development strategies and territorial community development strategies in digital format using the functional capabilities of the unified geoinformation system for monitoring and evaluating the development of regions and territorial communities | 2025—2026 | at least one regional development strategy and at least three territorial community development strategies developed in digital format |  | Ministry for Communities, Territories and Infrastructure Development By Order No. 1218 of Ministry for Ministry for Communities, Territories and Infrastructure Developmentdated 5 August 2025, the software of the geoinformation system for regional development (hereinafter — GIS RR) was put into pilot operation. All oblast state (military) administrations / the Kyiv City State (Military) Administration are actively engaged in working with GIS RR. In particular, as of 31 December 2025, 25 regional development strategies had been entered into GIS RR, of which 21 had been signed within the system, and 1 (Ternopil) was awaiting signature by the responsible official. At the same time, 3 draft updated regional development strategies (Lviv, Ivano-Frankivsk, Cherkasy) had been entered into the system but were still awaiting approval by the relevant oblast council, so the strategies had not yet been signed within the system. In addition, as of 31 December 2025, representatives of territorial communities from 5 pilot oblasts (Vinnytsia, Dnipropetrovsk, Mykolaiv, Rivne, Poltava) had begun working in GIS RR. |  |  |  |  |
|  | 3)modernization and expansion of the functionality of the unified geoinformation system for monitoring and evaluating the development of regions and territorial communities | 2027 | modernized functionality has been put into operation | Not started | The deadline for implementing this measure has not yet arrived. |  |  |  |  |
| 89. Creating conditions for increasing the accountability and transparency of state authorities and local self-government bodies at all levels, engaging residents — including internally displaced persons — in decision-making, disseminating best practices for establishing public self-organization bodies, and introducing mechanisms for electronic public consultations | 1)development of methodological recommendations for measuring the Digital Transformation Index of regions and the Digital Transformation Index of territorial communities | 2025 | an order of the Ministry of Digital Transformation has been issued | Ongoing | Ministry of Digital Transformation The structure of the Digital Transformation Index has been adapted to martial-law conditions. For frontline regions and communities, the draft Methodology retains only priority and currently relevant indicators. All indicators have been comprehensively brought into line with current legislation and the requests of oblast military administrations and territorial communities. The draft Methodology is undergoing internal approval within Ministry of Digital Transformation. |  |  |  |  |
|  | 2) ensuring quarterly determination of the level of digital transformation of regions and territorial communities on the "Diia. Digital Community" web portal | 2025—2027 | the level of digital transformation of regions and territorial communities published on the "Diia. Digital Community" web portal | in progress | Ministry of Digital Transformation Reporting data has been published at the following link:: https://hromada.gov.ua/research/indeks-cifrovoyi-transformaciyi-regioniv-ukrayini-2025-rik |  |  |  |  |
| 90. Creating a coordinated system of strategic, spatial, and budget planning for regional development at the national, regional, and local levels | optimization of the architecture of planning documents for the recovery and development of regions and territorial communities | 2025—2026 | legislative amendments adopted to simplify the system of planning documents | Ongoing | Ministry for Communities, Territories and Infrastructure Development The draft Law has completed the external approval procedure and is being prepared for submission to the Government for consideration. |  |  |  |  |
| Area: "Building the Capacity of State Regional Policy Actors" |  |  |  |  |  |  |  |  |  |
| 91.Promoting the improvement of the professional knowledge, skills, and abilities of civil servants and local self-government officials, in particular in the areas of strategic planning, public service delivery, budgeting (including gender-responsive budgeting), and investment attraction | ensuring training for civil servants and local self-government officials on strategic planning, public service delivery, budgeting (including gender-responsive budgeting), and investment attraction | 2025 – 2027 | training provided to at least 500 people | ongoing on a continuous basis | National Agency of Ukraine for Civil Service (NAUCS) In 2025, at the Higher School of Public Administration and regional professional development centers, training was completed on the following topics: strategic planning — 2,526 people (796 civil servants, 1,730 local self-government officials); public service delivery — 1,289 people (270 civil servants, 1,019 local self-government officials); budgeting, including gender-responsive budgeting — 1,178 people (233 civil servants, 945 local self-government officials); investment attraction — 785 people (89 civil servants, 696 local self-government officials). At educational institutions selected through competitive procedures as executors of NAUCS's state order for professional development, 274 people completed training on strategic management and planning, of whom 228 were civil servants and 46 were local self-government officials. |  |  |  |  |
| 92. Ensuring methodological and organizational support for the activities of regional development agencies established in accordance with the Law of Ukraine "On the Principles of State Regional Policy," as well as other local development institutions, with a view to increasing their institutional capacity for the effective implementation of state regional policy | 1) increasing the institutional capacity of regional development agencies by establishing cooperation with international technical assistance projects | 2025—2027 | at least two memoranda of cooperation concluded with international technical assistance projects | Completed | Ministry for Communities, Territories and Infrastructure Development Regional development agencies have concluded 6 memoranda with the international organization EURADA, which unites regional development agencies working on economic growth in countries of the European Union and beyond. |  |  |  |  |
|  | 2) stimulating the participation of representatives of regional development agencies in educational and training programs in the areas of strategic planning, project management, and international cooperation | 2025—2027 | representatives of regional development agencies participated in at least five educational/training programs | Completed | Ministry for Communities, Territories and Infrastructure Development Based on a summary of information on the activities of regional development agencies regarding participation in educational and training programs, forums, discussions, and round tables, varying levels of activity are observed among regions, which may be due to both the organizational capacity of the agencies and the specific characteristics of regional development, the security situation, and the stage of institutional formation of individual regional development agencies (RDAs). The highest levels of participation were recorded in Poltava (95), Lviv (82 events), and Khmelnytskyi (78 events) oblasts. High activity is also demonstrated by Rivne (49), Zhytomyr (43), Mykolaiv (34), and Kirovohrad (29) oblasts, indicating systematic agency work in developing partnerships and professional cooperation. A moderate level of activity is observed in Volyn (19 events), Kharkiv (12), Ternopil (9), Luhansk and Cherkasy (7 each), as well as Kyiv and Chernivtsi oblasts (6 each). At the same time, in a number of regions the number of events is lower, in particular in Vinnytsia, Zakarpattia, Kherson, Ivano-Frankivsk, Odesa, Sumy, and Chernihiv oblasts. This situation is linked to personnel, organizational, or security-related challenges, as well as differing levels of engagement in interregional and international initiatives. In Dnipropetrovsk and Donetsk oblasts, no regional development agencies currently exist, while in Zaporizhzhia Oblast an agency was established only recently, which currently affects its level of participation in relevant events. Overall, the results indicate a positive practice of active participation by most regional development agencies in professional and communication activities, which contributes to strengthening institutional capacity, developing partnerships, and exchanging experience between regions. |  |  |  |  |
| Operational Goal 2. Development of various forms of cooperation and effective management of public investments |  |  |  |  |  |  |  |  |  |
| Area “Development of Cooperation at the Regional Level” |  |  |  |  |  |  |  |  |  |
| 93. Improvement of the regulatory and legal framework in the field of cooperation between territorial communities and promotion of the development of all forms of cooperation between territorial communities | Development of cooperation between territorial communities through the conclusion of inter-municipal cooperation agreements | 2025—2027 | no fewer than 20 new inter-municipal cooperation agreements concluded annually. |  | Vinnytsia Oblast As of 01.01.2026, the total number of cooperation projects in Vinnytsia Oblast is 26, of which 14 projects are in the fields of education, healthcare, and social services. In total, 29 territorial communities of the oblast use instruments of municipal cooperation. Volyn Oblast In 2025, 15 new inter-municipal cooperation agreements were concluded between administrative-territorial units of foreign states and Volyn Oblast. Donetsk Oblast In 2025, 4 inter-municipal cooperation agreements between territorial communities were concluded. In particular, Mariupol City Council concluded 3 agreements on cooperation between territorial communities in the form of delegating the performance of certain tasks related to the activities of the "YaMariupol" assistance centers, the "YaMariupol.Turbota" household service centers, and the "YaMariupol.Rodyna" wellness centers, with the Sartana Settlement Military-Civil Administration and the Manhush and Mykilske settlement councils. In addition, a cooperation agreement was concluded between the Sofiivka Settlement Council of Dnipropetrovsk Oblast and the Bakhmut City Military Administration of Donetsk Oblast in the form of the joint project "Reconstruction of an outpatient clinic building into a residential building" in the settlement of Sofiivka, Kryvyi Rih District, Dnipropetrovsk Oblast. Zhytomyr Oblast During 2025, 5 inter-municipal cooperation agreements were concluded in the oblast: an agreement on cooperation between territorial communities in the form of delegation of powers with the transfer of corresponding resources (material and financial) for the provision of primary medical care, dated 31.12.2025; an agreement covering social, humanitarian, medical, educational and cultural services, as well as psychosocial support for veterans and families of servicemembers, dated 27.11.2025; an agreement on cooperation between territorial communities in the form of delegation of the performance of certain tasks with the transfer of corresponding resources in the field of social protection of war veterans and demobilized persons, dated 07.11.2025; an agreement on cooperation between territorial communities in the form of joint financing (maintenance) of the Administrative Services Center of Zvyahel City Council, Zvyahel District, Zhytomyr Oblast, dated 24.06.2025; and an agreement on cooperation between territorial communities in the form of the joint project "Construction of a waste-processing enterprise", dated 20.02.2025. Also: an agreement between Semenivka Village Council and the municipality of Saint-Léger-lès-Domart (Sails-le-Lanois) (France) in the field of social protection, educational projects and the development of the volunteer movement; a memorandum between Korosten City Council and the town of Malvern (United Kingdom) in the fields of energy efficiency, municipal management, sport and culture; a partnership agreement between the city of Zhytomyr (Ukraine) and the city of Kassel (Germany); a twinning agreement between the cities of Zhytomyr and Dortmund (Germany); a memorandum of friendship and cooperation between Teteriv [community] — a cooperation agreement between territorial communities in the form of implementing the joint project "Implementation of joint project initiatives in the provision of services" — and the Jabłonna Commune (Poland); a memorandum of understanding between the city of Korosten and the Spandau district of Berlin (Germany); a memorandum of cooperation between Brusyliv territorial community and the municipality of the city of Skuodas (Lithuania); and a memorandum of cooperation between Ovruch territorial community and the city of Vincennes, Indiana (USA). |  |  |  |  |
|  |  |  |  |  | Zakarpattia Oblast As of 01.01.2026, the number of agreements involving territorial communities participating in international partnerships with municipalities of EU member states stands at 300. Zaporizhzhia Oblast. As part of the development of cooperation between territorial communities, 2 inter-municipal cooperation agreements were concluded in 2025: - an agreement on cooperation between territorial communities in the form of joint financing (maintenance) of the municipal institution "Social Services Center" of Dniprorudne City Council, Vasylivka District, Zaporizhzhia Oblast, dated 26.06.2025 (involving the Dniprorudne, Kamianka-Dniprovska city, Stepnohirsk settlement, Vodiane and Blahovishchenka rural military administrations); - an agreement on cooperation between territorial communities in the form of implementing the joint project "Together We Are Stronger" (provision of water supply services and removal of solid household waste), dated 17.12.2025 (Chernihivka settlement and Shyrokivske rural councils). Ivano-Frankivsk Oblast During 2025, 5 inter-municipal cooperation agreements between territorial communities of the oblast were concluded, bringing the total number of such agreements to 48. Also, as part of the "Shoulder to Shoulder: United Communities" project, implemented pursuant to Cabinet of Ministers Resolution No. 97 of 31.01.2025 and comprising 4 waves of the project in 2025, communities of Ivano-Frankivsk Oblast concluded memoranda with frontline "outpost" communities: Wave 1 – 6 pairs, Wave 2 – 11 pairs, Wave 3 – 29 pairs, Wave 4 – 38 pairs of communities. |  |  |  |  |
|  |  |  |  |  | Kyiv Oblast During 2025, 8 inter-municipal cooperation agreements were concluded between territorial communities of Kyiv Oblast. Kirovohrad Oblast As of 1 January 2026, territorial communities of the oblast had concluded 11 inter-municipal cooperation agreements. Within the framework of the national project "Shoulder to Shoulder: United Communities," communities of Kirovohrad Oblast have been designated as partner communities, assisting outpost communities with recovery, humanitarian and material-technical aid, and support for cultural, educational and sporting events aimed at strengthening social ties and engaging youth, among other things. In Wave I of the project, 4 communities from Kirovohrad Oblast take part; in Wave II, 10 communities; in Wave III, 26 communities; and in Wave IV, 26 communities. In total, the project covers 46 territorial communities of Kirovohrad Oblast and 55 outpost communities from Dnipropetrovsk, Donetsk, Zaporizhzhia, Luhansk, Mykolaiv, Odesa, Sumy, Kharkiv, Kherson and Chernihiv oblasts. The Haivoron, Kropyvnytskyi and Pryiutivka territorial communities of the oblast cooperate with three or more outpost communities. Communities from Waves I–III have concluded cooperation memoranda and developed agreed cooperation plans. Partnerships among communities under Wave IV are being established, and the signing of memoranda is ongoing. Luhansk Oblast In 2025, as part of the implementation of the national project "Shoulder to Shoulder: United Communities," the Kreminna Military Administration concluded 4 cooperation memoranda with territorial communities of Ukraine: the Bukachivtsi territorial community of Ivano-Frankivsk Oblast; the Kostryna territorial community of Zakarpattia Oblast; the Dolyna territorial community of Ivano-Frankivsk Oblast; and the Brody territorial community of Lviv Oblast. The Bilovodsk Settlement Military Administration concluded 3 memoranda with the Bilokrynytsia, Hoshcha and Smyha village/settlement councils of Rivne Oblast. On 30 October 2025, the Shchastia City Military Administration concluded a memorandum on community cooperation in the form of a partnership with the Dobrotvir settlement territorial community of Shevchenkove [Sheptytskyi] District, Lviv Oblast. The Bilokurakyne Settlement Military Administration concluded a partnership cooperation memorandum between the Kadubivtsi Village Council of Chernivtsi District, Chernivtsi Oblast, and the Bilokurakyne Settlement Military Administration of Svatove District, Luhansk Oblast. The Kolomyichykha Settlement Military Administration, under the national "Shoulder to Shoulder" project, signed a cooperation memorandum with the Kupchyntsi united territorial community of Ternopil District, Ternopil Oblast. The Chmyrivka Settlement Military Administration, within the framework of the national project "Shoulder to Shoulder: United Communities," signed cooperation memoranda with five territorial communities: the Velyka Omelyana territorial community of Rivne Oblast; the Hoshcha territorial community of Rivne Oblast; the Mylyatyn territorial community of Rivne Oblast; the Mlyniv territorial community of Rivne Oblast; and the Yavoriv territorial community of Lviv Oblast. In September 2025, the Lozno-Oleksandrivka Settlement Military Administration, as part of the fourth wave of the project, signed a memorandum with the Kopychyntsi city territorial community of Ternopil Oblast. On 16.12.2025, the Troitske settlement territorial community of Luhansk Oblast, as part of the implementation of the national project, signed a memorandum with the Vyshnivka rural territorial community of Volyn Oblast. In 2025, the Bilolutsk Settlement Military Administration signed 4 cooperation memoranda with territorial communities of Ukraine as part of the national project "Shoulder to Shoulder: United Communities." The Aidar Settlement Military Administration, within the framework of the national project "Shoulder to Shoulder: United Communities," concluded 5 cooperation memoranda (with the Dunaivtsi city territorial community of Khmelnytskyi Oblast, the Pechenizhyn settlement territorial community of Ivano-Frankivsk Oblast, the Yabluniv settlement territorial community of Ivano-Frankivsk Oblast, the Zhydachiv city territorial community of Lviv Oblast, and the Smidyn rural territorial community of Volyn Oblast). Lviv Oblast In total, 89 cooperation agreements between communities of Lviv Oblast have been concluded and entered into the register. In 2025, 2 cooperation agreements were concluded: between Lviv and Bibrka communities (in the form of joint financing (maintenance) of a municipal institution), and between Novokalyniv and Dobromyl communities (in the form of implementing a joint project). Mykolaiv Oblast In 2025, territorial communities of Mykolaiv Oblast concluded 19 cooperation agreements (in accordance with the Law of Ukraine "On Cooperation of Territorial Communities"). Odesa Oblast In 2025, 21 inter-municipal cooperation agreements were concluded in Odesa Oblast. Poltava Oblast In 2025, communities of the oblast concluded 6 inter-municipal cooperation agreements. Rivne Oblast Territorial communities of Rivne Oblast have concluded 120 inter-municipal cooperation agreements, of which 55 are currently in force. During 2025, communities of Rivne Oblast concluded 22 community cooperation agreements, including agreements on cooperation between territorial communities in the form of joint financing (maintenance) of municipally owned institutions and organizations, delegation of the performance of certain tasks with the transfer of corresponding resources, and implementation of joint projects. Sumy Oblast As of 01.01.2026, according to the Register of Territorial Community Cooperation Agreements, 11 inter-municipal cooperation agreements have been concluded in Sumy Oblast, of which 4 were entered into the Register in 2025. Ternopil Oblast Territorial communities of the oblast concluded 5 inter-municipal cooperation agreements in 2025. Within the framework of the Interreg NEXT Poland–Ukraine 2021–2027 programme, reconstruction is under way of treatment facilities and the sewerage system. Kharkiv Oblast. The Kharkiv Oblast State (Military) Administration promotes the development of all forms of cooperation between territorial communities. Territorial communities of Kharkiv Oblast actively make use of the opportunities set out in the Law of Ukraine "On Cooperation of Territorial Communities." In 2025, territorial communities concluded 11 inter-municipal cooperation agreements in the following areas: delegation of the performance of certain tasks in the field of education; joint financing (maintenance) of municipal institutions; and delegation of the performance of certain tasks in the field of urban planning and architecture. In addition, territorial communities of Kharkiv Oblast take an active part in implementing the national project "Shoulder to Shoulder: United Communities" (hereinafter — the Project). In total, 51 territorial communities of Kharkiv Oblast participate in the Project, having or negotiating partnership relations with 141 territorial communities from Vinnytsia, Cherkasy, Lviv, Ivano-Frankivsk, Khmelnytskyi, Kyiv, Zhytomyr, Ternopil, Zakarpattia, Rivne, Kirovohrad, Volyn, Poltava, Chernivtsi and Donetsk oblasts. |  |  |  | Kyiv Oblast. The main problematic issues hindering the development of inter-municipal cooperation are: legal inconsistencies regarding the norm on joint ownership of communities in the implementation of cooperation projects; the absence of automation of the cooperation agreement register; and a lack of financial support for the implementation of such agreements from the state, international projects and technical assistance programs. |
|  |  |  |  |  | Kherson Oblast During 2025, territorial communities of Kherson Oblast concluded 5 inter-municipal cooperation agreements, which is helping to expand partnership ties and creates preconditions for implementing joint projects with administrative-territorial units of the Republic of Moldova, the Republic of Estonia, the Republic of Croatia, Romania and the Republic of Lithuania. |  |  |  | Kherson Oblast The slowdown in the process of concluding inter-municipal cooperation agreements is due to the fact that part of the oblast's territorial communities are under temporary occupation or in an active combat zone, which affects the readiness of foreign partners to formalize long-term contractual relations. |
|  |  |  |  |  | Khmelnytskyi Oblast In 2025, as part of the national project "Shoulder to Shoulder: United Communities," 41 territorial communities of Khmelnytskyi Oblast concluded cooperation memoranda with territorial communities from 9 frontline regions; assistance was provided in the form of monetary transfers and humanitarian kits, online master classes were held, children's recreational programs were organized, and a number of joint sporting and cultural events were held. Cherkasy Oblast. Inter-municipal cooperation, an effective tool for territorial development, improving the quality of public services, and the effective exercise by local self-government bodies of their powers, is being implemented in the oblast. As of May 2024, only 8 inter-municipal cooperation agreements had been concluded in the oblast, ranking it 18th in Ukraine on this indicator. As a result of work carried out to intensify the conclusion of such agreements, significant positive changes have occurred. In 2025, Cherkasy Oblast became the leader in Ukraine in terms of the dynamics of concluding territorial-community cooperation agreements (68 agreements concluded during 2025). As of 31.12.2025, Cherkasy Oblast ranked 2nd in Ukraine in terms of the number of active inter-municipal cooperation agreements entered into the register of the Ministry for Communities, Territories and Infrastructure Development : the number of such agreements amounted to 80, including: 16 in Zvenyhorodka District, 27 in Zolotonosha District, 11 in Uman District, 14 in Cherkasy District, 10 between communities of different districts of Cherkasy Oblast, and 2 between communities of different oblasts. Key areas covered by the cooperation agreements: provision of services by municipal enterprises and institutions (social service centers, rehabilitation centers, inclusive resource centers, centers for the professional development of teaching staff, labor archives, medical institutions); joint maintenance of municipal enterprises and institutions (social service centers, educational and medical institutions, labor archive); establishment and operation of project offices; cooperation in tourism; transportation of pupils to educational institutions; urban planning and architecture; fire safety; enhancing the professional competence of local self-government officials, exchange of experience and best practices; waste management; implementation of joint projects and programs for sustainable socio-economic development; teaching of the "Defense of Ukraine" subject; provision of practical assistance and legal support to executive committees and to the transport sector; and exchange of education-management practices. In 2025, the Regional Development Department of the Cherkasy Oblast State Administration, jointly with U-LEAD with Europe in Cherkasy Oblast, UNDP Ukraine, and the "Cherkasy Regional Development Agency" institution, carried out advisory and methodological work with territorial communities and district military administrations of the oblast regarding the conclusion of inter-municipal cooperation agreements. In particular, on 17.04.2025 a Zoom meeting was held with representatives of district military administrations and territorial communities of the oblast, during which the current state of concluding such agreements in Cherkasy Oblast and key achievements in this area were presented, participants were called upon to further intensify this process, and relevant advisory and methodological recommendations were provided. In May 2025, within Uman District, all 12 communities concluded an innovative cooperation agreement establishing the "Umanshchyna Project Office"; in June 2025, 9 communities of Zolotonosha District concluded a similar agreement establishing the "Left-Bank Cherkasy Region Project Office." The main activities envisaged under these project offices include: jointly developing project ideas for participation in state and international funding programs; attracting investors and donors; jointly implementing infrastructure projects; cooperation in the fields of environmental initiatives, security and civil protection; and developing small and medium-sized business and tourism potential. In 2025, two meetings of the coordination councils were held for each of the project offices; in addition, with the participation of UNDP Ukraine and U-LEAD with Europe in Cherkasy Oblast, training was conducted for project managers of Zolotonosha and Uman districts. Also, with the support of the "Together with Kernel" charitable foundation, on 09.10.2025 a study tour was organized for participants of the "Left-Bank Cherkasy Region Project Office" to the Opishnya territorial community of Poltava Oblast. Chernivtsi Oblast. Chernivtsi Oblast has 21 inter-municipal cooperation agreements in force. Of these, 3 agreements were concluded in 2025: - 1 – between Khotyn and the Kamianets-Podilskyi, Stara Ushytsia and Kytaihorod communities of [Khmelnytskyi] Oblast, in the form of establishing the joint municipal enterprise "Ponyzzia," which unites the border territories of Bukovyna and Podillia for the development of tourism and socio-economic cooperation — the first inter-regional enterprise of this type in Ukraine. The other 2 agreements are between the Verenchanka, Horishni Sherivtsi and Kadubivtsi communities, in the form of delegating the performance of certain tasks in the field of urban planning and architecture. Chernihiv Oblast During 2025, 8 agreements were concluded. |  | Khmelnytskyi Oblast 6,500 |  |  |
| 94. Promoting the development of international territorial cooperation, in particular by building international partnerships at the regional and local level | 1) Expanding international regional cooperation by initiating partnership relations between cities and regions, as well as concluding new agreements and implementing existing partnership and cooperation agreements between cities and regions, 2027: at least five new cooperation and partnership agreements concluded between cities and regions. | 2027 | at least five new cooperation and partnership agreements concluded between cities and regions. |  | Vinnytsia Oblast In 2025, Vinnytsia Oblast worked actively to develop international territorial cooperation and expand its network of partnerships. In particular, the Vinnytsia Oblast Military Administration concluded two cooperation agreements: with Somerset County (United Kingdom) and with the Apulia Region (Italian Republic). At the same time, territorial communities of the oblast continued to consistently develop international ties, concluding partnership agreements with regions of the Republic of Poland, the Republic of Moldova, the Kingdom of Spain, Romania, the Italian Republic and the Republic of Estonia, which helps deepen inter-regional cooperation and bring international experience into the region's development. A four-party memorandum of understanding was also concluded between Vinnytsia Oblast Council, Vinnytsia City Council, and the Bourgogne-Franche-Comté Region together with the city of Dijon, French Republic. Volyn Oblast - On 9 April 2025, a large-scale event "Grant Opportunities for Communities and the Development of International Partnership" was held, organized by the Volyn Oblast Military Administration together with the Volyn Regional Development Agency, with support from the Swiss-Ukrainian UCORD project. Representatives of territorial communities of the oblast, of international programs (Interreg NEXT "Poland–Ukraine 2021–2027," UNDP, GIZ, UCORD), donor organizations and technical assistance projects took part. - On 17 July 2025, in Lutsk, the Department of External Relations and International Technical Assistance of the Oblast State Administration, together with an expert of the Regional Contact Point for the Interreg NEXT "Poland–Ukraine 2021–2027" Programme in Volyn Oblast, organized and held a meeting of project teams implementing 17 projects under the Interreg NEXT "Poland–Ukraine 2021–2027" Programme. Participants discussed cooperation in implementing the projects, ways to strengthen one another and improve efficiency, and further steps. The meeting was attended by Vasyl Khimiak, Head of the Representative Office of the Joint Secretariat of the Interreg NEXT "Poland–Ukraine 2021–2027" Programme in Lviv. - On 13 November 2025, as part of online training, the Head of the Department of European Integration and International Cooperation of the Volyn Oblast State Administration briefed representatives of Volyn communities on current grant competitions, prospects for participating in future calls for project proposals, and features of international programs, including current initiatives under the "Environment" thematic objective within the Interreg NEXT "Poland–Ukraine 2021–2027" Programme. Donetsk Oblast As of 01.01.2026, inter-regional cooperation between Donetsk Oblast and 8 regions in 5 countries across Europe, the USA and Asia is ongoing; in particular, on 07.08.2025 a memorandum of friendship and cooperation was concluded between Donetsk Oblast and the State of Connecticut (USA). At the level of the oblast's communities, inter-territorial cooperation continues with 31 foreign administrative-territorial units in 11 countries across Europe and the USA, and new international relationships are developing. Zhytomyr Oblast As part of efforts to encourage participation in EU Interreg NEXT programs, the "Impact.Zhytomyr 2.0" project-management training was organized for territorial communities of Zhytomyr Oblast. As part of the training, a forum was also held at which 14 selected community teams presented their project concepts to representatives of international organizations. |  |  |  |  |
|  |  |  |  |  | Kyiv Oblast As a result of work in 2025, new partnership agreements were concluded and existing ones renewed. In particular: - a partnership agreement with Buckinghamshire County (United Kingdom); - a partnership agreement with the state of Lower Austria (Austria); - a partnership agreement with the Central Bohemian Region (Czech Republic); - a cooperation memorandum with HD Hyundai XiteSolution; - a number of memoranda were signed during the 3rd International Summit of Cities and Regions and the URC 2025 Conference in Rome (18 memoranda concluded by communities of Kyiv Oblast and 2 agreements by the Kyiv Oblast State Administration); - a memorandum of understanding between the Kyiv Oblast Military Administration and the Seoul Metropolitan Government on the modernization of transport infrastructure. Kirovohrad Oblast. Cooperation with foreign partner regions has been intensified in the oblast under existing bilateral agreements. Thus, within the framework of the Agreement between the Kirovohrad Oblast State Administration of Ukraine and the Administration of the Lower Silesian Voivodeship of the Republic of Poland on regional cooperation, an oblast delegation took part, from 17 to 22 March 2025, in the Lower Silesian Forum for Ukraine's Recovery (hereinafter — the Forum), held in Wrocław, Lower Silesian Voivodeship, Republic of Poland. During the Forum, a Memorandum of Understanding was signed between the Kirovohrad Oblast Military (State) Administration (Ukraine) and the Administration of the Lower Silesian Voivodeship (Republic of Poland), which envisages the participation of Lower Silesian enterprises in the reconstruction of infrastructure, construction and energy in Kirovohrad Oblast; growth in bilateral trade, in particular in agriculture, energy, research and digital sectors; support for attracting Lower Silesian investment into Ukraine; and support for the participation of businesses from Kirovohrad Oblast and Lower Silesia in exhibitions, trade fairs and economic missions. Cooperation is also expanding at the level of territorial communities of Kirovohrad Oblast and regions around the world, including EU member states. Under agreements already concluded, active cooperation continues between the Kropyvnytskyi city territorial community and the communities of Krefeld (Germany) and Venlo (Netherlands); between Oleksandriia City Council and the Council of Bath and North East Somerset, United Kingdom; between the Bobrynets city territorial community and the municipality of Madona (Latvia); between the Novoarkhanhelsk settlement territorial community and the municipality of the city of Valka (Latvia); and between the Subotivka rural territorial community and the Żarki commune of the Republic of Poland. In November 2025, a protocol of intent was concluded between the Novoukrainka city territorial community of Ukraine and the village council of Selemet, Republic of Moldova. Lviv Oblast In 2025, the following were signed: - A memorandum of understanding and cooperation with the Administrative Council of Skåne County (Kingdom of Sweden); - A memorandum of cooperation with the South-East European Cooperative Initiative (SECI); - A memorandum of cooperation between the Chamber of Regions of the Congress of Local and Regional Authorities under the President of Ukraine and the Association of Self-Governing Regions of Slovakia. Mykolaiv Oblast During 2025, the following were signed: a Declaration on Cooperation and Relations between the Pervomaisk city territorial community and the community of Vejle (Kingdom of Denmark); a Letter of Intent on measures aimed at establishing partnership cooperation between the city of Nova Odesa (Ukraine) and Myślenice County (Republic of Poland); a Cooperation Pact between the municipality of Ostuni (Italian Republic) and the Koblevo rural territorial community; a Partnership Agreement between Mykolaiv City Council and the municipality of Trelleborg, Skåne County (Kingdom of Sweden); a Memorandum of Cooperation between the Berlin district of Tempelhof-Schöneberg (Federal Republic of Germany) and the city of Mykolaiv; a Memorandum of Understanding between Mykolaiv City Council (Ukraine) and the municipality of Montpellier (French Republic); a Twinning Agreement between Mykolaiv City Council (Ukraine) and the municipality of Bari (Italian Republic); a Cooperation Agreement between the city of Mykolaiv, the municipality of Narbonne and Grand Narbonne; and a Twinning Agreement between Mykolaiv City Council (Ukraine) and the special sports, cultural, tourist, business and service district of Santiago de Cali (Republic of Colombia). Odesa Oblast In 2025, 4 training sessions were provided for representatives of local self-government bodies and local executive authorities on competing for EU Interreg NEXT program projects. Also, within the framework of the "Black Sea Basin 2021–2027" Interreg NEXT grant programme, implementation continued in 2025 of 5 environmental-sector international technical assistance (ITA) projects in Odesa Oblast. In accordance with established procedure, the Odesa Oblast State (Military) Administration acts as the beneficiary of the said projects; the Director of the [relevant] Department has been designated, by corresponding orders of the Odesa Oblast State Administration, as the person responsible on behalf of the beneficiary for overseeing their implementation, and takes part in the projects' public events upon separate invitations from the project teams. Information on training sessions for the preparation and implementation of EU Interreg NEXT program projects was promptly communicated to territorial communities of the oblast. Poltava Oblast In 2025, communities of the oblast concluded 7 new bilateral documents on international cooperation. The Poltava Oblast Military Administration concluded a Memorandum of Understanding with the Council of Suffolk County, United Kingdom of Great Britain and Northern Ireland. Sumy Oblast The Sumy Oblast State Administration – Oblast Military Administration concluded 2 agreements: with the Abruzzo Region (Italy) and the Region of Murcia (Spain). In total, 8 inter-regional agreements have been signed at the oblast level. Local self-government bodies signed 2 inter-regional agreements in 2025: the Trostianets community with the city of Sylvi [Silvi], Italy, and the Konotop community with the city of Stargard, Poland (40 agreements are in force in total). Kharkiv Oblast The Kharkiv Oblast Military Administration has been consistently working to implement the Interreg programme as an effective mechanism for inter-regional cooperation. Thus, pursuant to an instruction from the leadership of the Kharkiv Oblast Military Administration dated 26 November 2024 No. 23559/2, issued in response to a letter from the Cabinet of Ministers of Ukraine dated 26 November 2024 No. 28551/0/2-24, the district military administrations of Kharkiv Oblast were informed, by letter of the Department of Economics and International Relations of the Kharkiv Oblast State (Military) Administration dated 26 November 2024 No. 07.01-11/4308, about a training session on public procurement under the Interreg and Interreg NEXT programmes held on 12 December 2024. Pursuant to an instruction from the leadership of the Kharkiv Oblast Military Administration dated 20 September 2024 No. 18648/2, issued in response to a letter from the Secretariat of the Cabinet of Ministers of Ukraine dated 19 September 2024 No. 22475/0/2-24, the military administrations of settlements and local self-government bodies of Kharkiv Oblast were informed, by letter of the Department of Economics and International Relations of the Kharkiv Oblast State (Military) Administration dated 23 September 2024 No. 07.02-12/3027, about Interreg Cooperation Day in Ukraine held online on 2 October 2024. Pursuant to an instruction from the leadership of the Kharkiv Oblast Military Administration issued in response to a letter from the Secretariat of the Cabinet of Ministers of Ukraine dated 23.06.2025 No. 15418/0/2-25 (received by the Kharkiv Oblast Military Administration on 24.06.2025, No. 12197/2), structural units of the Kharkiv Oblast Military Administration, military administrations of settlements, and local self-government bodies of Kharkiv Oblast were informed, by letters of the Department of Economics and International Relations of the Kharkiv Oblast State (Military) Administration dated 26.06.2025 No. 07.02-21/3292 and dated 26.06.2025 No. 07.02-22/3301, that on 24.07.2025 an online seminar would be held reviewing the Interreg Europe Policy Learning Platform, aimed at familiarizing Ukrainian partners with the Platform's capabilities, including examples and methodology of its use, available educational resources, and forms of expert support. Pursuant to an instruction from the leadership of the Kharkiv Oblast Military Administration dated 31.07.2025 No. 14861/2, issued in response to a letter from the Secretariat of the Cabinet of Ministers of Ukraine dated 31.07.2025 No. 19053/0/2-25, the military administrations of settlements and local self-government bodies of Kharkiv Oblast were informed, by letter of the Department of Economics and International Relations of the Kharkiv Oblast State (Military) Administration dated 27.08.2025 No. 07.02-22/4331, that following the seminar reviewing the Interreg Europe Policy Learning Platform held on 24.07.2025, the Interreg Europe inter-regional cooperation programme launched a survey to identify the most relevant EU cohesion-policy priorities via an online form. Based on the survey results, a special event is to be organized aimed at strengthening the capacity of Ukrainian organizations within the Policy Learning Platform. Pursuant to an instruction from the leadership of the Kharkiv Oblast Military Administration, issued in response to a letter from the Ministry for Communities, Territories and Infrastructure Development dated 12.08.2025 No. 29088/31/14-25 regarding the updating of information on the participation status of Ukrainian communities and regions in the EU Interreg and Interreg NEXT programmes, the military administrations of settlements and local self-government bodies of Kharkiv Oblast were informed, by letter of the Department of Economics and International Relations of the Kharkiv Oblast State (Military) Administration dated 13.08.2025 No. 07.02-22/4104, of the need to provide such information; the Department subsequently informed the Ministry for Communities, Territories and Infrastructure Development of this by letter dated 14.08.2025 No. 07.02-19/4130. Khmelnytskyi Oblast In 2025, with a view to expanding international regional cooperation, 8 international documents of the relevant type were concluded. | Kyiv Oblast 2749,0 | Kyiv Oblast 392,3 |  | Kyiv Oblast Lack of direct contacts with representatives of partner regions who can influence decision-making on the implementation of joint initiatives; lengthy delays in receiving responses from representatives of foreign regions. |
|  |  |  |  |  | Chernivtsi Oblast Chernivtsi Oblast has concluded 24 agreements on international territorial cooperation with administrative-territorial units of Romania, the Republic of Moldova, the USA, the State of Israel, the Kingdom of Sweden and the Italian Republic. Of these: 3 are at the regional level, 3 at the district level, and 18 at the municipal level. Chernihiv Oblast The "KALYNA – Together for Training in European Project Management" project is being implemented in Chernihiv Oblast (in cooperation with the Île-de-France Region). Training of specialists in the management of EU financial instruments has begun. Within the initiative, 5 trainers were selected and trained, having completed internships in France to study experience working with programmes, including Interreg NEXT. The Chernihiv Regional Advanced Training Center held a series of training events for officials of the oblast state administration, district state administrations, and local self-government bodies on the specifics of submitting applications for, and monitoring, EU projects. Within a community capacity-building project, training events were held on the conditions for participating in EU programmes, including Interreg NEXT projects, and a study visit for oblast representatives to Poland was organized. Participants studied Polish practices in developing and implementing projects funded by EU financial institutions, as well as mechanisms of inter-municipal interaction. |  |  |  | Chernivtsi Oblast. The main problematic issues are low activity among territorial communities, limited financial resources for initiating and implementing international projects, and the complexity of the procedures for preparing and agreeing international territorial cooperation agreements. |
|  | 2) Conducting training and encouraging the participation of local self-government bodies and local executive authorities in competitions for EU Interreg NEXT programme projects | 2025—2027 | at least five information events, trainings/workshops held | ongoing on a continuous basis | Secretariat of the Cabinet of Ministers of Ukraine (SCMU). During 2025, coordinated by the Secretariat of the Cabinet of Ministers of Ukraine, the following information events, trainings and workshops were held, open to participation not only by local self-government bodies and local executive authorities but also by other current and potential partners: Online training "Working in the CST System" for partners of Interreg NEXT "Poland–Ukraine 2021–2027" programme projects (25 February 2025);Training for Ukrainian partners implementing Interreg NEXT "Poland–Ukraine 2021–2027" programme projects (27 June 2025, Mukachevo, Zakarpattia Oblast); Online training for Lead Partners of the Interreg NEXT "Hungary–Slovakia–Romania–Ukraine" programme (4 March 2025);Online training/webinar on the implementation of Interreg NEXT "Hungary–Slovakia–Romania–Ukraine" programme projects (27 March 2025); A series of online trainings for partners of projects under the Interreg NEXT Romania–Ukraine 2021–2027 programme (June 2025); An information event presenting the Interreg Europe Policy Learning Platform (24 July 2025, online); Online training on preparing EU-funded projects (10–12 December 2025, Kyiv, Ukraine); A training seminar on programme management within EU cohesion policy and on management verifications under Interreg programmes (19–21 August 2025, Kyiv, Ukraine); An information campaign for Interreg Cooperation Day 2025, aimed at providing valuable information about cooperation opportunities under the Interreg and Interreg NEXT programmes through an interactive approach — a quiz for all interested parties with themed prizes. |  |  | Funding source: international technical assistance funds. | - |
| 95. Introduction of new approaches to public investment management in strategic planning documents and in the implementation of state regional policy | Development and submission to the Cabinet of Ministers of Ukraine of draft regulatory acts on strategic planning of state regional policy regarding the introduction of new approaches to public investment management | 2027 | acts of the Cabinet of Ministers of Ukraine adopted. |  | Implementation deadline has not yet arrived. |  |  |  |  |
| 96. Promoting the mobilization of international technical assistance funds and international financial organizations for the implementation of public investment projects for the recovery and development of territorial communities | Ensuring the submission by territorial communities of public investment projects through the Unified Digital Integrated Information and Analytical System for Managing the Process of Reconstruction of Real Estate, Construction and Infrastructure (DREAM) for the implementation of intergovernmental programmes | 2025—2027 | the Unified Portfolio of Priority Public Investments, approved by the Strategic Investment Council, updated | Ongoing | Ministry of Economy The State Unified Project Portfolio (hereinafter — SUPP), approved by the Strategic Investment Council (minutes of the Strategic Investment Council meeting of 26 August 2025, No. 11) and updated on 24 October 2025 by a corresponding decision of the Strategic Investment Council (minutes of the Strategic Investment Council meeting of 24 October 2025, No. 13). As of 2025, the SUPP included 195 projects and programmes worth UAH 12.54 trillion — comprising 131 projects and 64 programmes. |  |  |  |  |
| 97. Strengthening the financial capacity of local self-government bodies, creating conditions to ensure that local self-government bodies fulfill their own and delegated powers | 1) Developing and submitting to the Cabinet of Ministers of Ukraine a draft law on improving the mechanism for horizontal equalization of local budget capacity | within six months after the adoption of the Law of Ukraine on the delineation of powers between local self-government bodies of different levels, between local self-government bodies, and between executive authorities on the principle of subsidiarity | the corresponding draft law submitted to the Verkhovna Rada of Ukraine | Not started | Ministry of Finance The implementation deadline has not yet arrived. In accordance with paragraph 51 of the Operational Action Plan for the implementation of the Public Finance Management Reform Strategy for 2026–2030, approved by Order of the Cabinet of Ministers of Ukraine No. 217-r of 25.02.2026, the deadline for this measure is Q4 2028. |  |  |  | Draft laws submitted by the Cabinet of Ministers of Ukraine to the Verkhovna Rada of Ukraine, registration Nos. 6281 and 6282 of 04.11.2021, on delineating the powers of local self-government bodies in connection with changes to the administrative-territorial structure, were withdrawn from consideration in February 2023. |
| 98. Promoting the mobilization of international technical assistance funds and international organizations' funds for the purpose of protecting cultural heritage | 1) Compiling information received from local self-government bodies and central executive authorities that hold cultural heritage sites on their balance sheets, regarding the preparation and submission of project applications for participation in competitive selections of projects in the field of cultural heritage protection | 2025 | at least three project applications submitted; at least one project approved | Completed | Ministry of Culture During the reporting period, 21 project applications in the field of cultural heritage protection were prepared and submitted to international organizations for consideration (with a view to mobilizing international technical assistance funds), including: 5 from Mykolaiv Oblast Council, 2 from Kharkiv, 7 from Khmelnytskyi, and 7 from Dnipropetrovsk. Following the competitive selections, 2 projects were approved: "Through the History of Wedding Fashion," submitted by Khmelnytskyi Oblast Council (grant programme of the UCORD project "Clusters of Revival"), and "Heritage Lab: Petrykivka," submitted by Dnipropetrovsk Oblast Council (supported by PFRU "Partnership for a Strong Ukraine"). In addition, 2 projects were being implemented during the reporting year: a 3D tour under the project "Art Unites: Masterpieces of the Art Museum in a New Dimension," within the "Cohesion through Culture" grant programme (Ukrainian Cultural Foundation, with financial support from UCORD) (Volyn Oblast Council); and "Beyond Nationalities: Ethnographic and Cultural Similarities between Romanians, Ukrainians and Slovaks of the Upper Tysa Region," under the Interreg VI-A NEXT Hungary–Slovakia–Romania–Ukraine 2021–2027 Programme (Zakarpattia Museum of Folk Architecture and Life, the Satu Mare County Museum (Romania), and the Museum of Ukrainian Culture in Svidník (Slovakia)). |  |  |  |  |
|  | 2) Organizing trainings, seminars, conferences and forums for territorial communities on attracting international funding for the protection of cultural heritage | 2025—2027 | at least five events held | Completed | Ministry of Culture On 11 December 2025, the Ministry of Culture held the conference "Culture and Investment: Public-Private Partnership, Patronage, Investment Projects." The event brought together representatives of state authorities, regional administrations, cultural institutions, the business community, international organizations and experts to develop joint investment solutions in the field of culture and to discuss creating additional opportunities for financing socio-cultural infrastructure. In addition, with a view to attracting grant and investment funds for cultural heritage protection, 7 thematic events were held, including: the international scientific-practical conference "Historical and Cultural Heritage in a Border Region," held within the grant project "Beyond Nationalities: Ethnographic and Cultural Similarities between Romanians, Ukrainians and Slovaks of the Upper Tysa Region" under the Interreg VI-A NEXT Hungary–Slovakia–Romania–Ukraine Programme (Municipal Institution "Zakarpattia Museum of Folk Architecture and Life" of Zakarpattia Oblast Council); the forum "MeetUP: Traditions without Prejudice" (Dnipropetrovsk Oblast Council); the roundtable "Ukrainian Regions and Ethno-Cultural Diversity: Finding One's Path to the EU" (within the project of Oles Honchar Dnipro National University, "European Multiculturalism as an Experience and a Path for Ukraine's European Integration"); training on "Current Issues in the Functioning of the Cultural Sector in Volyn Oblast" (Volyn Oblast Council) and "Digital Heritage of Communities: Preserving Identity through Cross-Border Cooperation" (Odesa Oblast State Administration together with the Municipal Institution "Odesa Regional Center of Ukrainian Culture" and the Regional Development Agency); and a seminar on cultural heritage protection (Kyiv and Kharkiv oblast councils). | 366,622 |  |  |  |
| 99. Reforming the State Fund for Regional Development and resuming the financing of regional development projects that will help reduce disparities in the development of regions and territorial communities and ensure the efficient and transparent use of budget funds | Reforming the State Fund for Regional Development in accordance with the new public investment management system, taking into account EU practices and approaches | 2026 | The State Fund for Regional Development model agreed with the European Commission | Ongoing | Ministry for Communities, Territories and Infrastructure Development In 2025, the transitional stage of reforming the public investment management system continued, and accordingly the approach to the distribution and use of State Fund for Regional Development (hereinafter — SFRD) funds had certain particular features. Under the Law of Ukraine "On the State Budget of Ukraine for 2025," the Ministry for Communities, Territories and Infrastructure Development was allocated UAH 1 billion under the "State Fund for Regional Development" programme. Article 48 of this Law establishes that in 2025 SFRD funds are directed to the implementation of public investment projects in accordance with a procedure determined by the Cabinet of Ministers of Ukraine. On 13 August, the Government, by Resolution No. 971, approved the procedure for using SFRD funds in 2025. The main purpose of the SFRD is to support regions and territorial communities in developing infrastructure, improving the quality of services, and expanding opportunities for residents. | 656869,751 | 284899,354 |  | In accordance with Article 24-1 of the Budget Code of Ukraine, the State Fund for Regional Development is established within the state budget as a public investment programme. When drafting the Budget Declaration and the draft State Budget of Ukraine, the State Fund for Regional Development is to be determined at no less than 1.5 percent of the projected volume of general fund revenues of the draft State Budget of Ukraine for the relevant budget period. At the same time, the Law of Ukraine "On the State Budget of Ukraine for 2026" No. 4695-IX of 03.12.2025 was adopted, under which the Ministry for Communities, Territories and Infrastructure Development, as the main spending unit for the budget programme under budget programme classification code (KPKVK) 3121070 "State Fund for Regional Development," is allocated expenditures of UAH 2 billion — 15 times less than the amount envisaged by the state's Medium-Term Plan of Priority Public Investments for 2026–2028. In accordance with Article 24-1 of the Budget Code, the Ministry for Communities, Territories and Infrastructure Development is drafting a resolution of the Cabinet of Ministers of Ukraine, "Certain Issues of the State Fund for Regional Development," which proposes to approve the Procedure for the preparation, assessment and prioritization of medium-term plans of priority public investments of regions (territorial communities) that may be implemented using State Fund for Regional Development funds, and the Procedure for using State Fund for Regional Development funds (including conditions for co-financing from local budgets). With a view to bringing the mechanisms for the functioning of the State Fund for Regional Development closer to EU structural funds, consultations are being held on the draft act with representatives of the European Union, the European Commission (the Directorate-General for Neighbourhood and Enlargement Negotiations (DG NEAR) and the Directorate-General for Regional and Urban Policy (DG REGIO)), and other stakeholders (the World Bank, EU4Reconstruction, etc.). |
| 100. Introducing the Unified Digital Integrated Information and Analytical System for Managing the Process of Reconstruction of Real Estate, Construction and Infrastructure (DREAM) to ensure end-to-end management of investment projects at the regional and local level | 1) Developing and submitting to the Cabinet of Ministers of Ukraine a draft resolution approving the Procedure for the operation of the Unified Digital Integrated Information and Analytical System for Managing the Process of Reconstruction of Real Estate, Construction and Infrastructure (DREAM) | 2025 | a resolution of the Cabinet of Ministers of Ukraine adopted | Ongoing | Ministry for Communities, Territories and Infrastructure Development In 2025, the Ministry for Communities, Territories and Infrastructure Development developed a draft resolution of the Cabinet of Ministers of Ukraine, "Certain Issues Concerning the Operation of the Digital Integrated Information and Analytical System for Coordination and Monitoring of Public Investment Projects and Public Investment Programmes (DREAM)," which was sent for approval to interested central executive authorities by letter dated 23.05.2025 No. 609/31/63-25. However, the Ministry of Finance did not support the draft act, noting that it does not support regulating the operation of the DREAM system separately from determining the procedure for operating the Unified Information System for Managing Public Investment Projects (the "Concept"), which should be aligned with the architecture of the unified digital ecosystem for public investment management. Taking the Ministry of Finance's comments into account, the Ministry for Communities, Territories and Infrastructure Development, together with the Ministry of Finance and the Ministry of Economy, agreed on a draft Concept for the Unified Information System for Managing Public Investment Projects and the role of the DREAM system within it. The revised draft act was resubmitted for approval to interested central executive authorities by letter dated 12.09.2025 No. 1233/31/63-25. The Ministry of Finance again did not support the draft act. |  |  |  | Item 39 of Task 5 of the roadmap implementation action plan provides for "developing a concept for a unified digital ecosystem for public investment management based on an updated methodological framework, describing its main components, including the Unified Digital Integrated Information and Analytical System for Managing the Process of Reconstruction of Real Estate, Construction and Infrastructure (the DREAM ecosystem) (a single bank of projects that have passed established evaluation and selection procedures, with monitoring arrangements), the Ministry of Finance's IT systems for planning and monitoring the execution of state and local budgets (reflecting projects selected for funding in the budget), Prozorro (procurement planning and implementation), the Treasury (project financing execution), and their mutual integration to ensure end-to-end process management" (hereinafter — the Concept). The lead implementer of this measure is the Ministry of Finance, and the deadline for the measure was envisaged as May 2025. The draft Concept was sent by the Ministry of Finance to the Ministry for Development of Communities and Territories for approval by letter dated 13.11.2025 No. 55000-07-5/32908, and was approved by the Ministry for Communities, Territories and Infrastructure Development with comments. After processing comments from central executive authorities, the Ministry of Finance, by letter dated 02.03.2026 No. 55000-07-5/32908, resubmitted a draft order of the Cabinet of Ministers of Ukraine on approving the Concept to the Ministry for Communities, Territories and Infrastructure Development. This draft act was approved with comments by letter of the Ministry for Communities, Territories and Infrastructure Development dated 05.03.2026 No. 5465/31/10-26. The draft act approving the Concept has not yet been adopted. Once the Government adopts the act approving the Concept, the Ministry for Communities, Territories and Infrastructure Development will submit to the Government the corresponding draft act to implement measure 1) of Task 100 of the State Strategy for Regional Development Action Plan. |
|  | 2)Ensuring public access to data on reconstruction projects placed in the Unified Digital Integrated Information and Analytical System for Managing the Process of Reconstruction of Real Estate, Construction and Infrastructure (DREAM) at all stages, including planning, financing, procurement, construction and commissioning, in order to ensure open and transparent monitoring of project implementation and better coordination of recovery efforts across sectors | 2025 рік | the functionality of the DREAM system provides access to public data on reconstruction projects at all stages | Completed | Ministry for Communities, Territories and Infrastructure Development The functional purpose of the DREAM system is precisely to provide digital support throughout the life cycle of a project or programme. DREAM is currently defined as a key digital tool of the public investment management (PIM) reform, ensuring efficiency, integrity, transparency and accountability in the allocation of state and international funds at every stage of a project's life cycle: preparation, development, prioritization, securing funding, procurement, implementation and monitoring. At present, the DREAM system provides: a structured display of projects and programmes; traceability of a project's progress from initiation to implementation; display of its inclusion within relevant portfolios; links to funding data; links to procurement through integration with the Prozorro e-procurement system; tracking of implementation stages; and public availability of information sufficient for public oversight and monitoring. Currently, 978 communities and 23 regions have already approved their own medium-term plans of priority public investments, and 826 communities and 23 regions have formed unified project portfolios, which are reflected in the DREAM system. |  |  |  | Item 39 of Task 5 of the roadmap implementation action plan provides for developing the aforementioned Concept, with the Ministry of Finance as lead implementer and a deadline originally envisaged for May 2025 (see details above). Within the implementation of this Concept, a phased adaptation of the functional capabilities of the system to the requirements of the PIM reform is envisaged, in particular expanding its functionality to support the full cycle of preparation, evaluation, prioritization and monitoring of projects and programmes. Following such adaptation, and after corresponding amendments are made to regulatory legal acts, it is envisaged that the system will be given an updated name — the Digital Integrated Information and Analytical System for the Preparation and Monitoring of Public Investment Projects and Public Investment Programmes (DREAM) — and will be defined as a functional component of the Unified Information System for Managing Public Investment Projects. |
|  | 3) Ensuring that the Unified Digital Integrated Information and Analytical System for Managing the Process of Reconstruction of Real Estate, Construction and Infrastructure (DREAM) is put into industrial operation | 2025—2026 | an order of the Ministry for Communities, Territories and Infrastructure Development issued | Ongoing | Ministry for Communities, Territories and Infrastructure Development In accordance with Order of the Ministry for Communities, Territories and Infrastructure Development No. 1289 of 20.08.2025, the software of the Unified Digital Integrated Information and Analytical System for Managing the Process of Reconstruction of Real Estate, Construction and Infrastructure was put into pilot (trial) operation. The modernization of the DREAM ecosystem as an informatization tool, and the introduction of new functional capabilities, are being carried out in accordance with the requirements set out in Resolution of the Cabinet of Ministers of Ukraine No. 205 of 21 February 2025, "Certain Issues Concerning the Creation, Administration and Operation of Informatization Tools," and constitute a phased process requiring significant resources and time. |  |  |  |  |
|  | 4) Modernizing and expanding the functionality of the Unified Digital Integrated Information and Analytical System for Managing the Process of Reconstruction of Real Estate, Construction and Infrastructure (DREAM), including creating auxiliary technical tools for the preparation, evaluation and analysis of the implementation of investment projects | 2025—2027 | modernized functionality put into operation | ongoing on a continuous basis | Ministry for Communities, Territories and Infrastructure Development In accordance with subparagraph 3 of paragraph 2 of Resolution of the Cabinet of Ministers of Ukraine No. 527 of 28 February 2025, "Certain Issues of Public Investment Management" (as amended by Resolution No. 1049 of 26 August 2025), pending the entry into force of a Cabinet of Ministers regulatory act determining the procedure for the operation and components of the Unified Information System for Managing Public Investment Projects, the preparation and evaluation of public investment projects and public investment programmes, the formation of the state's unified project portfolio and sectoral portfolios, and the entry and updating of information on the implementation of public investment projects and programmes, are carried out using the software tools of the DREAM ecosystem. The modernization of the DREAM ecosystem as an informatization tool, and the introduction of new functional capabilities, are being carried out in accordance with the requirements set out in Resolution of the Cabinet of Ministers of Ukraine No. 205 of 21 February 2025, and constitute a phased process requiring significant resources and time. |  |  |  |  |
| 101. Introducing a systematic approach to the preparation, screening, prioritization, selection, risk identification, implementation, monitoring and performance evaluation of public investment projects at the regional and local level for subsequent budget financing and the provision of state support | 1) Developing and approving methodological recommendations on the preparation, screening, prioritization, evaluation, selection, risk identification, implementation, monitoring and performance evaluation of public investment projects at the regional and local level, with a clear division of functions among process participants | 2025 | an order of the Ministry of Economy issued | Ongoing | Ministry of Economy The Ministry of Economy developed and approved, by corresponding orders: - Methodological Recommendations on conducting an analysis of the environmental consequences and impact of implementing a public investment project on the natural environment, and an analysis of compliance with inclusiveness and barrier-free-access requirements, as well as compliance with the Sustainable Development Goals, during the preparation of a public investment project at the state, regional and local level (Order of the Ministry of Economy, Environment and Agriculture of Ukraine No. 353 of 28.08.2025); - Methodological Recommendations on the procedure for establishing and operating local investment councils, and Methodological Recommendations on the procedure for developing and monitoring the implementation of a region's (territorial community's) medium-term plan of priority public investments (Order of the Ministry of Economy, Environment and Agriculture of Ukraine No. 352 of 28.08.2025); - Model Regulations on the public investment management unit at the central, regional and local level (Order of the Ministry of Economy, Environment and Agriculture of Ukraine No. 2942 of 06.08.2025). |  |  |  |  |
|  | 3) Conducting training for representatives of oblast state (military) administrations and local self-government bodies on the public investment management system through the preparation, screening, prioritization, selection, risk identification, implementation, monitoring and performance evaluation of public investment projects | 2025—2027 | at least five trainings held | Ongoing | Ministry for Communities, Territories and Infrastructure Development During the reporting period, a number of training events on public investment management were held for representatives of oblast state (military) administrations, local self-government bodies and other institutions, including: - a presentation on using the Guide to Managing the Implementation of Public Investment Projects; - training on the institutional support of public investment management units at the regional and local level; - a practical seminar entitled "Public Investment Management Reform: Practical Aspects of Implementation." |  |  |  | With a view to completing the formation of a coherent regulatory model for the operation of the digital public investment management system, the Ministry of Finance of Ukraine has prepared a draft Concept for a Unified Digital Ecosystem for Public Investment Management and a corresponding action plan for its implementation, which will, among other things, provide for the regulatory framing of the use of the DREAM system as one of the tools for public investment management, and the phased integration of the DREAM system with the information systems of the Ministry of Finance of Ukraine, the Ministry of Economy of Ukraine, the State Treasury Service of Ukraine, and other state information resources. As part of its proposals on the draft UIS Concept, the Ministry for Communities, Territories and Infrastructure Development proposed to address, via a Cabinet of Ministers resolution, the need to update the regulatory framework governing the operation of the DREAM system. As of now, the Ministry for Communities, Territories and Infrastructure Developmenthas prepared a draft Cabinet of Ministers resolution to approve an updated Regulation on the DREAM system as a component of the UIS. Modernization of the DREAM system will be carried out on an ongoing basis in accordance with new regulatory legal acts, as well as in accordance with amendments made to existing regulatory legal acts. |